## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-147-RAIL-BRUNT-Track Drainage Rev.0 | itp |  |  |  |  | ITP-147-RAIL-BRUNT-Track Drainage Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-147-RAIL-BRUNT-Track Drainage
label | ITP Description: Track Drainage
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 28/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - MTM Type Approval Product Register
label | Reference - A9402
checkpoint | 1.3 - MTM Track Drainage Standard
label | Reference - L1-CHE-STD-030
checkpoint | 1.4 - VicRoads Section 701
label | Reference - VicRoads Section 701
checkpoint | 1.5 - VicRoads Section 705
label | Reference - VicRoads Section 705
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Supply of:
label | – HDPE Slotted Pipe
label | – Geofabric
label | Reference - A9402 L1-CHE-STD-030 Section 701
label | Acceptance Criteria - To be type approved by MTM.
label | ○ Drainage Pipes to be supplied in accordance to Section 701
label | ○ To be inspected upon delivery to have no damage.
label | Method - Visual Measure, Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Supply of:
label | – LDPE Liner
label | – Clean Stone
label | – Bedding Sand
label | – Beaching Rock
label | Reference - L1-CHE-STD-030 Section 701
label | Acceptance Criteria - To meet L1-CHE-STD-030 requirements.
label | ○ Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 & Table 701.092
label | ○ To be inspected upon delivery to have no damage.
label | Method - Visual Measure, Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Supply of:
label | – Riser
label | – Standard Headwall
label | – Class D Pit Cover
label | Reference - L1-CHE-STD-030 Section 705
label | Acceptance Criteria - To meet L1-CHE-STD-030 requirements.
label | ○ To be supplied in accordance to Section 705
label | ○ To be inspected upon delivery to have no damage.
label | Method - Visual Measure, Document Review
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Primary Documentations
label | Reference - A4263 PTDT Form B - Track Certifier Booking Form
label | Acceptance Criteria - Approved PTDT
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved Permit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Pre-Commencement of Work
label | Reference - ITP, Quality Checklist, SWMS
label | Acceptance Criteria - All approved by relevant representative.
label | Method - Document review and approval
label | Frequency - Once (Prior to Works)
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Approved Templates
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Survey Track Drainage Alignment & Pits
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation.
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE Supervisor, Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Records & Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Grade Existing Open Cess Drain
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Grade through existing cess drain alignment to depth indicated on design documentation.
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Excavate Slotted Pipe Drainage Trench
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Place the Following and Compact:
label | – Bedding Sand
label | – Geofabric
label | – Slotted Pipe
label | – Stone
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable).
label | ○ Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
label | (a) Bedding
label | – Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (b) Backfill
label | (i) Material of nominal size 40 mm or less after compaction
label | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (ii) Material of nominal size greater than 40 mm after compaction
label | – Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure.
label | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | ○ Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation.
label | Attach: Compaction Test Reports
label | Method - Visual Inspection, Survey / Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site, Compaction Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Pit, Headwall & Beaching Rock Installation
label | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
label | Method - Visual Inspection, Measure
label | Frequency - As Task Progresses
label | Category - HP
label | Responsibility - SE/PE Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: Photos on site
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-Construction Activities
checkpoint | 6.1 - Track Certification
label | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
label | Acceptance Criteria - Track Geometry Conformance Certificate
label | ○ Track System and Component
label | Method - Visual Measure, Document Review
label | Frequency - Once (upon completion of occupation works)
label | Category - HP
label | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
label | Verifying Documents - This ITP Signed Off
label | Attach: Relevant Conformance Certs as per acceptance criteria
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - As-Built Drawings
label | Reference - As-Built Drawing Management Procedure (A8197) Section 701
label | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM.
label | ○ Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
label | Method - Document review and approval
label | Frequency - Once
label | Category - HP
label | Responsibility - SE/PE Supervisor
label | Verifying Documents - This ITP Signed Off
label | Attach: As-Built Survey Pickup
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MTM Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP