## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 04 - Irrigation | itp |  |  |  | Yes | ITP 04 - Irrigation | 18906d78-8c63-446b-9596-a404b809030a
checkpoint-group |  |  | section | PRELIMINARY APPROVALS
checkpoint-status |  |  | checkpoint | 1 - Design Review and Approval
label | 4ad9ce0e-b184-59c3-9583-7e7860dab499 |  | note | Acceptance Criteria: Irrigation design drawing has been approved - ensure design meets plumbing requirements and is suitable for intended irrigation needs. Review by licensed plumber and sign off by client.
label | ba678110-c559-5ca4-85fe-d0d4957b8614 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Material Review and Approval
label | 48910b94-4298-598a-84d1-98576b216639 |  | note | Acceptance Criteria: Irrigation material samples and material types have been approved
label | 175fded9-bc84-51cc-a02d-159ec79607af |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Coordination and Permit Acquisition for Live Area Work
label | 44dd6e86-edc9-5f29-9e17-654b8f1bea79 |  | note | Acceptance Criteria: All necessary permits for work within live areas obtained. Compliance with zoning and site work plans documented through coordination efforts.
label | 2992e66f-a752-59a7-b92a-f5f7e229587d |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | MATERIAL INSPECTION
checkpoint-status |  |  | checkpoint | 1 - Inspection of Delivered Materials
label | bd804dbf-4421-5f75-9e97-ed81004c5e82 |  | note | Acceptance Criteria: Upon delivery of piping, fittings, valves, and other materials. Check for damage, ensure specifications (size, material type) match the project requirements, and materials meet approvals.
label | c0d1e62b-cd2d-5bcc-ab6d-9633488700e2 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | PENETRATIONS
checkpoint-status |  |  | checkpoint | 1 - Review of Scanning Reports for Area Penetration
label | 6f7ad92c-b62c-5877-a024-a6c4b6301a4e |  | note | Acceptance Criteria: Scanning reports for areas to be penetrated are reviewed to ensure avoidance of existing services and structural elements.
label | 05017ec0-4c57-5f65-b6d9-39736007a854 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 2 - Engineering Approval
label | 6d9a1ed5-7ec3-5068-85ab-c1e4a2882378 |  | note | Acceptance Criteria: Obtain approval from a licensed engineer for all proposed penetrations, ensuring they do not compromise structural integrity or interfere with other building services.
label | 31c8c7d2-23ee-53dc-bd2a-2f597d408a7d |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Penetration Execution (Peno)
label | 119e4a82-b9c3-599a-8d96-13025e3a186f |  | note | Acceptance Criteria: Proceed with penetrations only after engineering approval and successful scanning.
label | 8365609a-5228-5e08-913b-782c4f0d5af8 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 4 - Waterproofing Coordination
label | acfbab36-17cf-5629-8996-ffdbd2e820eb |  | note | Acceptance Criteria: Verify waterproofing has been completed by the designated contractor and ensure its integration with our scope of work is documented.
label | 1be91ed1-8985-5e89-9b18-84122852d742 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | IRRIGATION INSTALLATION
checkpoint-status |  |  | checkpoint | 1 - Rough-In Plumbing Installation
label | fc13fb1a-09b3-591e-8660-8d66f1422983 |  | note | Acceptance Criteria: Poly pipework for water points is installed according to approved design, securely and correctly. Installation is visually inspected and approved by site plumber.
label | 5f7d6012-75be-5321-9509-8ecfb90c2405 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Vertical Cabling for Irrigation Control
label | 6cc90ef2-b4a2-5bf7-9931-55788df2cb6a |  | note | Acceptance Criteria: Ensure vertical cabling to centralized controllers is installed using scissor lifts or similar equipment under strict safety controls, with all installations matching the design.
label | 5afe074b-4544-52e2-90ba-20d6612fe6bd |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 3 - Dripline Irrigation System Installation
label | 0799a116-4658-5d4a-aef1-af829e26a66b |  | note | Acceptance Criteria: Dripline system is installed as per design, with secure placement and proper connection to water sources. System passes visual inspection, ensuring it's ready for testing.
label | 931295bc-e72f-5bbf-b77f-95503f90177e |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 4 - System Testing and Commissioning
label | 61647b87-41a3-5728-9d99-50e7d1eaa447 |  | note | Acceptance Criteria: The irrigation system undergoes pressure testing for leaks and functional testing of automation. Testing results meet project standards, ensuring system is operational and effective.
label | 40f178c1-b5e0-5b98-abe8-d715f790fa3d |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | HANDOVER
checkpoint-status |  |  | checkpoint | 1 - ITP and Handover Approval
label | 74dc665a-166f-5ca8-9420-9ad5e0c1691d |  | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | 543c0744-d5c3-58a5-bef1-7d8936bc99fd |  | note | Assignees and Verification Method: Client - Surveillance, Internal - Surveillance
checklist-sectioned |  |  | checklist | ITP 01 - Soft Landscaping | itp |  |  |  | Yes | ITP 01 - Soft Landscaping | 1b2031f4-cac1-493c-b5e0-c6d84322abdb
checkpoint-group |  |  | section | PRELIMINARY APPROVALS
checkpoint-status |  |  | checkpoint | 1 - Insulation, Drainage Cell, and Geo-fabric Approval
label | b8ef2fee-35fa-5271-892e-f7c9ef44a25e |  | note | Acceptance Criteria: Insulation, drainage cells, and geofabric specs submitted and approved per project requirements.
label | ceb83ab0-e429-5f65-b43b-dd2844c47a9c |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Soil Quality Testing
label | caea6de2-a468-508e-a851-162a412d20c3 |  | note | Acceptance Criteria: Test results documented and approved.
label | 5fa03cb4-4e24-5dd3-a137-19e0d35e3038 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Mulch Type Approval
label | 100c8d71-97aa-51d6-b900-f249a8574670 |  | note | Acceptance Criteria: Mulch type sample and data sheet approved.
label | 4e7c906a-f8d5-584c-9699-ce2d09373a18 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Plant Substitution Approval
label | ace97410-b6b5-566d-a907-068cfaaf1051 |  | note | Acceptance Criteria: Substitutes listed and approved.
label | a08ac1e0-3632-5b58-95b1-15b93c6440d8 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Nursery Visit with Architect for Plant Selection
label | 22815331-cba2-5ba1-bdba-98a3a2b7ea99 |  | note | Acceptance Criteria: Plants inspected and selection approved by the architect.
label | 080a614d-3e38-5844-8ba2-9411721ca2b0 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | ON-STRUCTURE GARDEN BED & PLANTER INFILL
checkpoint-status |  |  | checkpoint | 1 - Installation of Insulation Layer (for Green Roof Only)
label | 6feabdb1-588f-5ed5-b545-47b8619f64b4 |  | note | Acceptance Criteria: 20mm insulation layer correctly installed, inspected, and approved by foreman. Photo evidence and docket.
label | c5a506af-160b-5a4f-80ac-1694fa6795e2 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 2 - Installation of Coreflute
label | 984713d3-03eb-5099-a125-26e1478674f8 |  | note | Acceptance Criteria: Coreflute installed as per specifications, inspected, and approved by foreman. Photo evidence.
label | 53103a9b-28a7-5565-bacf-b3a20cdfe4ef |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 3 - Geo-fabric Laying
label | cbb5481b-4ae2-585e-99e2-18aa49fbc75a |  | note | Acceptance Criteria: Geo-fabric properly laid out, inspected, and approved by foreman. Photo evidence.
label | 8173b132-8488-5139-bd46-3e2717cbce73 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 4 - Drainage Cell Installation
label | ec8c98cf-b4ef-5d60-a5f2-b4885a33f923 |  | note | Acceptance Criteria: Drainage cells installed correctly, inspected, and approved by foreman. Photo evidence.
label | 0483970e-ec6c-5075-b12a-8d2178902029 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 5 - Soil and Mulch Type Verification
label | ce47ae28-77cb-505a-a904-1c16d9561311 |  | note | Acceptance Criteria: Soil and mulch added to specified levels, correct type, inspected, and approved by foreman. Docket to be retained.
label | 530ddffd-c9b7-5765-b282-39a11c1b0e2c |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | PLANTING
checkpoint-status |  |  | checkpoint | 1 - Delivered Plant Health Inspection
label | d2f70db9-22ef-5341-9ffa-da3c3d283076 |  | note | Acceptance Criteria: Health and accuracy verified, approved by foreman.
label | 9b56e006-50ed-5a17-9d05-e3f524836f9f |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 2 - Verification of Plant Layout According to Design
label | 1bb9bc16-f44a-59de-8427-c81b4ba5004a |  | note | Acceptance Criteria: Plant placement matches the design plans, approved by foreman and client.
label | 9fb33af8-55b8-58d0-89a0-23d7b40048ca |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Tree Securing and Stability Inspection
label | 9ca0c0d9-7888-508a-b99f-3aaffc1fd5bb |  | note | Acceptance Criteria: Anchoring methods inspected, approved by foreman.
label | 154ab456-8241-5793-a7bd-1ad3c0d00b81 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 4 - Installation and Inspection of Tree Inspection Risers
label | 63f8ab82-13a0-525f-80cb-7985575b21e6 |  | note | Acceptance Criteria: One inspection riser per tree within planters installed and inspected for compliance with specifications.
label | a6f9fb41-eaa7-550f-a867-be082b115ade |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | HANDOVER
checkpoint-status |  |  | checkpoint | 1 - ITP and Handover Approval
label | 845c90d3-69ae-5d79-b9df-6cb7da97a2a3 |  | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | 2a04082e-04a7-5682-887a-823fc1b0be7f |  | note | Assignees and Verification Method: Internal - Surveillance, Client - Surveillance
checklist-sectioned |  |  | checklist | GFPS-AU - Electrofusion Installation Checklist |  |  |  |  | Yes | GFPS-AU - Electrofusion Installation Checklist | 502cc8d3-a392-4741-a0ad-02c4145a792c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details:
text | 7985d927-869e-5fa3-aa1c-b0de39b4c29e |  | textbox | Project Name
date | 1c4a1da0-0029-5ffb-873d-52685f2cd4aa |  | date | Installation Date
text | c015a27a-58dd-5215-858d-fb062547433c |  | textbox | Welder’s Name
text | 2e21039d-fdd2-5249-a235-ff02d12dffea |  | textbox | Welder’s ID
text | 021444b5-6fd1-54c2-b033-343f894d4d9f |  | textbox | Company Name
text | faf00e57-7e0a-5d1a-905a-2a7f70232600 |  | textbox | Pipe Brand
date | 08cdd5e0-bbd7-5c63-ac88-c67f71a9a18d |  | date | Pipe Date
text | d185eee3-c2a2-5db8-8784-e91d6370fac9 |  | textbox | Welding Machine Model
text | f6ab01fd-a68f-557b-94e8-cfaa35d683b3 |  | textbox | Welding Machine S/N
text | 215d1dda-767c-545c-9599-1d4528558f00 |  | textbox | Fitting Brand
text | dfb420e4-18d7-56eb-bd34-4a4be154535e |  | textbox | Fitting Batch No.
radio | 9bbaf4e2-45bf-540a-bc5a-ab4063c302b9 |  | radio | Is the machine calibrated? (please select) | Yes,No
checkpoint-group |  |  | section | 1. Clean pipe surface
checkpoint-status |  |  | checkpoint | Weather Concerns:
button | a51558f6-af5f-50d5-a344-a98e8239789a |  | button | Rainy? | Yes,No
button | 91dc0f55-0e97-5685-9225-13c40862c9c6 |  | button | Windy? | Yes,No
checkpoint-status |  |  | checkpoint | Environmental Concerns:
button | 7a0d765e-4254-5c8d-a953-5f2affea398f |  | button | Clay, dirt, bentonite etc. present? | Yes,No
checkpoint-status |  |  | checkpoint | Wash pipe with clean water and clean rag.
checkpoint-group |  |  | section | 2. Pipe inspection
checkpoint-status |  |  | checkpoint | 2.1 Dimensions
label | 8a2f2d09-d996-5f4d-9183-5e811b9cbebd |  | note | Tooling: use Diameter / Pi tape to measure.
text | dc5be16c-5a74-5bae-bc24-1cb45521c2f1 |  | textbox | ○ Pipe OD: |  |  | mm
text | 7b422527-8371-5dbb-95c2-cc72d1c87d0f |  | textbox | ○ Pipe SDR:
text | abfb343a-0d62-5360-b420-0069add593f1 |  | textbox | ○ Min OD: |  |  | mm
text | a8b91cdd-8ace-5786-9687-24ad8ba84cfe |  | textbox | ○ Max OD: |  |  | mm
label | 1ce6247c-eb53-5e8a-b5ef-7a85010f3129 |  | note | Reject under-size pipe.
checkpoint-status |  |  | checkpoint | 2.2 Pipe Surface
button | 7bdcbee0-bd2f-529e-8986-9cecd6aa699b |  | button | ○ Check for flat spots, using an ovality gauge: | Yes,No
label | 9f5e474d-438d-53a2-bd4a-9d22f148beff |  | note | If Yes, reject all pipes with flat spots.
label | 323e6698-9d60-5687-9563-2f4c3c6359e6 |  | note | ○ Pipe gouges or damaged: reject or cut pipe
checkpoint-status |  |  | checkpoint | 2.3 Pipe Ovality
label | c4394ced-8bd9-5725-82ae-9de158ede9d5 |  | note | Must use re-rounding tools, if ovality exceeds:
label | 9421ece0-097c-5e10-91bb-b31607007b98 |  | note | ○ 3mm or 1.5%xDN for pipe ≤ 315mm OD
label | d7e8e8b4-1093-5a91-994c-ce8a53c9b96d |  | note | ○ 5mm or 1%x DN for pipe ≥ 355 -800mm OD
checkpoint-status |  |  | checkpoint | 2.4 Pipe Reversion
label | 65eeb227-c591-5a88-a286-5e36be6508e9 |  | note | Check pipe end reversion using a steel ruler or sprit level (straight edge).
label | a291a613-d568-53eb-abdb-2d10894e11fa |  | note | Pipe ends with toe-in (tapered edge) must be cut off.
checkpoint-group |  |  | section | 3. Square pipe end
checkpoint-status |  |  | checkpoint | 3.1 Cut pipe square at 90° angle, checked using a builders square.
checkpoint-status |  |  | checkpoint | 3.2 Use deburring tool to remove swarf and sharp edges from the pipe end.
checkpoint-group |  |  | section | 4. PE Fitting inspection
checkpoint-status |  |  | checkpoint | PE Fitting inspection
text | fd9c331d-118b-50ce-b197-08a190f4ff18 |  | textbox | Fitting’s SDR:
button | fccecd26-310c-56e7-a10e-e7ef29ea642b |  | button | Check SDR Range / Pipe Compatibility: | Yes,No
text | 93085e88-cd33-57a7-9e7f-796a390504c0 |  | textbox | Fitting Resistance (Ohms):
checkpoint-group |  |  | section | 5. Pipe peeling length
checkpoint-status |  |  | checkpoint | Measure half the length of the fitting, plus an additional 20 mm and mark on the pipe.
checkpoint-status |  |  | checkpoint | Pipe peeling length
text | ba28546c-b495-517b-bf49-08616ed33b68 |  | textbox | (half length of the fitting) + 20mm (pipe peeling length) = |  |  | mm ¦ mm
checkpoint-group |  |  | section | 6. Peel pipe: minimum 2 peels CRITICAL FACTOR Use GF Rotary Peeler to ensure the peeling quality.
checkpoint-status |  |  | checkpoint | 6.1 Check: The peeling tool blade is sharp. Replace the blade if necessary.
label | daf89a09-d14d-56e6-a48c-f3e8fa8b5375 |  | note | Measure 1st peel thickness.
checkpoint-status |  |  | checkpoint | 6.2 Measure peel strip thickness with Micrometre or Vernier Callipers (+0.01 mm tolerance)
label | dfd8ea68-e295-58fa-ace3-98e46f564ef5 |  | note | ○ d63-d315 Pipe: 0.3 - 0.5mm
label | c517d141-b1fa-5c84-a7a4-a4bafa80042a |  | note | ○ >d315 Pipe: 0.4-0.6mm
label | 538be644-9e64-5a26-a4de-f2abf4018e92 |  | note | Measure 2nd peel thickness.
checkpoint-status |  |  | checkpoint | 6.3 Never peel more than the minimum peeled pipe OD, as mea- sured using Diameter tape.
checkpoint-status |  |  | checkpoint | 6.4 Peeling records:
label | 10d1c28c-761d-5c94-acf2-6974314bcfad |  | note | ○ 1st peel: |  |  | mm
label | ac0ec24f-be9d-5ed0-a026-b766e03dbab9 |  | note | ○ 2nd peel: |  |  | mm
label | 8b560bca-2159-5bd1-911c-c221277aa483 |  | note | ○ 3rd peel: |  |  | mm (if necessary)
label | 70d39246-78a1-563d-8ff7-68a4b19fc34c |  | note | ○ 4th peel: |  |  | mm (if necessary)
checkpoint-group |  |  | section | 7. Clean peeled area only, using manufacturer approved > 90% Alcohol wipes
checkpoint-status |  |  | checkpoint | 7.1 Only wipe inside the peeled zone to prevent introducing contamination, outside the unpeeled area.
label | 87a77ab5-fb9e-517b-9386-313f7a13c4ca |  | note | CRITICAL FACTOR
checkpoint-status |  |  | checkpoint | 7.2 Wipe away from the pipe end in one direction - not back and forth.
checkpoint-status |  |  | checkpoint | 7.3 Alcohol solution must ful- ly evaporate / flash off prior to joint assembly.
checkpoint-group |  |  | section | 8. Mark pipe insertion depth
checkpoint-status |  |  | checkpoint | 8.1 Using a marking pen, measure half the length of the fitting.
checkpoint-status |  |  | checkpoint | 8.2 Measure and mark the pipe end, at 4 points around the pipe circumference.
checkpoint-status |  |  | checkpoint | If necessary, pipe reround- ing clamps can be installed at the pipe insertion depth mark.
checkpoint-group |  |  | section | 9. Insert pipe into fitting and check annular gap, with align- ment clamps fitted
checkpoint-status |  |  | checkpoint | 9.1 Note gaps?
text | 7ebac809-da66-563b-afaa-5d3dc20aac0e |  | textbox | If Yes, how big is the gap? |  |  | mm
checkpoint-status |  |  | checkpoint | 9.2 Check: annular gap should be evenly distributed around the socket mouth.
checkpoint-status |  |  | checkpoint | Straightening clamps can be used when pipe curvature (i.e. coiled pipe) prevents smooth insertion into the fitting, including prevention of pipe misalignment.
checkpoint-group |  |  | section | 10. Electrofusion Welding
checkpoint-status |  |  | checkpoint | Electrofusion Welding
button | 6ca8caca-765a-5c19-8297-05f83e45b225 |  | button | ○ Is manufacturer’s welding time completed? | Yes,No
button | d0af5831-e7d1-5f34-aca6-4347b926b1d8 |  | button | ○ Are there any Welding Machine Error Message? | Yes,No
text | 5c1e44bc-f349-5385-bc12-de0f9120eb0f |  | textbox | If Yes, what are the error messages?
checkpoint-status |  |  | checkpoint | DO NOT remove alignment clamps until cooling time elapses:
checkpoint-status |  |  | checkpoint | Is manufacturer’s cooling time completed?
checkpoint-group |  |  | section | 11. Post Weld Inspection
checkpoint-status |  |  | checkpoint | 11.1 Inspect the fitting to ensure molten polymer has not extruded from the socket mouth, or visible heating wires displaced between the joint annular gap.
checkpoint-status |  |  | checkpoint | 11.2 Check that the melt fusion indicator pins have fully risen.
checkpoint-status |  |  | checkpoint | 11.3 Check the pipe has not moved during welding by ensuring the insertion depth mark is in the same position as marked on the pipe surface during joint assembly.
checklist-sectioned |  |  | checklist | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters) | itp |  |  |  | Yes | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters) | bdb5825d-10c1-4c45-b640-1ed05063c4dd
checkpoint-group |  |  | section | PRELIMINARY APPROVALS
checkpoint-status |  |  | checkpoint | 1 - Shop Drawings Approval
label | de4ec093-4ae3-5fb1-9cf4-d1d5e9c2d76e |  | note | Acceptance Criteria: All shop drawings submitted and approved.
label | 8449799d-d7bb-5e59-89f9-26fa57243b50 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Physical Samples Approval / Selections of Material including Color
label | 46d6a72d-8689-5a74-85a3-7db11316b758 |  | note | Acceptance Criteria: Physical samples, material types, and color selections submitted and approved.
label | 8f676717-36db-5dfb-b622-edbbe170a50b |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Approval of Pedestal for Planters
label | e275ea69-c57f-5e57-ad3c-fd76e037c196 |  | note | Acceptance Criteria: Specifications for pedestals, including design, load capacity, and materials, submitted and approved.
label | 6cecd53f-9402-50e5-ba83-4b6a7750dac9 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | DELIVERED GOODS INSPECTION
checkpoint-status |  |  | checkpoint | 1 - Verification of Delivered Items Against Shop Drawings
label | af03eff3-4527-5470-9aa2-62ddf973c478 |  | note | Acceptance Criteria: Delivered items match the approved shop drawings, verified by foreman with photographic evidence.
label | 4d792815-626f-5c63-9906-ba1b2517a798 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 2 - Confirmation of Delivered Goods Quantities
label | ede91b4c-d14f-509a-9d8f-882aaa74c62d |  | note | Acceptance Criteria: Quantities of delivered goods align with documented requirements, confirmed by foreman's sign-off.
label | b2df83b9-a701-5859-b133-4116a68e79bc |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | INSTALLATION INSPECTION
checkpoint-status |  |  | checkpoint | 1 - Compliance of Fixings on Shop Drawings
label | 2e49221c-9f55-5f3f-a15a-7d0df9dcb6a7 |  | note | Acceptance Criteria: Installation of fixings verified against shop drawings, approved by foreman.
label | ceaa3ba4-39f1-5941-bcae-d5782cb70f39 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-status |  |  | checkpoint | 2 - Completion and Testing of Waterproofing
label | a71bf010-0352-5b58-a464-92a7810a8d74 |  | note | Acceptance Criteria: Waterproofing finished as per design and successfully tested, with foreman's approval.
label | 2c0a21b3-9fe6-5398-9028-768394f14e35 |  | note | Assignees and Verification Method: Internal - Hold Point
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Security of Planter Installations
label | 269efb1d-75a4-50d1-8e94-12b5f95fc3c3 |  | note | Acceptance Criteria: Planters secured correctly as per installation guidelines, confirmed by foreman's sign-off.
label | 1e9b8fb5-73c5-5ed6-8d4c-05e14d922812 |  | note | Assignees and Verification Method: Internal - Surveillance
checkpoint-group |  |  | section | HANDOVER
checkpoint-status |  |  | checkpoint | 1 - ITP and Handover Approval
label | d632da20-72eb-59fd-9d65-89a5ba08d747 |  | note | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | 2aafa6ca-edb6-50b1-81a8-21dfec55ffef |  | note | Assignees and Verification Method: Internal - Hold Point, Client - Hold Point
holdpoint |  |  | signoff | HOLD POINT