## 1.0 Material Testing
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | A | B | C | 0 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-06-26 | 2024-08-12 | 2024-08-19 | 2024-08-01
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  |  |  | 2024-09-02
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-06-27 | 2024-08-19 | 2024-08-30 | 2024-09-02
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/5: Specification for In-Situ Stabiisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Graeme Stokes |  |  |  | 2024-09-02
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  |  |  | 2024-09-03
[7 empty] | Issued by: Project Director |  | Chris Seath |  |  |  | 2024-09-03
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS | [14 empty] | To avoid doubt, if 1 days production is 4,000m2, are we basing on 4,000m2 or 1,500m2 | Removed reference to frequency
1.01 | AP40 Basecourse Aggregates used for overlay (if applicable) Notes: H = Hold point up to approval of Optimisation Testing M = Monitor during production | Crushing Resistance | H | 1 per 10,000 m3 | NZS4407:3.10 | < 10% passing 2.36mm sieve at 130kN | IANZ report | Contractor |  | A | I | R | dd/mm/yy | Changed to m3
|  | Maximum Wet/Dry Strength | H | 1 per 10,000 m3 | NZS4407:3.10 & AS 1141.22 |  | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | Weathering Quality Index | H | 1 per 10,000 m3 | NZS4407:3.11 | AA, AB, AC, BA, BB, CA | IANZ Report | Contractor |  | A | I | R | dd/mm/yy | Changed to m3
1.03 |  | Calfornia Bearing Ratio (CBR) | H | 1 per 10,000 m3 | NZS4402:4.1.3 NZS4407:3.15 | Compaceted using NZ Vibe Hammer 4-day soaked CBR ≥ 80% | IANZ Report | Contractor |  | A | I | R | dd/mm/yy | Changed to m3
1.04 |  | Quality of Fines, either PI or SE or CI | H | 1 per 1,000 m3 | NZS4407:3.4 - PI NZS4407:3.5 - CI | PI ≤ 5 CI ≤ 3 | IANZ Report | Contractor | NZTA M04: 2024 AP40 - Class 2 PI and CI applies | A | I | R | dd/mm/yy | Changed to m3
1.05 |  | Broken Faces Content | H | 1 per 1,000 m3 | NZS4407:3.14 | ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | IANZ Report | Contractor | Waived if aggregate is from crushed hard rock quarry | A | I | R | dd/mm/yy | Changed to m3
1.06 |  | Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | NZTA M04:2024-Class 2 Class 2 in Table 12 for PSD Table 13 for shape control | IANZ report | Contractor |  | A | I | R | dd/mm/yy | Changed to m3
1.07 | Optimisation of Stabilising Agent(s) | Blend Particle Size Distribution | H | 1 per 1,000 m3 | NZS4407:3.8.1 | Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading. | Report using IANZ Reports for AP40 and TP PSDs | Designer | Designer to advise if "average" blend is acceptable. | R | A | I | dd/mm/yy
1.08 |  | Indirect Tensile Strength, ITS | H | 1 Optimisation test per aggregate type | NZTA T/19: 2020 | Testing at 1mm/min: BSM Dry ITS: 175 kPa to 400 kPa BSM Soaked ITS: 150 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 210 kPa to 480 kPa BSM Soaked ITS: 180 kPa to 450 kPa | IANZ Report | Designer | Designer to advise on binder content(s) Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field | R | A | I | dd/mm/yy | Have incresed the 50.8mm/min allowable ITS values by 20%. Not comfortable with increasing by 40%
1.09 |  | Unconfined Compressive Strength, UCS | H | 1 Optimisation test per aggregate type | CCNZ / NPTG / CETANZ Industry Guide | UCS limits set by the design engineeer | IANZ Report | Designer |  | R | A | I | dd/mm/yy
1.1 |  | Modified Maximum Dry Density | H | Single Point DD vs WC during optimisation test | NZS 4402.4.1.3 | To determine target density | IANZ Report | Designer | Required before Stabilisation comences | R | A | I | dd/mm/yy
Need to cover Solid Density
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 2.0 Pre Construction Works
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | A | B | C | 0 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-06-26 | 2024-08-12 | 2024-08-19 | 2024-08-01
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  |  |  | 2024-09-02
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-06-27 | 2024-08-19 | 2024-08-30 | 2024-09-02
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/5: Specification for In-Situ Stabiisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Graeme Stokes |  |  |  | 2024-09-02
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  |  |  | 2024-09-03
[7 empty] | Issued by: Project Director |  | Chris Seath |  |  |  | 2024-09-03
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date | Thorsten's Notes (Rev.A changes) | Aidan/Nick Notes (Rev.B) | TF's Notes (Rev.C)
2.0. BEFORE BITUMEN STABILISATION STARTS
2.01 | Setout section | Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking | H | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor |  |  | I | R | dd/mm/yy
2.02 | Pre-hoe, shape and proof roll | Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting | H | Prior to stabilisation per section | Use grader's machine control and inspect shape |  | N/A | Stabilising Contractor | Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement |  | A | R | dd/mm/yy | Can the grader's machine control spit out an as-built accurate enough for this purpose? | Where we have altered prehoe level in the past to accommodate consistent overlay thickness, we have struck shallow subgrade and/or significant earthworks to prepare layer | Shallow pavement depths to be identified from TP profiles (pavement design process).
2.03 |  |  |  |  | Visual check or Vibratory Roller's response meter |  | Stabilising Contractor confirm no obvious soft areas found | Stabiliisng Contractor | Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions |  | A | R | dd/mm/yy |  | Not all rollers have response meter's. What is deemed ok and what is deemed not? Different rollers have different systems i.e. Bomag and CAT calculate vibration freedback differently. | F30: changed and to or C29: changed to reflect that the pre-shaping may change from the general case of pre-shaping parallel to new design
2.04 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy
2.05 |  | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy
2.06 |  | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Stabilising Contractor |  | I | A | R | dd/mm/yy
2.07 | Overlay and check levels | Supply, pre-compact and trim to line and level with NZTA M/4 AP40 | H | Prior to stabilisation per section | Survey | As per NZTA Z/16 | Check with Grader and visual inspection | Stabilising Contractor with Main Contractor | This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to): - overlay aggregate quality / consistency - moisture content - any concerns with shape and tie in - etc. |  | I | R | dd/mm/yy | I've made the previous step a hold point. Would we need to have a hold point here as well? Level sheet would be the case if you did lift pegs | I like this as a hold point as it allows an opportunity for us to complete a last minute check of the basecourse before it is foamed. It gives an opportunity to address concerns with shape and tie in if they are not right - we have had issues with Mobile Mapper produced designs and feel more comfortable having additional checks prior to foaming.
2.08 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Stabilising Contractor |  |  | I | R | dd/mm/yy
Wind
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep. | [5 empty] | Need to cover Solid Density
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 3.0 FBS
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | A | B | C | 0 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-06-26 | 2024-08-12 | 2024-08-19 | 2024-08-01
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  |  |  | 2024-09-02
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-06-27 | 2024-08-19 | 2024-08-30 | 2024-09-02
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/5: Specification for In-Situ Stabiisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Graeme Stokes |  |  |  | 2024-09-02
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  |  |  | 2024-09-03
[7 empty] | Issued by: Project Director |  | Chris Seath |  |  |  | 2024-09-03
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date | Thorsten's Notes (Rev.A changes) | Aidan/Nick Notes (Rev.B) | TF's Notes (Rev.C)
3.0. BITUMEN STABILISATION OPERATION
3.01 | Stabilising Agents | Lime (if applicable - check PI delete otherwise) | M | Per Batch | TNZ M/15 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.02 |  | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy |  | Weather - rain/likelihood of rain - need to accommodate/reflect this risk and controls here
3.03 |  | Bitumen (130/150) | M | Per Batch | M/1 | Conform to Specification | Certificate in contractor's site folder | Stabilising Contractor |  |  | I | R | dd/mm/yy |  | Wind
3.04 | Weather conditions | Material behind stabiliser | M | Prior to spreading | Measurement | Material after stabilisation: BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C | Daily work Log | Stabilsing Contractor |  |  | I | R | dd/mm/yy
3.05 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed < 25 km/hr | Daily work Log | Stabilsing Contractor |  |  | I | R | dd/mm/yy
3.06 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Stabilsing Contractor |  |  | I | R | dd/mm/yy
3.07 | Spreading of powdered stabilising agent (Cement / Lime) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 0.5kg/m2 of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy |  | Why not B5 +/- 0.5kg? | Changed to reflect B5
3.08 |  | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.09 | Injection of bituminous stabilising agent (FBS or BE) | Flow meter and operator's display readings | M | Continous monitoring by the operator and the grounds person | Visual display reading | ± 5% of specified rate | N/A | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.1 |  | Compare tonnes used (from the stabiiser's PCU) with the measured area | M | Record usage from PCU at the end of each run | Record readings at the end of each run | ± 3% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.11 |  | Compare tonnes used (from delivery docket) with measured area | M | For each bitumen tanker load | Dip bitumen tanker before and after | ± 2.5% of specified rate | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.12 | Injection & Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy |  | Does this need to be a minimum of 150mm, typically this is 100mm. | Discused and agreed with Nick to keep this as 150mm. In cases where the difference between 100mm and 150mm causes another stabilisation run, identified in the cut plan, then the pavement designer shall be consulted
3.13 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Stabilising Contractor |  |  | I | R | dd/mm/yy
3.14 | FBS material | Stabilised material strength - ITS | M | 3 soaked ITS + 3 dry ITS per Lot or when the material changes | NZTA T/19N: 2020 | Testing at 1mm/min: BSM Dry ITS: 150 kPa to 400 kPa BSM Soaked ITS: 120 kPa to 350 kPa Testing at 50.8mm/min: BSM Dry ITS: 180 kPa to 450 kPa BSM Soaked ITS: 150 kPa to 420 kPa | IANZ Report | Stabilising Contractor | ITS briquettes to be produced on site if travel time to lab > 30 minutes. | I | A | R | dd/mm/yy |  | Really keen to understand a bit more around direction of this testing | UCS deleted. ITS to check design intent has been achieved. The intent is to flag a possible issue for further investigations, which may push out placement of TAC, for example.
3.15 | Compaction | Plateau Density Test | H | On first day per site and then 1 per 10,000m2 unless material or anvil conditions change | Draft NZTA T/24 (Aug-2024) | To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD | Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed | Stabilising Contractor | If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER | I | A | R | dd/mm/yy | Anvil conditions determined after pre-hoeing. Response meter, experience, etc. Risk of overcompaction dealt with by getting the right roller. Vario / Oscilation with the correct compaction effort should be used Assessment of PDT through ConQA | Vario rollers not widely available. Machine breakdown, acceleration demand and additional resources for delivery will need a practical means of demonstrating compliance. Relying on Vario for all of this work is a delivery risk. Although comfortable with what was proposed at T24-WG in Tauranga, we would still need to review this final document. Is it a risk to use T24-DRAFT given scale and profile of this project? Should we be including compaction time limitations here? | We will generally be FBS'ing to 200mm (max 220mm). Meeting on the 14/08/2024 discussed the follwing: - process around agreeing the target density through ConQA and having a Plan B where the appropriate data transmission coverage is not available - some examples of rediculous number of static passes - PDT not suitable for final compaction due to the process of final compaction not being able to be simulated due to water, equipment space, etc in PDT section .
3.16 |  | Maximum Dry Density | M | On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes | NZS 4402.4.1.3 | For analysis of DoC To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site | IANZ Report | Stabilising Contractor | MDD briqutte to be produced on site if travel time to lab > 30 minutes Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out. | I | A | R | dd/mm/yy | Material behind the stabiliser should be at just below the OMC (referred to as the fluff point) for optimum dispersion of the bitumen. Hand squeeze test generally gives within 1% of OMC. Experienced stabilising ground person should be getting this right. Let's assess practicallity of MDD on site. | Concern is we don’t have a wide enough density spread given site area. Risk of not having appropriate Target Density in hand given the site area. Would suggest increasing testing frequency of PDT and MDD. | This has not been done in the past, so we (DNA/Hiway) may need to adjust the frequency as we go. The testing staff in on site all day so this shouldn't attract any more cost if the site testing is paid for on a daily basis. It may require a few more moulds on site which is not a significant cost.
3.17 |  | Degree of Compaction (DoC) | H | 5 per 1,000m2 | NZS 4407.4.2.1 (DT full stabilising depth) | Average DoC ≥ 98% Minimum DoC ≥ 95% | IANZ Report | Stabilising Contractor |  | I | A | R | dd/mm/yy | New PDT draft T24 does not require all the points anymore | Assumming design treatment depth is in increments of 50mm. If not, to we retract to closest 50mm increment? | Generally will be 200mm if we go to 220mm, for example, the testing would still be 200mm. This can be covered in te design handover brief
3.18 | Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover) | Clegg Impact Value | H | 5 per 1000m2 |  | CIV ≥ 50 | CIV form - ConQA | Stabilising Contractor |  | I | A | R | dd/mm/yy
3.19 |  | Degree of Saturation, DOS | M | 5 per 1000m2 | NZS 4407.4.2.2 and DOS calculation in NZTA B/5 | aim for DOS ≤ 80% | IANZ report | Contractor | Report only | I | A | R | dd/mm/yy | SD for FBS TBC | Assumming design covers Solid Density for this | This is in the B/5 specification so not DNZ's call to remove this requirement. Will investigate further as results come in. Solid Density being done on Raw and will investigate FBS'd SD.
Weather - rain/likelihood of rain - need to accommodate/reflect this risk and controls here
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep. | [5 empty] | Wind
Need to cover Solid Density
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 4.0 Post Construction
|  |  |  | Construction Process: Modified Basecourse Layer | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | A | B | C | 0 - IFC
[5 empty] | Finish RP |  | Prepared by Pavement Designer: |  | Thorsten Froebel | 2024-06-26 | 2024-08-12 | 2024-08-19 | 2024-08-01
|  |  |  | Project Name: T2W - Tirau to Waiouru - Rehabilitation Works |  |  | Reviewed by Construction Manager: |  | Wayne Bowden |  |  |  | 2024-09-02
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Aiden Smith / Nick Schilov | 2024-06-27 | 2024-08-19 | 2024-08-30 | 2024-09-02
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/5: Specification for In-Situ Stabiisation of Modified Pavement Layers, NZTA M/4: Spec forBasecourse Aggregate, NZTA T/19: Procedures for Direct and Indirect Tensile Strength Testing of Modified and Bound Pavement Materials |  |  | Approved Quality Manager.: |  | Graeme Stokes |  |  |  | 2024-09-02
[7 empty] | Approved by: Pavements SME.: |  | Thorsten Froebel |  |  |  | 2024-09-03
[7 empty] | Issued by: Project Director |  | Chris Seath |  |  |  | 2024-09-03
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Designer | Eng. Rep | Contractor | Date | Thorsten's Notes (Rev.A changes) | Aidan/Nick Notes (Rev.B) | TF's Notes (Rev.C)
4.0. Testing and Sgnoff
4.01 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Stabilising Contractor |  |  | A | R | dd/mm/yy
4.02 |  | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Stabilising Contractor |  |  | A | R | dd/mm/yy
4.03 |  | Surface Shape | H | every 20m | Measurement | < 10mm using 3m straight edge | Survey | Stabilising Contractor | Only required if the visual inspection appears unsatisfactory |  | A | R | dd/mm/yy
4.04 |  | Surface Levels | H | every 20m | Measurement | -5mm, +15mm | Survey | Stabilising Contractor |  |  | A | R | dd/mm/yy
4.05 |  | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Stabilising Contractor | ER to be present at pre-seal inspection |  | A | R | dd/mm/yy
4.06 |  | Roughness | H | Before Sealing | TNZ TM 7003 v1 | 100m rolling average ≤ 75 counts/km | Test Certificate | Contractor |  |  | A | R
4.07 | Pavement Layer Signoff | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineers Representative |  |  |  |  | dd/mm/yy |  | Additional notes;
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.