## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
5c3ec20e-3f84-4bef-92cf-d1d49bda1fb2 | checklist | ITP - Foam Bitumen Stabilisation - Pre Treatments Rev C | itp | ITP - Foam Bitumen Stabilisation - Pre Treatments
b5380e82-7ea2-43f9-9cf1-e3e33c4693b1 | section | 2.0. BEFORE BITUMEN STABILISATION STARTS
fc5a4667-6af6-4155-b643-7c27310d3064 | checkpoint | 2.01 - Setout section
b7469805-4d2d-5688-b1c2-ac7dc36cf157 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
e724fc98-a3cd-5be9-9b0c-267d845cf819 | note | Action (Hold, Monitor, Witness) - H
6d79dfa4-f884-5541-a77a-8fc8b9bd1aae | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
87ef72cf-2925-570c-9dcf-5b14bf8a84b6 | note | Inspection / Test method - Survey
d1b0ce30-8573-52d3-8386-713bd8239800 | note | Acceptance Criteria - Document existing furniture
1aa192fe-6cc8-5ee2-b323-b47be9784e4f | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
fc2f52e7-c16e-55d9-a62a-53e065adacd3 | note | Responsibility - Contractor
9ec84cce-fe78-5efb-ab57-1e13a5ab66b4 | note | Eng. Rep - I
7b121d1a-fcf3-553a-94b8-14cc6c9f0f82 | note | Contractor - R
c2cbd3a7-5e8b-4ca0-83a3-7fe870dc31ba | signoff | AUTHORITY HOLDPOINT
27b67008-3b42-40f0-a584-381bfc9ec55d | checkpoint | 2.02 - Pre-hoe, shape and proof roll
1a33fdc7-b426-5544-943b-ae7d3da94a72 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
f1b7b2ea-c8ce-56aa-8f17-a7ce62c9f405 | note | Action (Hold, Monitor, Witness) - H
c5821353-42c7-54cb-9f23-e7e9deac0b08 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
fa387cf4-552f-5095-9640-9b2894b34f9a | note | Inspection / Test method - Use grader's machine control and inspect shape
70508a94-ce95-5d84-828a-2be4ffda606c | note | Record documents (QCP - Quality Control Portal) - N/A
09fd418c-7356-549d-8ed6-5fd35d5afdea | note | Responsibility - Stabilising Contractor
fda5d0b8-d342-5fa6-a369-3938d12aac04 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
ba171a3d-4ee8-50bf-825f-08f9a92d3583 | note | Eng. Rep - A
d8a80e99-bbcd-5346-9212-c09f3113f77e | note | Contractor - R
153e22f6-8332-4b5f-8ef6-164b57d847d0 | signoff | AUTHORITY HOLDPOINT
99764d25-1bc5-4ee4-8eac-200f107a4eb6 | checkpoint | 2.03 - Pre-hoe, shape and proof roll
7e7244cb-29dd-5271-87ab-8eeaf538db0b | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
ab334fdf-e593-538b-9bce-ab93d8153b82 | note | Action (Hold, Monitor, Witness) - H
8af1194d-4a39-592c-a9a6-d8bd85129e56 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
6e14ef5c-0158-54c9-8e49-28e4593cca90 | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
b6297ab8-c5f6-5cd8-82ff-8b23cfe1eb43 | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
2dc434f3-9644-511f-91c2-92a986086842 | note | Responsibility - Stabiliisng Contractor
20763f7e-1f40-569c-8cc2-e6ed866a5182 | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
7fe1a52c-9ba6-5ab0-b4fd-f8cb25d76034 | note | Eng. Rep - A
12f25bd5-3890-5116-80ce-57ed8b1cf47c | note | Contractor - R
b0347f78-412b-4a28-bfd3-45818549bfff | signoff | AUTHORITY HOLDPOINT
bb116b83-3e20-44e6-a2b9-71d5d4de447a | checkpoint | 2.04 - Compaction
058499d2-be7f-5b01-9ea2-af4ff46c5874 | note | Detail of Activity / Test - Plateau Density Test
75aa1f03-8d4d-52c8-b5ee-40b6298b46f3 | note | Action (Hold, Monitor, Witness) - H
d4751b14-aa88-5829-afbe-556528e51199 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
d49f8c39-72bd-5f51-8c6f-2a1891d4d089 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
ac60ac3c-7330-5527-9da5-d226d63b0bd3 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
2f7d7c07-1d7e-550f-b460-b95b4acc33a8 | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
6450f46c-b1c6-5f98-ad2b-c325eb217762 | note | ○ IANZ report when processed
87bef643-8269-5062-929c-c74583eaa879 | note | Responsibility - Stabilising Contractor
046b2466-037f-562d-848e-7383192569e5 | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
7ac7a66f-50a4-5c7f-89dd-24d7d2d5d8bf | note | Designer - I
bcaeb408-5c93-5ff7-8977-f4336aa67cdc | note | Eng. Rep - A
5941c94e-d642-59b2-a4ad-53c9a4c7ce2c | note | Contractor - R
d3bc96d8-73d8-4cfb-8ea2-52821e351822 | signoff | AUTHORITY HOLDPOINT
c10aec6c-2b5b-412e-a647-bfc63ee16f10 | checkpoint | 2.05 - Compaction
901435da-41cb-523d-963d-705a3b8063a9 | note | Detail of Activity / Test - Maximum Dry Density
b061050b-7434-5188-b556-818ebfb82388 | note | Action (Hold, Monitor, Witness) - M
5cac288d-9b8f-5551-8486-d0857c7cee12 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
21801d26-1e34-52d2-9fe4-753db1354c5e | note | Inspection / Test method - NZS 4402.4.1.3
bc6d77f9-2a20-583a-8a77-37f04050e0ac | note | Acceptance Criteria - For analysis of DoC
df535908-0605-5135-9f59-1ee9853ead46 | note | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
e02909d4-7fe6-5d65-b7c1-2cd730384df3 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
6da2f203-8631-560c-a79b-07df86d38458 | note | Responsibility - Stabilising Contractor
d50877a6-c186-5104-bc67-f4cdb7e1807f | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
6b6977d0-5412-539d-b0a7-4bfbc8848bc2 | note | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
f26b344b-6a96-5b92-9f5c-38990138b396 | note | Designer - I
0d87ed54-5817-5330-87c8-b2d6f17f04e7 | note | Eng. Rep - A
201e2e87-3c8e-56d6-aae2-79e7a5693e87 | note | Contractor - R
1ceca5d7-3c2d-461b-936b-f25e0fdd9ad7 | checkpoint | 2.06 - Compaction
bf61e0aa-8c32-5224-bb3b-d59c189fcc6d | note | Detail of Activity / Test - Degree of Compaction (DoC)
3d71ddbe-abc3-5eb7-96e7-9a19cd506f37 | note | Action (Hold, Monitor, Witness) - H
7de0b9cf-65d1-521c-805c-4c1b7b3b2471 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
4b7ac3fd-5ed9-5c29-be5b-c04e4d404463 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
f8152922-8603-5b46-b269-27adb71591b0 | note | Acceptance Criteria - Average DoC ≥ 95%, Minimum DoC ≥ 92%
1fc14b82-1c04-5cb6-a20c-46422e9014be | note | Record documents (QCP - Quality Control Portal) - IANZ Report
507979e9-19fa-5fff-aacc-33085d19abee | note | Responsibility - Stabilising Contractor
17381022-6206-5f0a-a079-46bc59b6ff05 | note | Designer - I
5fbee23f-f138-5ba7-8cfa-b2222c955975 | note | Eng. Rep - A
d1be43e6-511e-534d-88ef-fa55fb79f734 | note | Contractor - R
898fe605-3296-4d54-94cc-cae663c28e43 | signoff | AUTHORITY HOLDPOINT
6bf12dc1-6647-4bda-9ec0-13c4d2445c68 | checkpoint | 2.07 - Overlay and check levels
8923d334-d910-5e42-bb6a-34a2f4def70e | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
ffb8b7f6-3e8a-5d69-be7c-5aade7a14c87 | note | Action (Hold, Monitor, Witness) - H
eb450803-e054-5eba-86a7-f39bb7229336 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to stabilisation per section
b800b703-c2e4-5248-872c-86e59ba9b4f2 | note | Inspection / Test method - Survey
87457d51-bacc-58b8-9afb-f576c0bd082f | note | Acceptance Criteria - As per NZTA Z/16
| note | ○ Minimum: -5mm
| note | ○ Maximum: +15mm
225536c8-03d8-5ecc-b29d-2bf16f16d15a | note | Record documents (QCP - Quality Control Portal) - Drawing Showing levels and crossfalls
c593bfeb-8b16-5594-a073-f168d2628f01 | note | Responsibility - Stabilising Contractor with Main Contractor
ba34c5c1-6006-5c4e-bef4-2783f004ece4 | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
5b4cc416-89e3-5a61-892c-88f667c3d685 | note | – overlay aggregate quality / consistency
5bc33a54-86b2-5f1e-9278-5d6224f2c40e | note | – moisture content
7231f15a-2317-5de3-a22a-1ec79f39b14b | note | – any concerns with shape and tie in
380969e7-5837-5d34-bbad-5d2dccc711bf | note | – etc.
48eede4b-6cfd-57dd-b8e4-14f45872dcf5 | note | Eng. Rep - I
645469d6-fa15-591a-872b-eb63ee1c74ed | note | Contractor - R
129867dc-0b95-40f6-86d6-b51aa80378ae | signoff | AUTHORITY HOLDPOINT
dece3019-bde1-4321-9231-cedd7a8b66b9 | checkpoint | 2.08 - Production Plan
521feea3-a803-59c7-859d-dee41bea4adb | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
ccf083d1-d138-5afc-9a67-f45ba0495a69 | note | Action (Hold, Monitor, Witness) - M
e4d579f1-2d77-56b2-a5ad-6b9c29a782e0 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
cfc164ff-c29a-543e-823a-ecb59fbeefe0 | note | Inspection / Test method - Daily Report
afd81382-4a7e-59f1-ad3d-7f70e31bfdc4 | note | Acceptance Criteria - Points covered in NZTA B/5
119e766d-05ae-5ffc-9a05-bdb23e617546 | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
9f37db90-cb9f-52c9-b4e2-253cf35768e1 | note | Responsibility - Stabilising Contractor
387bb612-5d94-544b-90e9-a875fdccf7a8 | note | Eng. Rep - I
936415f3-bcc7-5ead-8c88-16cd13f3e590 | note | Contractor - R
6c0708eb-f46f-4385-9d0b-39267adaca6d | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c34b8ce0-3d61-544e-8c75-834a27e89cf5 | textbox | Contractor's Rep Name:
4f59ee66-2f61-53b1-bf3a-e5fd6e5e4671 | textbox | Engineer's Rep. Name:
35138d07-1c71-5210-86a8-ba8ffc6540a9 | date | Date:
edd9ccc1-984f-4551-8bdf-d2aa5a2495f8 | signoff | Add Signature