## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP | [5 empty] | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
bool | Set out
bool | Core Holes
bool | Install dowels
checkpoint | Pre approvals for the cast insitu concrete
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove back propping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | Pit + Lid - 01 - 1D-12
checkpoint | Pit + Lid - 02 - 22D-7
checkpoint | Pit + Lid - 03 - 22D-8
checkpoint | Pit + Lid - 04 - 22D-9
checkpoint | Pit + Lid - 05
checkpoint | Pit + Lid - 06
checkpoint | Pit + Lid - 07
checkpoint | Pit + Lid - 08
checkpoint | Pit + Lid - 09
checkpoint | Pit + Lid - 10
bool | Tank Lid
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Pit-1D-12)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Height, Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Pit-1D-12)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Quality Assurance
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Pit-22D-7)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Height, Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Pit-22D-7)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Quality Assurance
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Pit-22D-8)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Height, Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Pit-22D-8)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Quality Assurance
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Pit-22D-9)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Height, Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Pit-22D-9)
section | Pit Base
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters ( Foot Anchor - 5t x 95mm) - 3 Nos Minimum
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Shape the concrete up to pipe invert level
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Walls
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Place the stater bars for hume pipe concreting
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Pit Lid
checkpoint | Availability of updated shop drawing
checkpoint | Site Safety / Workers Safety
checkpoint | Overall Measurements of construction Element (Attach Photos)
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Concrete cover- 60mm Against Earth Face, 40mm Other sides
bool | Lifters - As per the drawing
bool | ID Plate
checkpoint | Curing Procedure arranged
checkpoint | Final Check, Photo Taken
checkpoint | Curing Procedure arranged
date | Pour Date
section | Quality Assurance
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER