## Project Breakdown
CHECKLISTS
Job Name | 1100 - Shelly Beach Road
Job Details |  | prepopulate | Job Details Checklist
Precast Manufacture |  | ability to add
Basement Panels |  | Ability to add | Add 1. Standard
| BSB01 | prepopulate | Add 1. Standard
| BSB02 | prepopulate | Add 1. Standard
| BSB03 | prepopulate | Add 1. Standard
| BSB04 | prepopulate | Add 1. Standard
| BSB05 | prepopulate | Add 1. Standard
| BSB06 | prepopulate | Add 1. Standard
| BSB07 | prepopulate | Add 1. Standard
| BSB08 | prepopulate | Add 1. Standard
| BSB09 | prepopulate | Add 1. Standard
| BSB10 | prepopulate | Add 1. Standard
| BSB11 | prepopulate | Add 1. Standard
| BSB12 | prepopulate | Add 1. Standard
| BSB13 | prepopulate | Add 1. Standard
| BSB14 | prepopulate | Add 1. Standard
| BSB15 | prepopulate | Add 1. Standard
| BSB16 | prepopulate | Add 1. Standard
| BSB17 | prepopulate | Add 1. Standard
| BSB18 | prepopulate | Add 1. Standard
| BSB19 | prepopulate | Add 1. Standard
| BSB20 | prepopulate | Add 1. Standard
| BSB21 | prepopulate | Add 1. Standard
| BSB22 | prepopulate | Add 1. Standard
| BSB23 | prepopulate | Add 1. Standard
| BSB24 | prepopulate | Add 1. Standard
| BSB25 | prepopulate | Add 1. Standard
| BSB26 | prepopulate | Add 1. Standard
| BSB27 | prepopulate | Add 1. Standard
Ground Floor Panels |  | Ability to add | Add 1. Standard
| GSB01 | prepopulate | Add 1. Standard
| GSB02 | prepopulate | Add 1. Standard
| GSB03 | prepopulate | Add 1. Standard
| GSB04 | prepopulate | Add 1. Standard
| GSB05 | prepopulate | Add 1. Standard
| GSB06 | prepopulate | Add 1. Standard
| GSB07 | prepopulate | Add 1. Standard
| GSB08 | prepopulate | Add 1. Standard
| GSB09 | prepopulate | Add 1. Standard
| GSB10 | prepopulate | Add 1. Standard
| GSB11 | prepopulate | Add 1. Standard
| GSB12 | prepopulate | Add 1. Standard
| GSB13 | prepopulate | Add 1. Standard
| GSB14 | prepopulate | Add 1. Standard
| GSB15 | prepopulate | Add 1. Standard
| GSB16 | prepopulate | Add 1. Standard
| GSB17 | prepopulate | Add 1. Standard
| GSB18 | prepopulate | Add 1. Standard
| GSB19 | prepopulate | Add 1. Standard
| GSB20 | prepopulate | Add 1. Standard
| GSB21 | prepopulate | Add 1. Standard
| GSB22 | prepopulate | Add 1. Standard
| GSB23 | prepopulate | Add 1. Standard
| GSB24 | prepopulate | Add 1. Standard
| GSB25 | prepopulate | Add 1. Standard
| GSB26 | prepopulate | Add 1. Standard
| GSB27 | prepopulate | Add 1. Standard
| GSB28 | prepopulate | Add 1. Standard
| GSB29 | prepopulate | Add 1. Standard
| GSB30 | prepopulate | Add 1. Standard
| GSB31 | prepopulate | Add 1. Standard
| GSB32 | prepopulate | Add 1. Standard

## 1.Standard
type | name | values | prefix
checklist | ""
section | Precast Element Details (Project Manager)
checkpoint | Concrete Details Complete
text | Concrete Volume
text | Concrete Strength
text | Enter Drawing Revision Number
text | Cast Date
text | Admixture Required
section | Reinforcing Yard Checks (Reinforcing Supervisor)
checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint | Overall cage dimensions in plan checked and there will be sufficent concrete cover to edges
checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
section | Formwork Set Up Checks (QA)
checkpoint | Length/Width/Thickness/Cutouts/Diagonals
checkpoint | Edge Details & Rebates
checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
checkpoint | MF roughening's
checkpoint | Sides Straight & Magnets Fastened
checkpoint | Mould Face Clean
section | Prepour Checks (QA)
checkpoint | Mould Cleaned & Oiled
checkpoint | Check covers on all sides, MF and TF, openings
checkpoint | Starters (Size, Grade, Setout and Length)
Checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
checkpoint | Lifters
checkpoint | Tie wire Trimmed
checkpoint | Panel fully clean
checkpoint | General Photos Attached
checkpoint | Concrete Docket Attached
checkpoint | Shop Drawing Checked Off (attach photo)
section | Post Pour (QA)
checkpoint | Confirm formwork has not shifted during placing of concrete
checkpoint | Face lifters placed in correct location
checkpoint | Roughening Lines Correct
section | Demould Inspection (Yard Supervisor)
checkpoint | Mould Face Acceptable?
checkpoint | Trowel Face acceptable?
checkpoint | Item Labelled?
checkpoint | Drossbachs cleaned out and clear?
checkpoint | Top lifters are cleared out and eyes are free of concrete?
checkpoint | Drossbachs drilled ?
checkpoint | Nail plates removed?
checkpoint | Jet washed?
checkpoint | Weld plates are cleaned and free of concrete?
checkpoint | Starter bars bent for transportation?
checkpoint | Structural repair required?
checkpoint | Chamfer Inspection
checkpoint | Silicone Inspection
checkpoint | Honey combing from Vibrating
checkpoint | Final check with drawing
section | Loading Out (Yard Supervisor)
checkpoint | Photo taken of Panel on Truck
checkpoint | No remedial work required on site
section | Test Results, Certificates and Documentation (QA)
checkpoint | Upload reinforcing detail sheets
checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint | Upload Concrete test results
checklist | Site Works Defect #1 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #1
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #2 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #2
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #3 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #3
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #4 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #4
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client
checklist | Site Works Defect #5 (Siteworks Manager)
section | Details
checkpoint-no-value | Site Works Defect #5
date | Date when scoping document was created
checkpoint | What is the Defect (Take photo of defect, highlight area of repair and add description where required on the photo or comment)
checkpoint | Remedial required
tickbox | Grind
tickbox | Sand
tickbox | Fill
tickbox | Drill
tickbox | Plaster
tickbox | Paint
tickbox | colour match
tickbox | Epoxy Reo
dropdown | PHQ, Dayworks,
checkpoint | NCR Raised if Required
checkpoint | Remedial completed (Take photo to evidence)
date | Date remedial completed
signoff | Remedial acceptable and signed off by client