## struct
resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
step | bar: Tier 1
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
|  |  |  | step |  |  | Tier 1: L10
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 20
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 21
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 22
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 23
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 24
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 25
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 26
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 27
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 28
|  |  |  | step |  |  | Tier 1: L11
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.07 Rough in Common areas | ITP No.30 Structured Cabling Rough In |  |  | folder-with-checklists |  |  | Tier 2: Common Areas
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L12
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L13
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L14
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L15
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L16
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L17
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L18
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L19
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L20
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L21
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L22
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19
|  |  |  | step |  |  | Tier 1: L23
ITR No.10 Hallway Rough In |  |  |  | checklist |  |  | Tier 2: Hallway
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 1
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 2
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 3
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 4
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 5
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 6
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 7
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 8
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 9
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 10
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 11
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 12
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 13
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 14
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 15
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 16
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 17
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 18
ITR No.09 Apartment Rough In of Electrical Services |  |  |  | checklist |  |  | Tier 2: Apartment 19