## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | Site QA | dynamic | TAL - BNZ Cameron Road
Columns
|  | Site has been cleaned in advance of our arrival on site |  | Site has been cleaned in advance of our arrival on site
|  | Walls are plumb & level |  | Walls are plumb and level
|  | Tiling works running to programme - prior trades completed |  | Tiling works running to programme - prior trades completed
|  | Has prior trades QA been signed off by main contractor |  | Has prior trades QA been signed off by main contractor
|  | Gib compound & sanding cleaned up from rooms |  | Gib compound and sanding cleaned up from rooms
|  | Task Analysis signed onto by tilers & provided to main contractor |  | Task Analysis signed onto by tilers and provided to main contractor
|  | Inductions completed |  | Inductions completed
|  | Site Inspection checklist has been completed |  | Site Inspection checklist has been completed
|  | All tools tagged & tested - (photo's required) |  | All tools tagged and tested - (photo's required)
|  | Tiler has current sitesafe - Input number & expiry |  | Tiler has current sitesafe - Input number and expiry
|  | Tiler has correct PPE |  | Tiler has correct PPE
|  | Correct drawings supplied as per onsite |  | Correct drawings supplied as per onsite
|  | Prime floor substrate prior to tiling |  | Prime floor substrate prior to tiling
|  | Levelling to floor & screed 1:8 fall at entrance tiling |  | Levelling to floor & screed 1:8 fall at entrance tiling
|  | Tiles set out according to latest drawing - always check revisions on site |  | Tiles set out according to latest drawing - always check revisions on site
|  | Specified product used with notched trowel or required product |  | Specified product used with notched trowel or required product
|  | Correct spacer size used for spacing as per specs & tile lipping within BRANZ tolerances |  | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
|  | floor substrate straight, signed off by MC, & ready for installation. (insert notes for remediation if required) |  | floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
|  | Install tiles to interior floors |  | Install tiles to interior floors
|  | Cut tiles to circular perimeter of tiles & buff edges |  | Cut tiles to circular perimeter of tiles and buff edges
|  | Silicone is completed to all tile junctions where required |  | Silicone is completed to all tile junctions where required
|  | Correct tile trim supplied & installed where required |  | Correct tile trim supplied and installed where required