## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart Inspections
section | Details
checkpoint | Site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Has prior trades QA been signed off by main contractor
checkpoint | Gib compound and sanding cleaned up from rooms
checkpoint | Task Analysis signed onto by tilers and provided to main contractor
checkpoint | Inductions completed
checkpoint | Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current sitesafe - Input number and expiry
checkpoint | Tiler has correct PPE
checkpoint | Correct drawings supplied as per onsite
checklist | QA - Tiling Installation
section | Tiling to floor
checkpoint | Prime floor substrate prior to tiling
checkpoint | Levelling to floor & screed 1:8 fall at entrance tiling
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install tiles to interior floors
checkpoint | Cut tiles to circular perimeter of tiles and buff edges
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Correct tile trim supplied and installed where required