## ITP
INSPECTION TEST PLAN | [5 empty] | DOCUMENT TITLE:INSPECTION TEST PLAN
ITP NO:
Works: | External and Internal plasterboard work
Builder: Conquest | [5 empty] | Project Address: Balfour Place, Lindfield
Inspection Area
Building No:
Unit No:
Responsible person for inspection
Name |  | Job Title |  | Initial |  | Signature | Date
Activity |  |  | Satisfactory |  |  |  | Inspected By(Initials) | Date | Builder Inspected(Initials)
|  |  | YES | NO | N/A | Comments
Wall set out
Framing
1:Firebox Installation
2:Frame Alignment
3:Fix to structural members
4:Openings
5:Nogging
6:Door frames fixing
7:Supplier inspection(studco)
Hebel
1:Angle in place
2:hebel panels Alignment
3:Panels finish(patches done)
4:Fire-rated caulking and sealing
5:CSR HEBEL Insepection
External cladding
1:Sarking install
2:Top hats in place
3:Horizontal & Vertical Alignment
4:Fixing to structural members
5:Frame Alignment
6:panel instal
7:Joints caulking & Sealing
8:Defects
9:Final Inspection
Plasterboard for walls
1:Ply nogging
2:Rogh-in sign off
3:Insulations
4:MR/Villaboard in wet areas
5:Plasterboard Lining
Plasterboard for Ceiling
1:Comfirm Ceiling height
2:Comfirm Access panel location
3:Ceiling frame work
4:Ceiling bulkheads
5:Pelmets
6:Ceiling insulation
7:MR plasterboard in wet area
8:Ceiling plasterboard Lining
Setting&Sanding
1:Angle /LB/P50 install
2:First coat setting
3:Second coat setting
4:Final coat setting
5:Sanding
6:patching
7:Defects
8:Final Insepection

## Unit Breakdown
Level 1 | 1.01 | 1.02 | 1.03 | 1.05 | 1.06 | 1.07 | 1.08 | 1.09 | 1.1 | 1.11
Level 2 | 2.01 | 2.02 | 2.03 | 2.05 | 2.06 | 2.07 | 2.08 | 2.09 | 2.1 | 2.11 | 2.12 | 2.13 | 2.15 | 2.16 | 2.17 | 2.18 | 2.19 | 2.2 | 2.21 | 2.22 | 2.23
Level 3 | 3.01 | 3.02 | 3.03 | 3.05 | 3.06 | 3.07 | 3.08 | 3.09 | 3.1 | 3.11 | 3.12 | 3.13 | 3.15 | 3.16 | 3.17 | 3.18 | 3.19 | 3.2 | 3.21 | 3.22 | 3.23
Level 4 | PH01 | PH02 | PH03 | PH5 | PH06 | PH07 | PH08