## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Ingrounds (Pipes below Raft Slab)
section | Pipes - Geofab
checkpoint | 90mm PVC with socked geofab
section | Trench
checkpoint | 200mm Trench - 400mm Wide - Trench Base to be 300mm below bliding
checkpoint | Lay trench base with 20mm rock
checkpoint | Install 90mm slotted stormwater with geofab sock
section | Backfill
checkpoint | Backfill
checklist | Ingrounds (Pipes in Raft Slab)
section | Lift Pumps
checkpoint | Pump and conduit lines installed correctly
checkpoint | Conduits to elecrial boards
section | Pipes to B2 from B3 along retaining well
checkpoint | Pipes to be sleeved through precast wall from B3-B2
checkpoint | Correct location
section | Vertical Strip Drain Connections
checkpoint | Install vertical strip drain to solid pipe above B2 as high as possible
section | In Raft Pipes
checkpoint | Correct size
checkpoint | IL's pipes to be supported and sewer lagged
checkpoint | Correct primer and glue used
section | Pits in Raft
checkpoint | Pipes inlet and outlet IL's correct
checkpoint | Pipe sizing correct
checkpoint | Grated lid installed correct size
section | Pressure Relief Pipes Hydrostatic
checkpoint | 80mm PVC - Returns at RL 0.50
checkpoint | Back to inraft 100mm SN8 pipe -In raft slab
section | Stormwater pumpwells 1&2 create two separate ITP's
checkpoint | Inlet - Outlet pipes at correct IL's
checkpoint | Pump out line size and position correct
checkpoint | Conduit to access panels to correct area
section | Spoon Drain Outlet
checkpoint | Outlets to be directly behind columns
checkpoint | 100mm pipe to be fit off with drop in grates once stripped
section | Sewer Pit
checkpoint | Correct pipe sizes
checkpoint | Inlet sizes and IL's correct
checkpoint | Pump out lines to correct location
checkpoint | Correct pumpout size
checkpoint | Chamber Vents
checklist | Meter Assemblies & Risers
section | Details
checkpoint | Valves Tagged
checkpoint | Meters on
checkpoint | Assembly Complete
checkpoint | Pipe Support
checklist | Lagging
section | Details
checkpoint | Lagging Complete
checkpoint | Photos must be attached
checklist | Drains
section | Details
checkpoint | All drains installed as per Plan referenced on spreadsheet
checkpoint | Photos must be attached
checklist | Corridors
section | Details
checkpoint | Hot Water
checkpoint | Cold Water
checkpoint | Hot Water Lagging
checkpoint | Testing
checkpoint | Pipes clipped
checkpoint | Valves Tagged
checkpoint | Door Headers (Fire rated with Hilti 611A)
checkpoint | Hot Water Meters Installed
checkpoint | Photos must be attached
checklist | Rough In
section | Details
checkpoint | DRAIN COMPLETE
checkpoint | OVERFLOW EXPOSED AND CHOPPED DOWN
checkpoint | UN-USED PENO'S SEALED
checkpoint | ROUGH IN COMPLETE
checkpoint | HEADER PIPES FIRE CAULKED
checkpoint | TMV ACCESSIBLE TO A/P
checkpoint | HOT WATER METERS INSTALLED
checkpoint | CROSS CONNECTIONS
checkpoint | MIXER STRAIGHT, SET BACK CORRECT
checkpoint | WATER PRESSURE TESTED
checkpoint | ROLL OVERS COMPLETE AND SECURE
checkpoint | APARTMENT CLEAN OF MATERIALS
checkpoint | FW CLEANNED, COVERED AND CLEAR OF DEBRIS
checkpoint | AAV REQUIRED?
checkpoint | FIXTURE SET OUT CORRECT
checkpoint | CLIENT VARIATION CHECKED AGAINST SCHEDULE
checklist | Kitchen Fit Off
section | SINK
checkpoint | JOINERY
checkpoint | STONE
checkpoint | MIXER
checkpoint | WASTE
checkpoint | DW CONNECT
section | Cooktop
checkpoint | STONE/ SPLASH
checkpoint | COOKTOP
checkpoint | CONNECTION
checklist | BATHROOM 1 & 2 Fit Off
section | Basin
checkpoint | JOINERY
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | Shower
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checkpoint | BATH
checklist | ENSUITE Fit Off
section | Basin
checkpoint | JOINERY
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | Shower
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checkpoint | BATH
checklist | LAUNDRY Fit Off
section | Details
checkpoint | TILE
checkpoint | TROUGH
checkpoint | MINI STOP
checkpoint | STAND PIPE
checklist | DDA Fit Off
section | Basin
checkpoint | JOINERY
checkpoint | STONE
checkpoint | BASIN
checkpoint | MIXER
section | WC
checkpoint | TILE
checkpoint | GROUT
checkpoint | WC
section | Shower
checkpoint | TILE
checkpoint | GROUT
checkpoint | RAIL
checklist | Residential Lounge Fit Off
section | Sink
checkpoint | JOINERY
checkpoint | STONE
checkpoint | MIXER
checkpoint | WASTE
checkpoint | DW CONNECT
section | Cooktop
checkpoint | STONE/ SPLASH
checkpoint | COOKTOP
checkpoint | CONNECTION
checklist | KITCHEN Commissioning
section | Details
checkpoint | KITCHEN SINK
checkpoint | SINK MIXER
checkpoint | DISHWASHER
checkpoint | DISHWASHER RAN
checkpoint | HOT PLATE
checkpoint | SINK WASTE
checkpoint | COVERPLATES
checklist | BATHROOM 1 & 2 Commissioning
section | Details
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | BATH MIXER
checkpoint | BATH OUTLET
checkpoint | AAV
checkpoint | BATH
checklist | ENSUITE Commissioning
section | Details
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | BATH MIXER
checkpoint | BATH OUTLET
checkpoint | AAV
checkpoint | BATH
checklist | LAUNDRY Commissioning
section | Details
checkpoint | W.M STOPS
checkpoint | TROUGH
checkpoint | TROUGH MIXER
checkpoint | TROUGH WASTE
checkpoint | STAND PIPE
checkpoint | FLOOR WASTE
checklist | DDA Commissioning
section | Details
checkpoint | W.C
checkpoint | BASIN
checkpoint | CLEAN BASIN FW
checkpoint | SHOWER MIXER
checkpoint | SHOWER ROSE
checkpoint | SHOWER WASTE CLEANED
checkpoint | TEMP VALVE
checkpoint | AAV
checklist | Residential Lounge Commissioning
section | Details
checkpoint | KITCHEN SINK
checkpoint | SINK MIXER
checkpoint | DISHWASHER
checkpoint | DISHWASHER RAN
checkpoint | HOT PLATE
checkpoint | SINK WASTE
checkpoint | COVERPLATES
checklist | Penetrations
section | Details
checkpoint | Slab Penetrations (All slab penetations installed as per Plan)