## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-137-STR-PSDS-Structural Concrete
ITP Description: |  | Structural Concrete
Discipline (e.g. CIV/STR/RAIL: |  | 137-STR-PSDS
Revision Number: |  | 0
Revision Date: |  | 2024-02-22
ITP created by: |  | Mathew Velcek
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team :
Inspection & Test Plan - Structural Concrete
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-02-22
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 602 October 2007 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 610 February 2020 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 611 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | VicRoads Section 614 June 2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Non Dependent | AS3810.1 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Concrete Mix | 610.07 Table 610.071 IFC Drawings | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
2.2 | ACRS Certification (for Reinforcement) | 611.05 (a) | Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days of award of contract | HP | Nominated Authority | This ITP
2.3 | Bar Chairs/Aspros Certification | 610.26 (a) | Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days prior to placement of reinforcement | HP | Nominated Authority | This ITP
2.4 | Evaporative Retardant | 610.17 (f) | Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | HP | Nominated Authority | This ITP
2.5 | Curing Compound | 610.23 (d) | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, 4 weeks prior to placement of concrete | HP | Nominated Authority | This ITP
3 | Preliminaries - Procedures & Documentation
3.1 | Concrete Placement and Compaction Work Method Statements | 610.18 (a) (i) | Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.2 | Concrete Sampling and Testing Procedure | 610.18 (a) (v) | Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.3 | Concrete Placement and Compaction Toolbox Meeting | 610.18 (a) (iv) | Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.4 | Hot and/or Cold Weather Concreting Procedure | 610.17 (a) | Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 2 weeks prior to placement of concrete | HP | Nominated Authority | This ITP
3.5 | Curing Methodology (for Concrete and Grout) | 610.23 (a) | Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of concrete | HP | Nominated Authority | ConQA Hold Point Release
3.6 | Concrete Drilling Procedure | 610.46 | Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Approval number [free text box] | Document Review | Where applicable, once, 2 days prior to drilling | HP | Nominated Authority | ConQA Hold Point Release
3.7 | Temprature difference measuring-Calibration | MRPA Quality Management Plan | Calibration records are valid and up to date. Attach: Calibration certificate | Document review | Where applicable | HP* | PE | This ITP Attached calibration certificate
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.2 | Survey Set-out | IFC Drawings 610.47 (a) Table 610.472 | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
4.3 | Excavation support | 602.02 | For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal. Enter: Teambinder Approval number [free text box] | Document Review | Where applicable, not less than 10 business days prior to excavation | WP | SE/PE/SPE | ConQA Hold Point Release
4.4 | Excavation Inspection | 602.03 | Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority. | Visual | Where applicable, prior to placing blinding concrete | HP | Nominated Authority | ConQA Hold Point Release
5 | Construction Activities
5.1 | Formwork Design and Construction | IFC Drawings 614.04 614.05 614.06 | Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected. | Document Review Visual Measure | Each type of element | IP | Temporary Works Designer Proof Engineer SE/PE/SPE | This ITP
5.2 | Formwork Certification - Formwork Inspection (Members Greater than 2m) | 614.08 | The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Walls with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B | Document Review Visual Measure | Each element (where greater than 2m) | HP | Temporary Works Designer Proof Engineer | ConQA Hold Point Release
5.3 | Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m) | 614.08 | The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Walls with heights less than 2.0 metres Attach: Attachment C | Document Review Visual Measure | Each element (where 2m or less) | HP | Temporary Works Designer Proof Engineer | ConQA Hold Point Release
5.4 | Pre-pour Survey | 610.47 (a) Table 610.472 | A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element. | Measure Visual | Each element | HP* | Surveyor SE/PE/SPE | This ITP
5.5 | Reinforcement Placement | IFC Drawings 611.06 611.09 611.10 611.11 611.12 | The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations). | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.6 | Cast-in Items | IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2 | All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm | Measure Visual | Where applicable, each element | IP | Foreman SE/PE/SPE | This ITP
5.7 | Thermal Differential Monitoring | 610.22 | Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints | Measure | Where applicable, each element | IP | Foreman SE/PE/SPE | This ITP
5.8 | Pre-pour Inspection | IFC Drawings 610.18 (a) (ii) & (iii) | Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. ATTACH: Pre-Pour Checklist | Measure Visual | Each element | HP | Nominated Authority | ConQA Hold Point Release Pre-pour checklist
5.9 | Weather Conditions & Evaporation Limits | Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171 | All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record. | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP Concret Pour Record
5.10 | Concrete Testing - Sampling Frequency | Site Sampling & Testing Procedure 610.16 (b) | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record. | Test | Each element | IP | Concrete Tester Foreman SE/PE/SPE | This ITP Concret Pour Record
5.11 | Concrete Testing - Slump | 610.16 (c) | Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record. | Test | Each sample of Standard or Superplasticised Concrete | IP | Concrete Tester | This ITP Concret Pour Record
5.12 | Concrete Testing - Spread, Passability & Viscosity | 610.13 (b) | Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record. | Test | Each sample of Self-compacting Concrete | IP | Concrete Tester | This ITP Concret Pour Record
5.13 | Concrete Testing - Compressive Strength Cylinders | Site Sampling & Testing Procedure | Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record. | Test | Each sample | IP | Concrete Tester | This ITP
5.14 | Supply & Discharge Rates | 610.13 (a) & (f) | Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record. | Measure Visual | Each load | IP | Foreman SE/PE/SPE | This ITP Concret Pour Record
5.15 | Placement & Compaction | Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i) | All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets | Visual | Each load | SP | Foreman SE/PE/SPE | This ITP Concret Pour Record
5.16 | Surface Finishes | IFC Drawings 610.31 610.20 | Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.17 | Curing | IFC Drawings 610.23 (f) | The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location. Where formwork is removed prior to the completion of the curing period, curing shall recommence within half an hour. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.18 | Curing after formwork removal | IFC Drawings | After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing | Visual | Each element | IP | SE | Thip ITP
6 | Post-construction Activities
6.1 | Thermal Differential Monitoring | 610.22 | Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report | Document Review | Where applicable, each element | IP | Foreman SE/PE/SPE | This ITP
6.2 | Removal of Formwork | 610.25 | Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in Table 610.251 have elapsed, after completion of the placing of concrete. | Document Review | Where applicable, each element | IP | Foreman SE/PE/SPE | This ITP
6.3 | Surface Inspection - Cracks | 610.24 | No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair. | Visual Measure | Each element | IP | SE/PE/SPE | This ITP
6.4 | Surface Inspection - Surface Finish | IFC Drawings 610.31 (a) - (n) 610.32 | Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. | Visual | Each element | IP | SE/PE/SPE | This ITP
6.5 | Measurement of Concrete Cover | 610.34 | Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record | Measure | Each element | IP | SE/PE/SPE | This ITP
6.6 | Early Age Compressive Strength Results - Placement of Fill Against Concrete | Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35 | Fill is not placed against concrete within 14 days of pour. Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure. Attach: Concrete Test Results or Maturity Test Results | Document Review | Where applicable, each substructure element | SP | Foreman SE/PE/SPE | This ITP
6.7 | Compressive Strength Test Results | IFC Drawings Table 610.05.051 610.16 (g) | 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results | Document Review | Each cylinder | IP | SE/PE/SPE | This ITP
6.8 | As-built Survey | IFC Drawings 610.47 Table 610.472 | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.9 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /