## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Cleanroom Checklist - GPL-QSE-ITP-FIT-012 (Rev00)
section | Prior to Works
checkpoint | Confirm sealant product to be used
text | Sealant brand, type, batch number, production date, shelf life:
checkpoint | Confirm corner details to be used within cleanroom
text | Floor to wall:
text | Wall to wall:
text | Wall to ceiling:
checkpoint | Cleanroom material delivered clean, protected, and undamaged (plastic wrap), provide photos
bool | Sandwich panels
bool | Mechanical ductwork
bool | Hydraulic ipework
bool | HEPA filters
bool | Grilles
bool | Lights
bool | Windows
bool | Doors
checkpoint | Confirm relevant approved design drawing
text | Refer Shop Drawings, confirm dwg no. and revision no.
section | During Works
checkpoint | Cleanroom walls checklist, provide photos
bool | Support framing installed as specified
bool | Panel joints fully sealed
bool | Wall to wall joints are coved and sealed
bool | Wall to ceiling joints are coved and sealed
bool | Wall to floor joints are coved and sealed
bool | All penetrations fully sealed
checkpoint | Cleanroom ceilings checklist, provide photos
bool | Support framing installed as specified
bool | Panel joints fully sealed
bool | Ceiling to wall joints are coved and sealed
bool | All penetrations fully sealed
checkpoint | Mechanical checklist, provide photos
bool | Confirm ductwork flanges ae bolted & sealed
bool | Confirm insulation installed and sealed
bool | Confirm inside of ductwork is clean
bool | Pressure testing completed
bool | Supply & return air grilles completed
bool | HEPA factory certificates of conformity saved
bool | HEPA installation complete & test points installed either side
checkpoint | Pass Through Hatches installed, cleaned and sealed
label | Attach commissioning tests
checkpoint | Electrical checklist, provide photos
bool | Confirm sub mains power & distribution boards are installed
bool | All penetrations & cables sealed
bool | Confirm light fittings installed and tested
checkpoint | Compressed Air checklist, provide photos
bool | Pipework and Isolation valves installed as per approved specification
bool | Pipework labelled for contents and directional flow
bool | Backflow protection installed
bool | Pressure testing completed
bool | Hose connections within cleanroom sealed
checkpoint | Confirm joinery is installed and completed
label | Confirm no wood is exposed, all must be sealed, no gaps
checkpoint | Doors & Access Control checklist
bool | Glass supplied as per specification & Australian Standards
bool | Doors closing flush and sealed when in closed position
bool | Hardware fitting flush & sealed to surface
bool | Interlocks installed in accordance with approved design
bool | Sealant to hinges, frame, glazing, and door closers all complete
checkpoint | Windows checklist
bool | Glass supplied as per specification & Australian Standards
bool | Window glass finishing flush and sealed
checkpoint | Confirm sealing works are completed throughout
checkpoint | Confirm testing & monitoring instrumentation is calibrated
text | BMS: Make, model, serial number:
text | EMS: Make, model, serial number:
checkpoint | Attach Cleanroom Consultant Inspection Report(s), and confirm all actions are closed out
section | After Works
checkpoint | Review panels & joints to ensure no visible damage/cracks/misalignments
checkpoint | Confirm final cleaning completed for area
checkpoint | Attach subcontractor ITP for Sandwich Panels
section | Sign Offs
checkpoint | Orwell Sign Off
holdpoint | Request Sign Off
label | Authorised By: DL
label | Issue Date: 24.06.2023