## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | DN1210-003 ITP Earthworks Rev IFC1 | itp | DN1210-003 ITP Earthworks Rev IFC1 | 87e4688e-99ab-4155-9a39-0c7255ae4bd5
| section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS
| checkpoint | 1.1.1 - Earthworks Methodology
0d104855-89f4-593a-85bd-a50e0fe9215f | note | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
25a842ae-f368-56bf-896b-35fc18939be2 | note | Acceptance / Conformance Criteria - Engineers Approval
bcf47cec-4f3a-530c-9d04-d1129bd3fe6a | note | Standard / Specification - Appendix V
37a6a238-f616-5b99-a3c7-9f3188b36a68 | note | Verifying Document - Approved Methodology
39b5f231-e8ac-5ae7-ae5b-1d3a6d1a3e2c | note | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
7fc060d6-a7d5-5929-b685-00c4c82f5444 | note | Verification Activity: Activity - HP
de17480b-9985-509f-b3bc-3d9282f4410e | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1.2 - Ecology Sign Off
cab789a8-b93b-5ae2-8087-75845ee54abf | note | Detail - Confirmation from Ecology that earthworks can proceed
56e8fc5e-abb4-53f4-95cd-424f70f8dea3 | note | Acceptance / Conformance Criteria - Email
54b8b3a8-a4b8-5826-84b2-0394718c82c0 | note | Standard / Specification - Internal Hold Point
5b86395a-bf45-5246-af35-80455d218425 | note | Verifying Document - Email from Ecology NZ
c89c534e-0044-576a-bc67-1065b357bdfd | note | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
2ea624cd-7e2b-5a5c-8310-b435b1f9d82d | note | Verification Activity: Activity - H
4714b52a-304b-57fd-a3c9-afe336ad757b | note | Verification Activity: By - QM
| checkpoint | 1.1.3 - Erosion & Sedimentation Controls
90189df5-862e-578d-ac66-0cec0908d406 | note | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
60bf084c-2ef1-5d5d-bb11-3730f8061b1c | note | Acceptance / Conformance Criteria - As-built Completed
e50e3322-03bc-5b50-a82f-b1b5726dfa72 | note | Standard / Specification - Internal Hold Point
a6624630-2f33-5e2f-9195-8980356dc0db | note | Verifying Document - ESC As-built
eccc1421-408d-5927-9abf-dafa4be2987d | note | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
98deee31-b439-56dd-bbc4-ce083ff8680d | note | Verification Activity: Activity - H
54de11cd-f76c-5415-91b9-aecf8d005251 | note | Verification Activity: By - QM
| checkpoint | 1.2.1 - Weathering Resistance
455b43de-ffc1-5af2-a1de-cf40fa18ea41 | note | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
f8552aff-4b9f-5d2c-a904-d6da94d55840 | note | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
303ebd44-48a4-571f-842c-465066d59d51 | note | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
f35bdac5-7335-562e-a47e-19736f7337b6 | note | Verifying Document - IANZ Accredited Report
f5d5ff0f-2b7c-5113-b628-c021affab5ff | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
8fe01f64-c7b3-59ce-8bdb-e04d432f27e1 | note | Verification Activity: Activity - HP
27b4c96d-f6f1-577e-832e-aca2fad4548c | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.2 - Los Angeles Abrasion Test
6d44388d-ed58-540b-ba94-b9114a6f53d0 | note | Detail - NZS4407:2015, Test 3.12 - The Abrasion Resistance of Aggregate by use of the Los Angeles Machine
6af9c5f7-9082-58c6-a445-b02aea78da9a | note | Acceptance / Conformance Criteria - 0.5
81f1e4c6-0496-593b-aaf7-2460f9b0bc05 | note | Standard / Specification - PS 16.5.5 Appendix V
83bdb4ff-97b9-5efb-bb6b-0afeb201ad98 | note | Verifying Document - IANZ Accredited Report
2233790e-3df5-58d8-950c-3a824e566622 | note | Testing Quantity Required (based from schedule qtys) - 1 Test Required, Results to Engineer 2 wks before importing
4e604921-3ac9-5f94-aa82-22b57f94de55 | note | Verification Activity: Activity - HP
147b59c3-fe37-534c-9bbb-5d24fd9d31a4 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.3 - Particle Size Distribution
a247f6ea-c2f1-5c89-a542-e6c3b691162b | note | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
a5ae7ee5-97af-5ab1-a4a9-f34f0615fc4a | note | Acceptance / Conformance Criteria - No Particles >200mm
30c42a9c-5468-5ddc-8294-ee4b44b237fe | note | ○ Maximum fines 10% passing 75micron sieve
af373d42-19f1-5ebe-9a47-dee81487a830 | note | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
1107cdc3-faec-5731-a82c-a43b17dd3fb0 | note | Verifying Document - IANZ Accredited Report
a1e0c85f-e622-50ce-9b8b-a2a1ff24b887 | note | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
77c7929e-be41-5f74-9c23-69d4baa66048 | note | ○ 0-400 - 2 tests
81c9e55d-68ec-593b-955c-8cfe75a66d11 | note | ○ 400-1,500 - 3 tests
c8a6f68a-17d0-57ec-873e-fdf59f3bd15f | note | ○ 1,500-4,000 - 4 tests
e8a86c27-404e-5dcf-ad75-7093fad8fc25 | note | ○ >4,000 - 1 test for each additional 1,000m3
cea069ba-656a-5d8b-a896-3a16bc7a2650 | note | – Results to Engineer 2 wks before importing
7fddd767-f5a6-5c7c-b124-9737d1789702 | note | Verification Activity: Activity - HP
fd49fcb5-31fc-5ba3-b037-a9a5400dda71 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.4 - Maximum Dry Density and Optimum Water Content
e3bb3786-dfb5-5944-80d0-3bca0eae2690 | note | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
c9c03eee-c3c6-5b8f-bf85-9c8cc2963a5a | note | Acceptance / Conformance Criteria - Report Value Only
735a4b90-cf66-5701-b2ec-83c51d897255 | note | Standard / Specification - Appendix XVIII, Appendix V
b6933e85-9e77-5e0d-ac53-02b2bb6ed28a | note | Verifying Document - IANZ Accredited Report
c90cab11-e5f8-5e38-af10-b817d24bac03 | note | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
e92c2404-f896-5eb7-96ad-0389257f7de1 | note | Verification Activity: Activity - HP
ddbd66dd-516f-5c64-9c78-5a56b46248bd | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.5 - Soaked CBR
405d3666-c324-5372-8944-f29095b45593 | note | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
8b3db5d7-2af7-5ece-82a4-c56b78a1e74d | note | Acceptance / Conformance Criteria - >25%
b9dea11c-5f41-58bc-ac45-51cb9785a966 | note | Standard / Specification - PS 16.5.5, Appendix V
a0188409-65e1-5017-ae63-28794e961176 | note | Verifying Document - IANZ Accredited Report
5d8ecde9-fa21-58ca-b177-86a352aeb58b | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
4568dd7f-8d2f-5e6f-b936-479b8a1f7dee | note | Verification Activity: Activity - HP
a85d81f3-c063-51ca-8606-a7cf85fcdc13 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.6 - Solid Density
86feadec-2cf4-54f2-92ca-451a5718cf11 | note | Detail - NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles
c0c95f97-4b89-571b-9b8a-3eb659c2137c | note | Acceptance / Conformance Criteria - Report Value Only
4b795ca1-e4f8-5e95-b7aa-b41b5ce72d32 | note | Standard / Specification - Appendix XVIII, Appendix V
6af41c27-9d65-5220-96d6-422dfba7bede | note | Verifying Document - IANZ Accredited Report
0e33c057-1ab0-59b0-aa65-0d9e4596204e | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
e70b4675-8a59-557b-bc32-7e541f2bcb2c | note | Verification Activity: Activity - HP
4c5917fd-dd41-5f03-8fb8-0d49e52f5baf | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2.7 - Crushing Resistance
e3895585-b89f-5ff3-a848-8bd602992717 | note | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
7c707ea0-5bf2-515e-851d-5a872650e550 | note | Acceptance / Conformance Criteria - >100KN
a86e42bb-c961-58ca-8d7d-2f2810d541fe | note | Standard / Specification - Appendix XVIII, Appendix V
789dae34-e3d8-59c1-baea-43317b01c78d | note | Verifying Document - IANZ Accredited Report
9a719381-f8b5-5c9c-a7d3-f70743da7f1d | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
c8ea3b12-2b63-57ab-8fb2-bdc4261830b1 | note | Verification Activity: Activity - HP
37d17fc2-2563-5cf7-885a-aaded160a990 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3.1 - Particle Size Distribution
5500a823-de90-5fae-b654-46fac739d405 | note | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
fb118fa7-7067-5703-a701-3521776172af | note | Acceptance / Conformance Criteria - Report Value Only
c0c1507c-ef34-5ff8-b5f2-2d67df5faa81 | note | Standard / Specification - PS 16.5.12
f629e6c6-6c58-5b68-b3c7-f663ac7e7ecd | note | Verifying Document - IANZ Accredited Report
3f63d8cf-77d4-5e1f-898e-de00f21d5404 | note | Testing Quantity Required (based from schedule qtys) - Number of Tests Required?
e989a096-c208-544e-b3d3-79a5413d7251 | note | Stockpile size:
b2fc4c02-b88c-5191-860a-8fd102257e24 | note | ○ 0 to 400m3 – 2 tests
b9c060e1-3635-5a39-abe6-32c06bcaaf86 | note | ○ 400 to 1500m3 – 3 tests
2bf659e3-f2c6-5582-9b7a-6b45dc6096c5 | note | ○ 1500 to 4000m3 – 4 tests
77c86e10-7365-56fd-b6e4-4d3cd7293646 | note | ○ >4000m3 – 1 test for each additional 1,000m3
2e4a7d5c-6504-5210-b630-49aee01502f6 | note | – Results to Engineer 2wks before importing
98a632fe-7838-5415-83bf-bcdbcd57418d | note | Verification Activity: Activity - HP
40ab8af6-15c9-56b6-9825-58a59e44fc21 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3.2 - Maximum Dry Density and Optimum Water Content
56d35ba2-765a-58eb-847e-ecb2a74da5e3 | note | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
ac589409-3515-5145-898d-cce30efe5571 | note | Acceptance / Conformance Criteria - Report Value Only
e434a1b1-a134-552e-87c8-633a2375f5fc | note | Standard / Specification - PS 16.5.12
c30be714-03f2-52c1-b30d-506b1280e513 | note | Verifying Document - IANZ Accredited Report
9d9e5a1f-8a0b-550a-b5eb-12e72cf9c410 | note | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
05cd823d-e183-52a6-9e4f-fe4022db5aaa | note | Verification Activity: Activity - HP
1136acd7-a8da-533f-8fdf-30e0d8cd75b9 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4.1 - Crushing Resistance
16c2530f-9a49-54de-8328-b7d6d3aa0ffd | note | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
aa510cf1-5dec-5617-8513-48cf38aa40c0 | note | Acceptance / Conformance Criteria - >100KN
b3e554f2-3531-538b-be07-66f41752baf6 | note | Standard / Specification - Appendix XVIII
e05b8394-37d9-5b43-970a-2b3f5a2d638c | note | Verifying Document - IANZ Accredited Report
8830ac9f-4dbe-5315-ad7f-39f34c3d3407 | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
9dfbdb6f-bc40-5bdf-ad5b-3ccf30f3ffee | note | Verification Activity: Activity - HP
d65ba4d4-1351-57c0-ade1-641d6be463ea | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4.2 - Particle Size Distribution
7c63cec1-d77f-571c-82f5-f04a3fe85bd3 | note | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
e257efc7-a9b0-583a-927c-7cc989ea73ff | note | Acceptance / Conformance Criteria - Max Particle Size 53mm
080b8c60-2510-5f1d-a9bc-62fd78e805d6 | note | ○ Max 10% passing 13.2mm sieve
20af941c-9c90-5052-83f2-a997a07fd26a | note | Standard / Specification - Appendix XVIII
3d076029-5037-5ffe-b7b7-a4d803a2cbd1 | note | Verifying Document - IANZ Accredited Report
f3cc4b76-e86e-5cd5-b78b-2cb413dedc6e | note | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3, Results to Engineer 2wks before importing
aa4e1f07-9947-5ccc-9368-37ecdbc742e1 | note | Verification Activity: Activity - HP
c4f88f3b-3a15-5c5b-a32f-35cd0ea0964b | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4.3 - Weathering Resistance
ea32fa72-b426-5fce-8499-e60b73cb0cc0 | note | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
d53186d9-99b3-50e1-ad38-3116af32fdb1 | note | Acceptance / Conformance Criteria - CA or better
43cc3027-84d8-5f0a-968c-6a110e28fc24 | note | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
56a7ef2d-1538-5382-ab04-2a5d78ce4f43 | note | Verifying Document - IANZ Accredited Report
45a931e4-c16b-5b2d-a219-99b82043c1a7 | note | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
4f11e08b-a428-5496-9f61-7f9fefa86fee | note | Verification Activity: Activity - HP
8cd1c7e3-2ff9-5744-aeff-4108c6661726 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5.1 - Geotextile
3a88df61-3f1a-550c-94d9-b7af2c87bf57 | note | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
f32ac2fc-585f-5298-ad31-f1bf364ebe5f | note | Acceptance / Conformance Criteria - Engineers Approval
e40b5f84-336c-54fd-acce-915b13a43f8b | note | Standard / Specification - PS 16.5.7 Appendix V
a7859f63-d29a-5e59-b2c7-0459b955ea14 | note | Verifying Document - Data Sheets
43e247ac-a68e-5bc6-8e38-943217724484 | note | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
981ea3d0-0edc-552d-b40f-7a710ccf5c87 | note | Verification Activity: Activity - HP
5ecb55bf-6dd3-5a7e-8b3a-5a025ad69587 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6.1 - Laboratory Testing for Soil Suitability
010d3206-ba9e-55a2-96ba-898263e8f9ac | note | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse
a40d8b74-816d-5384-858a-37018196f028 | note | ○ Soil Reaction
8a17c5bb-8886-5ba2-b97f-dd797a8bf017 | note | ○ Electrical Conductivity
ac7eb074-bf3e-5c77-b56d-1d9e06434a0d | note | ○ Mechanical Analysis (texture)
501fa943-68c2-57b5-8881-80661b33f270 | note | ○ Stone Content
cdd2f9e9-e38f-57da-a77b-76810a24894c | note | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
228916c7-3c91-52ec-9095-02bc4182f6ff | note | ○ Organic Matter Content
d3ae7535-eeb1-5748-8d1f-40ad3e815a0f | note | ○ Check for Toxic or Hazardous substances
599b7b46-d953-52ac-9a14-61415586f08d | note | Acceptance / Conformance Criteria - Engineers Approval
580f54ed-bd7f-5fa6-9e96-4f1eee364204 | note | Standard / Specification - NZTA P39:2013 3.1
e58a48e4-074e-5419-b8f4-c5115d268738 | note | Verifying Document - Hill Laboratories Test Report
bca7e7ce-8f0c-5c46-bbe7-9c9b00e3649c | note | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
4caf85c5-b3d1-51f2-ae8a-4eacde45cd51 | note | Verification Activity: Activity - I
5fdd1e21-9457-50e5-a7b9-3ccd39339507 | note | Verification Activity: By - SE
| section | SECTION 2 – CUT SUBGRADE TESTING
| checkpoint | 2.1.1 - Proof Roll
3f42d642-f175-542b-82b1-b5985457f28f | note | Detail - Visual Inspection of Proof Roll
7fff358b-d85f-5211-aeca-a69e18d3e5bb | note | Acceptance / Conformance Criteria - Displacement <15mm
a197c149-fbfd-5ba1-8b7f-8b20882dc8c2 | note | Standard / Specification - Appendix XVIII
4f8645a9-3bfc-5a34-b967-f66786a89908 | note | Verifying Document - Visual Observation
75d1d38d-26b7-5102-b1ff-f76a43a42a76 | note | Testing Quantity Required (based from schedule qtys) - Across stripped area
74103d69-a1be-5ff9-86a8-29373f64ed06 | note | Verification Activity: Activity - V
93001987-c82a-50b0-a687-c7bf697943d7 | note | Verification Activity: By - SE
| checkpoint | 2.1.2 - Cut Subgrade Inspection
e26b7ef8-d97c-53fd-98d6-bd056ebb8715 | note | Detail - Engineer to inspect all foundation surface inspections
dd7408db-f9e9-5c49-a395-0b757e41b7eb | note | Acceptance / Conformance Criteria - Engineers Approval
8967e5c2-9ac2-5a5e-a527-f835a8f34437 | note | Standard / Specification - Appendix V
82c157b0-e50a-5f86-a528-dfb1cca45419 | note | Verifying Document - Visual Observation
226b4377-b9bc-53ee-90bf-2d4a82840a3b | note | Testing Quantity Required (based from schedule qtys) - Across stripped area
580e74ff-fe93-5045-83c9-aa7c7882396a | note | Verification Activity: Activity - HP
9776a4e5-9649-571d-a52c-cfd171f98003 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
bd66fb71-ae1b-5640-b1f8-904acfcf4caf | note | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
3a58ea8b-4e5e-56ec-a645-4316abdd9086 | note | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
beb4eb0e-ca18-56a8-8abb-ef2a25f558ab | note | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
f8e8deaf-c24b-52ec-bbc5-dd57761b1134 | note | ○ Single Test Min SU: >50kPa
d7d3c93d-c661-51d9-96fa-2886ab91ae83 | note | Standard / Specification - Appendix XVIII
4800964a-2e44-58dd-8ae5-6cfefab59414 | note | Verifying Document - Shear Vane Report
95fe8f2d-d11b-5ad8-9773-a44dc77da221 | note | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
00a5ee31-6cf8-513b-9d8e-b0f363bebd09 | note | Verification Activity: Activity - I
b1caa199-7822-547a-93a0-730499a9952f | note | Verification Activity: By - SE
| checkpoint | 2.2.2 - Cut Subgrade Testing - Cohesive Soil Scala Penetrometer
85939507-7536-56c8-98c0-750a595429d5 | note | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
21b65424-0e03-5334-9d9b-436ee7f600da | note | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
442bb04f-f985-56fa-882c-fcf48a8445dd | note | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
6799b695-b46a-56c9-b559-7101b39b40da | note | Standard / Specification - Appendix XVIII
3e9fea26-04a8-5abd-9ca0-93492092201e | note | Verifying Document - Scala Report
6b2f46b8-06b9-574b-872b-131d7b96bd02 | note | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
893b184e-00c9-5219-9d89-809882348d02 | note | Verification Activity: Activity - I
06b7a9ea-f1d5-5a3a-ba14-ecb6d27c0a51 | note | Verification Activity: By - SE
| checkpoint | 2.3.1 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
627f1969-cece-53a7-b4e0-887e064ead4a | note | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
15a01cd8-db36-51de-b3c9-bbd886d9a615 | note | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
d0c3d857-db70-5038-bc5f-70d9ab08bfc9 | note | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
bd8ecb9b-503f-59ea-9e89-aa4bd1860345 | note | Standard / Specification - Appendix XVIII
23f67828-a6b9-5f26-a05d-1d9b894134dd | note | Verifying Document - Scala Report
d54d614c-205d-5c9d-8389-d6f22661da36 | note | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
8f4f6f91-7c00-5db3-8f74-0404c390276c | note | Verification Activity: Activity - I
37ee757f-bfac-513d-82ec-e2d557e138d8 | note | Verification Activity: By - SE
| checkpoint | 2.4.1 - Release of Hold Point
d4d30683-245a-5408-bfc0-029abcc9783f | note | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
571f862a-d30f-5374-9c08-2c985747a972 | note | Acceptance / Conformance Criteria - Engineers Approval
47c959ed-67f2-51be-a333-886e62e90702 | note | Standard / Specification - PS 16.9.3
52c75e80-e641-57f3-87e8-5ff1a45838bc | note | Verifying Document - Written Certification
d1db5ac9-4c20-509e-86d7-1d88937f7487 | note | Testing Quantity Required (based from schedule qtys) - Engineers Approval
cb0ea1ae-9dbe-5947-a1d4-c0d8b0b8968b | note | Verification Activity: Activity - HP
6e564daa-c9ea-5c77-9393-9a6792317aae | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 3 – CUT SLOPE INSPECTIONS
| checkpoint | 3.1.1 - Cut Side Slope Inspection
9b8ee6b6-c1d8-5143-a084-b27a5d279ae0 | note | Detail - Inspection records to include photographs, logged soils (to NZ Geotechnical Guidelines) and shear vane testing
6f3952ff-2a7a-5418-ab3f-a84b218867af | note | Acceptance / Conformance Criteria - Engineers Approval
b2a0f6ea-38ff-504e-8302-4c02f4902b36 | note | Standard / Specification - PS 16.6.4
0cfbc095-713f-50b2-b962-1709167fda88 | note | Verifying Document - Site Records
6de84e34-6b3b-5965-ad4a-b91f06ab0ce5 | note | Testing Quantity Required (based from schedule qtys) - As per Engineer
12589d38-c993-5bb1-81fa-7b4ba2669742 | note | Verification Activity: Activity - HP
fe3486b0-6cc4-5d9b-a6e9-154171770e1c | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Cut Slope - Soil Log
1ad4f939-cb75-5ff9-9543-62cea2bb10fb | note | Detail - Soils to be logged to NZ Geotechnical Guidelines
7e8b5e53-75e3-5e68-998b-905d79354b01 | note | Acceptance / Conformance Criteria -
70e6c899-f866-57d8-8fdb-aac02ae513c1 | note | Standard / Specification - PS 16.6.4
3397ab39-8b75-56fd-be39-bd2c305125cb | note | Verifying Document - Soil Log
f9f254a0-753e-5be3-9750-266085fb3728 | note | Testing Quantity Required (based from schedule qtys) -
e9f36af9-e15c-5a9e-af0f-738b50136eb1 | note | Verification Activity: Activity - I
dc69b9db-23b1-5a06-8db4-abefd628ef4e | note | Verification Activity: By - SE
| checkpoint | 3.1.3 - Cut Slope - Shear Vane Test
e7163e68-b0e3-5f2f-96a5-ce33320c1c53 | note | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
45014ec0-1f8c-5270-b530-7f36a1ee06ac | note | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
58bfd0b1-7958-5993-a896-e3e22028cf3c | note | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
ffe515da-ee85-5ede-9fbf-b3c85024cae4 | note | ○ Single Test Min SU: >50kPa
af1d3197-a6e5-5b8f-8b21-ad8da62ca655 | note | Standard / Specification - PS 16.6.4
d8f50f3c-cc10-5a51-a094-69f7d2654f34 | note | Verifying Document - Shear Vane Report
15f00dfd-9baa-5595-b893-bc90b866bd83 | note | Testing Quantity Required (based from schedule qtys) -
739cd2cf-8354-588f-910e-bdad0829c121 | note | Verification Activity: Activity - I
847bef16-6e0a-527a-8e2f-63bb3d5f7e61 | note | Verification Activity: By - SE
| checkpoint | 3.1.4. - Drainage Measures if Seepage Encountered
b5d7ad09-54d7-5e1f-b147-e713fc784924 | note | Detail - Borehole Drains or ballasting may be required, to be directed by Engineer
7e769fe4-3a85-5663-8597-cce49df0563e | note | Acceptance / Conformance Criteria - Engineers Approval
c701c9ae-eb66-55ac-a955-752cb3f99dc5 | note | Standard / Specification - PS 16.6.4
1cfb59e9-e301-58d7-b234-ec9b84187ba8 | note | Verifying Document - Engineer approval
dc550f5d-09c6-57fa-a9de-3afe17fe3ff6 | note | Testing Quantity Required (based from schedule qtys) - As per Engineer
d87efcc5-a697-588f-b1e9-d5a654ad196d | note | Verification Activity: Activity - I
ff7ce86c-a7b2-50c1-9745-dd2b9d4105fb | note | Verification Activity: By - ENG
| checkpoint | 3.1.5 - Design and Grade Check
099ba27f-0aa3-5787-b331-288eca947e13 | note | Detail - Confirm cut slopes have been correctly excavated to design and grade
37b6532e-c53c-5014-8b83-16a87e3980b3 | note | Acceptance / Conformance Criteria -
4842107b-db4e-51fc-be72-d50f5651a07d | note | Standard / Specification - PS 16.7.1
a851bc90-faa8-5ded-a6b2-6d85e2e71932 | note | Verifying Document - Survey Records
df52a6eb-a78c-5b0b-8224-d27e7dfe1e35 | note | Testing Quantity Required (based from schedule qtys) -
d99347d2-cfb0-5075-b6f9-15124550728f | note | Verification Activity: Activity - D
c7722149-203e-5f1e-9298-257ba8192655 | note | Verification Activity: By - SV
| checkpoint | 3.1.6 - Stabilisation of Cut Slope Surface
9c8ca8ca-c3ff-5943-95c9-08571de46e16 | note | Detail - Cut slope surfaces to be topsoiled and grass seeded or planted as soon as possible
b47056ce-32ca-584b-b801-937b80fcb179 | note | Acceptance / Conformance Criteria -
190bbdb6-7726-574c-b85d-8f227be9e743 | note | Standard / Specification - PS 16.6.4
af2bc54a-add3-5907-9179-35f1b262589c | note | Verifying Document - Site Records
6cc1ee2b-ab37-5006-80a2-362747077ea2 | note | Testing Quantity Required (based from schedule qtys) -
3ae6586d-f990-52a3-aea5-9767d20674ab | note | Verification Activity: Activity - C
0480d17f-a566-54d9-836c-af9c3b82637b | note | Verification Activity: By - SE
| checkpoint | 3.2.1 - Release of Hold Point
5b1ee707-e641-5e41-9f82-01c7339af913 | note | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
f8acf895-08fb-5d6a-9df3-ae46998181f2 | note | Acceptance / Conformance Criteria - Engineers Approval
5a940419-9a05-569d-877c-84fd3a38bdaa | note | Standard / Specification - PS 16.9.3
14a675cd-e791-50fa-8907-42ad9b0d9518 | note | Verifying Document - Written Certification
dec9c9a2-e516-5c97-896f-06ea24f80b97 | note | Testing Quantity Required (based from schedule qtys) - Engineers Approval
df5c4d78-8ba2-528d-8713-a359de273af9 | note | Verification Activity: Activity - HP
473ff51d-3dff-59b1-8fea-b9093f074bc8 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 4 – UNDERCUT TO WASTE & BACKFILL
| checkpoint | 4.1.1 - Undercut Surface Inspection
eafb8a5a-c8d7-568a-a4da-a4044af9fde7 | note | Detail - Engineer to inspect undercut surface
59b61895-d03a-524f-9906-0bab0c512fae | note | Acceptance / Conformance Criteria - Engineers Approval
332d06ad-16bf-5aca-b370-c5a9bc5b2ce6 | note | Standard / Specification - Appendix V
02068a19-61ba-5c61-9eea-0ab28547c7d8 | note | Verifying Document - Engineers Approval
3bd18812-56b9-5747-a8f3-19c7b1be802a | note | Testing Quantity Required (based from schedule qtys) - Across stripped area
8d9f33b2-ec66-5b3c-a304-18eefd5ee936 | note | Verification Activity: Activity - WP
1d2eba01-d547-5a5c-92e1-b224ce415b25 | note | Verification Activity: By - ENG
| checkpoint | 4.1.2 - Placement of Geotextile on Undercut
c04a919e-c3f7-5310-82a5-6b0fab022ab9 | note | Detail - Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum
98ac6f09-aeb2-5fba-ac8a-b5a07c7cf703 | note | Acceptance / Conformance Criteria - Engineers Approval
17949f10-fbe3-5c39-a253-67d116933f92 | note | Standard / Specification - PS 16.6.4, TNZ F/7: 2003 8.3
c4091482-ed12-5378-86ad-800c128c3b79 | note | Verifying Document -
b49bef8e-cbd1-5bb3-a6b0-dd65950a5a8f | note | Testing Quantity Required (based from schedule qtys) -
62660ee4-52db-5f3d-a6d7-6223f479d337 | note | Verification Activity: Activity - WP
38fefbcc-a542-5d20-b88e-8e4b85d037a0 | note | Verification Activity: By - ENG
| checkpoint | 4.1.3 - Subsoil Drain inspection
f8f335cf-3f36-5edf-a43b-76b204e464f3 | note | Detail - Subsoils to be placed at base of cuts where directed by the Engineer
ebca4ad6-34af-5360-96a7-2623ea7582fe | note | Acceptance / Conformance Criteria - Engineers Approval
fccd3323-eab8-5990-8196-1a8cab2d2b22 | note | Standard / Specification - PS 16.6.4
bf61c6d8-7def-56c8-aadf-0dc8ba0f3866 | note | Verifying Document -
f0b03302-2718-5660-9e96-a23051f8f0a7 | note | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
161edf4e-7dec-5d2d-81b1-e869e63b344b | note | Verification Activity: Activity - WP
e4a94a26-48e1-5152-97d6-7945234ff646 | note | Verification Activity: By - ENG
| checkpoint | 4.2.1 - Release of Hold Point
df6a0f47-131d-5150-b664-3e2398ea95bd | note | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
19ac0b9a-87bd-5144-b9fb-134e403d3d9a | note | Acceptance / Conformance Criteria - Engineers Approval
e59e8ee8-111e-53aa-9e73-d14afd7e90cd | note | Standard / Specification - PS 16.9.3
5e2d2b7f-51c3-57b0-ab11-e99bf1b733c6 | note | Verifying Document - Written Certification
1233e552-20a2-5624-a4b6-4473dd62d5e0 | note | Testing Quantity Required (based from schedule qtys) - Engineers Approval
78e176d2-830b-592f-815a-f533b10fd2ce | note | Verification Activity: Activity - HP
b12fbd0d-43d9-5b7c-85cf-2c14f962f961 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 5 – COMPACTION OF IMPORTED FILL
| checkpoint | 5.1.1 - Compaction - Clegg Hammer
256db5c3-1fdd-5a71-85eb-078779522eb6 | note | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
4f0a304a-13ed-5f07-8d40-20244ff6ff4d | note | Acceptance / Conformance Criteria - Structural Fill:
c73ff527-8e22-5569-a18b-7840e24e53d8 | note | ○ Min CIV 18
1c058744-4d82-5867-bfc0-c5300dc33d61 | note | ○ Ave CIV 20
339e749c-f490-539c-8c6a-74df1480e8d2 | note | Non-Structural Fill:
84cdccf5-8b1d-5cf9-b7b9-0481b6737256 | note | ○ Min CIV 10
4729c983-c925-5f73-b89a-6b1c52193b49 | note | ○ Max CIV 12
6f3cbe26-7f59-59e4-9a8d-b81794a7f114 | note | Standard / Specification - Appendix XVIII
1190abb0-9387-5845-b2f9-89ea5868bd42 | note | Verifying Document - Clegg Hammer Report
46cb6500-5293-54de-bd5c-80d7dea83036 | note | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
1113be76-d87e-5eaa-b284-3e3b0399fcac | note | Verification Activity: Activity - I
1abc12d3-1d40-565a-9828-705e3a6e81b2 | note | Verification Activity: By - SE
| checkpoint | 5.1.2 - Compaction - NDM
5b33c92d-043e-5403-808c-d48497af90f3 | note | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
e54f28cb-9f6e-5015-90c6-d723332121e1 | note | Acceptance / Conformance Criteria - Ave >95% of MDD
bda4a583-1021-5daf-8d37-7911b23579fb | note | ○ Min >92% of MDD
d649f041-1fdd-5aca-b4f7-2ff276e9ac5c | note | ○ Non Granular Material
dd3c4e48-bee9-51f9-8e85-4f2dc9eac914 | note | ○ Max Air Voids 8%
0dd2b56e-40e6-57e6-ba2d-686c5534e15a | note | Standard / Specification - Appendix XVIII
5784e0a1-173e-5792-93c3-8df786c55ff4 | note | Verifying Document - IANZ Accredited Report
bcd85f8b-85e8-56da-a300-c4b5ef7f42b8 | note | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
855fc7af-754a-5edd-8093-5d01250af26d | note | Verification Activity: Activity - I
35b74913-1c23-570c-a29b-6a38def6f9b4 | note | Verification Activity: By - SE
| checkpoint | 5.1.3 - Compaction Trials
2d0fd9b7-688e-5f3d-82b3-d58e0a3ef953 | note | Detail - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (ie construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
982df744-6067-5c7e-98fd-3961f3c508e0 | note | Acceptance / Conformance Criteria - Engineers Approval
6da8b5af-6c4d-5267-8841-accb283d54c9 | note | Standard / Specification - PS 16.6.5
5afd4a8d-a2ca-5131-9bd7-f5e260b93cb1 | note | Verifying Document - Trial Results
38840069-bfa3-5364-bbc0-2bd7c1144c91 | note | Testing Quantity Required (based from schedule qtys) -
3ab6db38-4e76-5e78-8fdd-3e93a3812b55 | note | Verification Activity: Activity - R
1d6e11d4-ce9e-5717-8332-ee06095d29be | note | Verification Activity: By - ENG
| checkpoint | 5.2.1 - Compaction - Structural Fill Scala Penetrometer
edd45759-2e74-5acd-b50e-431368d9a029 | note | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
45a44b68-29f9-503a-a771-b808ad16301d | note | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
1fa0514e-4bcf-5990-906f-c570a3ce781b | note | Acceptance / Conformance Criteria - Minimum 5 blows per 100mm penetration
207fa720-d016-5723-914d-bf51f2305824 | note | Standard / Specification - PS 16.5.12
86d88f28-47d0-5253-b632-5fe62c626db2 | note | Verifying Document - Scala Report
17df2965-bb15-5c5f-8049-a05afca06b8c | note | Testing Quantity Required (based from schedule qtys) - Minimum 1 test per 500m3 of filling evenly distributed over the extent and depth of the filling. A minimum of 1 test per 500mm lift or part thereof to be completed through the full lift thickness.
9fd18c9d-d502-54fe-a461-d72145cac5f0 | note | Verification Activity: Activity - I
ee58569b-919d-528f-95c9-153058869d56 | note | Verification Activity: By - SE
| checkpoint | 5.2.2 - Compaction - Structural Fill NDM
1570d45b-f2fa-579c-8f93-5569dfe020e0 | note | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
c9d92d88-0f30-59c0-975e-aa650f10b9c8 | note | Acceptance / Conformance Criteria - Ave >95% of MDD
4b49159f-3182-5359-8e04-468f8a63c5fd | note | ○ Min >92% of MDD
6711d0c1-b6bf-51a6-84f8-9e16c7e0de54 | note | Standard / Specification - PS 16.5.12
8fd7be15-3b31-5588-a2a0-884f07354052 | note | Verifying Document - IANZ Accredited Report
b65d2562-3045-5642-93ab-0b085c0dcc8d | note | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
280b0c37-7468-5a2b-b5e2-7185bb139047 | note | Verification Activity: Activity - I
6f43f9c9-dde5-5587-a6fc-07d4f94286af | note | Verification Activity: By - SE
| checkpoint | 5.2.3 - Pumice Sand Fill
95825ea4-af2a-5167-9dfa-7c1f05612a32 | note | Detail - Pumice Sand Material shall be contained with an outer layer of fill with a minimum thickness of 600mm. Must be Hardfill and/or imported Type A1 material and/or Type A2 material and/or Type A3 material
178ca171-79b5-523e-ae5c-819584ecc076 | note | Acceptance / Conformance Criteria -
aecdf95b-b88f-56e3-8d57-b4f6f55b9221 | note | Standard / Specification - PS 16.5.12
2c1554b3-bf09-59ca-9acc-312feb5fde0a | note | Verifying Document - Site Records
be3c2045-920a-5084-9ba2-78fdaa13de71 | note | Testing Quantity Required (based from schedule qtys) -
0fb0d508-ee6b-56d9-a6fd-aced0354d4b0 | note | Verification Activity: Activity - E
fa4dc858-9acf-52e6-ba9c-6965443fb68a | note | Verification Activity: By - SE
| section | SECTION 6 – TOPSOIL PLACEMENT
| checkpoint | 6.1.2 - Topsoil Placement on cut and fill embankments
c57c4551-aaa4-5098-9046-dc7d23f1ca0e | note | Detail - Confirmation of thickness and material suitability
37271b8a-817a-51c3-bbb2-d5d76e057393 | note | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
4fb6212e-baa8-5eff-a2d5-03c6d4e2558d | note | Standard / Specification - PS 16.6.3 b)
2e01a5a2-2afe-5bc3-8a9f-4e1a52fe8fb9 | note | Verifying Document - Visual Observation
ca6b7040-f14a-5848-86e7-4d95f44a0433 | note | Testing Quantity Required (based from schedule qtys) - Once per lot after topsoil re-spread
e746025b-3f23-52a5-be29-352a14f73322 | note | Verification Activity: Activity - I
4e1b258e-ef24-5986-8e5b-6ba6f754acd1 | note | Verification Activity: By - SE
| section | SECTION 7 – SETTLEMENT INSTALLATION & MONITORING
| checkpoint | 7.1.1 - Instrument Reading Notice
2474dbde-e949-5825-9b4b-c6df21ad6318 | note | Detail - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
efdd939b-0b67-51ff-9c20-e9a31679142d | note | Acceptance / Conformance Criteria - 2 days notice to Eng
9f0d6b38-9cb1-5f20-8d1b-46eeacaa7afe | note | Standard / Specification - PS 16.8.2
ff47695f-9562-5a11-8a20-fb3b61c78347 | note | Verifying Document - Site Records
b85c747e-a11d-51f6-86b7-3c2b2be7644a | note | Testing Quantity Required (based from schedule qtys) - Every Time
496ce2b8-6b30-5794-949b-4a9acf650e0c | note | Verification Activity: Activity - I
3843524f-0169-5361-a158-82aaeea0e21b | note | Verification Activity: By - SE
| checkpoint | 7.1.2 - Results Submitted to Engineer
87101958-8d8c-5560-8a5d-50195fbfe269 | note | Detail - Results will be submitted to the Engineer within 1 day of reading the instruments
de408c69-44b4-5439-990d-77937c3b4016 | note | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
70d60a30-f100-527b-bb93-dcd75dcd5777 | note | Standard / Specification - PS 16.8.2
b26f9a57-afd9-5818-b622-62167996ee3c | note | Verifying Document - Site Records
e09ad6e8-76e8-5449-af36-eefcac171db1 | note | Testing Quantity Required (based from schedule qtys) - Every Time
68b23bc0-d786-5788-b57a-b5f08b6db791 | note | Verification Activity: Activity - I
508a2ea9-0a8f-5499-b90f-bbc59ed37728 | note | Verification Activity: By - SE
| checkpoint | 7.1.3 - Baseline Readings
1f8c5c6f-506f-5796-8d99-df90dfdf82f6 | note | Detail - The Contractor shall take 3 sets of baselines readings from all instruments at 2 day intervals
bfbb2fc1-1444-504d-be82-bb98f7a9da63 | note | Acceptance / Conformance Criteria - Engineers Approval
e51716a2-3967-5e3f-be3e-a39cd88dc21a | note | Standard / Specification - PS 16.8.2
daf0a108-e2ab-5cdc-9938-04cc9f45836b | note | Verifying Document - Site Records
97a084ad-0bf4-59d4-819a-332d362859be | note | Testing Quantity Required (based from schedule qtys) - Every 2 days
4e417044-eea9-5055-967f-aed806f96fcd | note | Verification Activity: Activity - I
6d60ec50-e044-544c-80c8-ee0f4d286d3d | note | Verification Activity: By - SE
| checkpoint | 7.1.4 - Readings During Active Fill Placement
9ca7a242-2120-5b8f-8bd5-7d5877ef15bc | note | Detail - During active fill placement, the Contractor shall read all monitoring plates twice a week or every 1 metre of fill whichever is more frequent
fffba1de-7baf-58a4-af8e-bf59287a0230 | note | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
2f36f692-12c8-5e42-93bf-4139aa18c46a | note | Standard / Specification - PS 16.8.2
f91f974a-1c52-5d89-91ce-5470db7cb45b | note | Verifying Document - Site Records
28d5748e-9940-52d1-941a-2f661d1c62e1 | note | Testing Quantity Required (based from schedule qtys) - Twice a week
47052b73-89c7-5c78-86c0-1379d14d2ba4 | note | Verification Activity: Activity - R
51ed8413-4c68-51a3-9bab-cfc5fe40d4cc | note | Verification Activity: By - SV
| checkpoint | 7.1.5 - Readings During No Active Earthworks in Area
59349510-5093-56e6-9b31-2b86a106b62f | note | Detail - The Contractor shall read all monitoring plates weekly if there is no active earthworks taking place in the area
bc09308d-ce64-52a7-846a-f2a958811848 | note | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
fed1769f-8b40-5709-af7a-bae82f58b2da | note | Standard / Specification - PS 16.8.2
02e0171c-d3e5-57fd-8252-bd127fc5d222 | note | Verifying Document - Site Records
9ae9bf1b-c3a4-5a0c-b25c-3bb2babd2ef2 | note | Testing Quantity Required (based from schedule qtys) - Weekly
adb58eec-eda8-53ef-bcb4-b4aa66a234da | note | Verification Activity: Activity - R
956129a4-7c2e-5fcd-a8f7-87a6084b44d0 | note | Verification Activity: By - SV
| checkpoint | 7.1.6 - Settlement Monitoring Termination
2d193302-9a34-530d-8aaf-5beb09eb81c4 | note | Detail - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
8b44e69d-5e8a-5994-8334-e7d50920584d | note | Acceptance / Conformance Criteria - Either:
37ab7b42-fa84-55c4-bbfb-9e386c5d74d1 | note | ○ 3 Consecutive Measurements showing T90 settlement value achieved
eb13ee56-5066-586f-b467-31a52257e7a0 | note | Or
7fea31c0-0e82-5dde-bebb-716edb6f045b | note | ○ Rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed
bcfce6d9-2866-5aec-adfb-f4c7d4a16d04 | note | Standard / Specification - PS 16.8.5
c631c054-1c68-5d5b-8245-bdaa614f1faa | note | Verifying Document - Site Records
0e40e002-c925-5025-9088-46850461feb3 | note | Testing Quantity Required (based from schedule qtys) - Engineers Approval
aca8ac54-a5c4-515f-a6ec-f41272263068 | note | Verification Activity: Activity - HP
1b5af12b-4a67-534a-bc67-e30d54e4106f | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 8 – AS-BUILTS
| checkpoint | 8.1.1 - As-Builts
9138d2a5-833b-5d74-bc27-4fb87fa471e1 | note | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
1e74c7bd-cbb9-57f6-a3fc-41e86ab88902 | note | Acceptance / Conformance Criteria -
32e603b1-d51a-555a-9b5b-3ae1fba7f11a | note | Standard / Specification - PS 16.7.6
81db03e5-3ca8-5ed3-8ded-74b94252a0e8 | note | Verifying Document - Survey Records
59a2d2b4-d219-5b31-8aca-a96c70384634 | note | Testing Quantity Required (based from schedule qtys) - During Earthworks
66cda388-c788-521b-9da5-06a0dac81c62 | note | Verification Activity: Activity - D
bf5d7d6e-ff88-5976-aefe-afe83d1a306c | note | Verification Activity: By - SV