## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-003 ITP Earthworks Rev IFC2 | itp |  |  |  |  | DN1210-003 ITP Earthworks Rev IFC2 | 87e4688e-99ab-4155-9a39-0c7255ae4bd5
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS
checkpoint | 1.1.1 - Earthworks Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Ecology Sign Off
label | Detail - Confirmation from Ecology that earthworks can proceed
label | Acceptance / Conformance Criteria - Email
label | Standard / Specification - Internal Hold Point
label | Verifying Document - Email from Ecology NZ
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - QM
checkpoint | 1.1.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that Erosion and Sedimentation Controls are in place prior to earthworks proceeding
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to Earthworks
label | Verification Activity: Activity - H
label | Verification Activity: By - QM
checkpoint | 1.2.1 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Los Angeles Abrasion Test
label | Detail - NZS4407:2015, Test 3.12 - The Abrasion Resistance of Aggregate by use of the Los Angeles Machine
label | Acceptance / Conformance Criteria - 0.5
label | Standard / Specification - PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Required, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm, Maximum fines 10% passing 75micron sieve
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Solid Density
label | Detail - NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required?
label | Stockpile size:
label | ○ 0 to 400m3 – 2 tests
label | ○ 400 to 1500m3 – 3 tests
label | ○ 1500 to 4000m3 – 4 tests
label | ○ >4000m3 – 1 test for each
label | ○ additional 1,000m3
label | – Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.2 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 53mm, Max 10% passing 13.2mm sieve
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3, Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.1 - Geotextile
label | Detail - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Data Sheets
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.1 - Laboratory Testing for Soil Suitability
label | Detail - Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse
label | ○ Soil Reaction
label | ○ Electrical Conductivity
label | ○ Mechanical Analysis (texture)
label | ○ Stone Content
label | ○ Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium
label | ○ Organic Matter Content
label | ○ Check for Toxic or Hazardous substances
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NZTA P39:2013 3.1
label | Verifying Document - Hill Laboratories Test Report
label | Testing Quantity Required (based from schedule qtys) - 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.7.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - PS 16.5.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7.2 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 130mm, Max 5% passing 19mm sieve
label | – – – – – – – – – – – –
label | Grading:
label | Sieve Size ¦¦ % Passing
label | – – – – – – – – – – – –
label | 130mm ¦¦ 100
label | 100mm ¦¦ 70-80
label | 63mm ¦¦ 0-50
label | 37.5mm ¦¦ 20-25
label | 19mm ¦¦ 0-5
label | – – – – – – – – – – – –
label | Standard / Specification - PS16.5.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source, Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – SITE WON LANDSCAPING FILL
checkpoint | 2.1.1 - On Site track-able Testing
label | Detail - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
label | Acceptance / Conformance Criteria - Trackable by Contractors Plant
label | Standard / Specification - PS 16.5.5
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - R
label | Verification Activity: By - ENG
checkpoint | 2.1.2 - Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it meets minimum shear vane strength of 80kPa
label | Acceptance / Conformance Criteria - Min >80kPa
label | Standard / Specification - PS 16.5.5
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - R
label | Verification Activity: By - ENG
checkpoint | 2.2.1 - Placement of Site Won Landscaping Fill
label | Detail - To be visually free of deletorious material, litter etc, and track rolled for compaction, with no slumping once placed
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - PS 16.5.6
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | SECTION 3 – CUT SUBGRADE TESTING
checkpoint | 3.1.1 - Proof Roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Displacement <15mm
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Cut Subgrade Inspection
label | Detail - Engineer to inspect all foundation surface inspections
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.2 - Cut Subgrade Testing - Cohesive Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - Written Certification
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CUT SLOPE INSPECTIONS
checkpoint | 4.1.1 - Cut Side Slope Inspection
label | Detail - Inspection records to include photographs, logged soils (to NZ Geotechnical Guidelines) and shear vane testing
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - As per Engineer
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 4.1.2 - Cut Slope - Soil Log
label | Detail - Soils to be logged to NZ Geotechnical Guidelines
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Soil Log
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Cut Slope - Shear Vane Test
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Drainage Measures if Seepage Encountered
label | Detail - Borehole Drains or ballasting may be required, to be directed by Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Engineer approval
label | Testing Quantity Required (based from schedule qtys) - As per Engineer
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 4.1.5 - Design and Grade Check
label | Detail - Confirm cut slopes have been correctly excavated to design and grade
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.1
label | Verifying Document - Survey Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 4.1.6 - Stabilisation of Cut Slope Surface
label | Detail - Cut slope surfaces to be topsoiled and grass seeded or planted as soon as possible
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.6.4
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - Written Certification
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – UNDERCUT TO WASTE & BACKFILL
checkpoint | 5.1.1 - Undercut Surface Inspection
label | Detail - Engineer to inspect undercut surface
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Across stripped area
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 5.1.2 - Placement of Geotextile on Undercut
label | Detail - Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4, TNZ F/7: 2003 8.3
label | Verifying Document -
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 5.1.3 - Subsoil Drain inspection
label | Detail - Subsoils to be placed at base of cuts where directed by the Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.4
label | Verifying Document -
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 5.2.1 - Release of Hold Point
label | Detail - To release the subgrade hold point and be able to start placing fill, the Contractor shall provide written certification that all insepcted and tested subgrade comlies with the requirements in PS 16.6
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.9.3
label | Verifying Document - Written Certification
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – COMPACTION OF IMPORTED FILL
checkpoint | 6.1.1 - Placement of Geotextile
label | Detail - A layer of Class B Geotextile Fabric to be placed between cut surface and imported A1 Structural Fill with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - NTC084
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2.1 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill: Min CIV 18, Ave CIV 20
label | ○ Non-Structural Fill: Min CIV 10, Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2.2 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD, Min >92% of MDD
label | ○ Non Granular Material: Max Air Voids 8%
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2.3 - Compaction Trials
label | Detail - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (ie construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.6.5
label | Verifying Document - Trial Results
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - R
label | Verification Activity: By - ENG
checkpoint | 6.3.1 - Compaction - Structural Fill Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 5 blows per 100mm penetration
label | Standard / Specification - PS 16.5.12
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - Minimum 1 test per 500m3 of filling evenly distributed over the extent and depth of the filling.
label | ○ A minimum of 1 test per 500mm lift or part thereof to be completed through the full lift thickness.
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.2 - Compaction - Structural Fill NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD, Min >92% of MDD
label | Standard / Specification - PS 16.5.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.3.3 - Pumice Sand Fill
label | Detail - Pumice Sand Material shall be contained with an outer layer of fill with a minimum thickness of 600mm. Must be Hardfill and/or imported Type A1 material and/or Type A2 material and/or Type A3 material
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.5.12
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) -
label | Verification Activity: Activity - E
label | Verification Activity: By - SE
section | SECTION 7 – TOPSOIL PLACEMENT
checkpoint | 7.1.2 - Topsoil Placement on cut and fill embankments
label | Detail - Confirmation of thickness and material suitability
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - PS 16.6.3 b)
label | Verifying Document - Visual Observation
label | Testing Quantity Required (based from schedule qtys) - Once per lot after topsoil re-spread
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 8 – SETTLEMENT INSTALLATION & MONITORING
checkpoint | 8.1.1 - Instrument Reading Notice
label | Detail - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
label | Acceptance / Conformance Criteria - 2 days notice to Eng
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every Time
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.1.2 - Results Submitted to Engineer
label | Detail - Results will be submitted to the Engineer within 1 day of reading the instruments
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every Time
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.1.3 - Baseline Readings
label | Detail - The Contractor shall take 3 sets of baselines readings from all instruments at 2 day intervals
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Every 2 days
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 8.1.4 - Readings During Active Fill Placement
label | Detail - During active fill placement, the Contractor shall read all monitoring plates twice a week or every 1 metre of fill whichever is more frequent
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Twice a week
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 8.1.5 - Readings During No Active Earthworks in Area
label | Detail - The Contractor shall read all monitoring plates weekly if there is no active earthworks taking place in the area
label | Acceptance / Conformance Criteria - To Engineer within 1 day of Reading
label | Standard / Specification - PS 16.8.2
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Weekly
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 8.1.6 - Settlement Monitoring Termination
label | Detail - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
label | Acceptance / Conformance Criteria - Either:
label | ○ 3 Consecutive Measurements showing T90 settlement value achieved
label | Or
label | ○ Rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed
label | Standard / Specification - PS 16.8.5
label | Verifying Document - Site Records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 9 – AS-BUILTS
checkpoint | 9.1.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV