## Stabilisation ITP
| PAVEMENT RENEWALS INSPECTION AND TEST PLAN – Chemical Stabilisation | [6 empty] | Doc No: Pavement Renewals
| Site Name: Hiruharama Settlement | [6 empty] | Rev: 1 Pages: 5
| Location – 035-0200-6270-6670 | [6 empty] | Prepared: | Nikhil Mishra | Date: | 2023-11-02
[8 empty] | Approved: |  | Date:
ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | Responsible Person | RECORDS / REMARKS
[6 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print name) | incl NCR ref
[6 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
Preliminary & General
Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classification risk profile (documented in the contract specific MMP) or the contract completion date. | V |  |  |  | Ted Philips/Mark Joblin
Approved RQP |  | Confirmation | Contract Specification | Before work commences | Principal Acceptance according to guidelines in appendix 6.3 TRWNOC | H | Mark Joblin | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. |  | Nikhil Mishra
Design Acceptance |  | Confirmation | Contract Specification | Before work commences | Principal Acceptance according to guidelines in appendix 6.3 TRWNOC | H | Mark Joblin | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. |  | Nikhil Mishra
Daily Production Plan |  | Confirmation | TNZ B5 | Daily | Principal Acceptance according to guidelines in appendix 6.3 TRWNOC | V |  |  |  | NOC Contract Manager
Set-out / Site preparation
Setout |  |  | Best Practice | Per installation | According to existing road profile and alignment | V | Nikhil Mishra |  |  | Richard Taare
Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H | Nikhil Mishra | Hold point - No excavation is to be commenced until services are located and accounted for |  | Richard Taare
Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H | Nikhil Mishra | Where risk of cultural discovery |  | Richard Taare
Notification of intention to start work |  | Notification |  | Before work commences | Letter drop to local residents | H | Nikhil Mishra | Hold point - No physical work is to be commenced on site until notification has been sent no later than 48 hours of establishing on site. |  | Richard Taare
Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H | Nikhil Mishra | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Richard Taare
Traffic Management | TMP | Visual check | CoPTTM | Before traffic management set up | TMP checked and approved - Plans approved | H | Nikhil Mishra | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | Richard Taare
| Setup | Visual check | Traffic Management Plan | Before work commences | Traffic management complies with TMP | H | Nikhil Mishra | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | Richard Taare
Sediment Control |  | Physical | ESMP DN-ZH-GU074.1 | Before Excavation Commences | Sediment and erosion control measures aligning with DN-ZH-GU074.1 and ESMP | H | Nikhil Mishra | Hold point - No physical works are to be commenced until sediment control measure is in place |  | Richard Taare
Dust Control |  | Physical | ESMP | During Execution | Complies with ESMP | H | Nikhil Mishra | Hold point - No physical works are to be commenced until dust control practices are implemented |  | Richard Taare
Noise Control |  | Physical | ESMP | During Execution | Complies with ESMP | H | Nikhil Mishra | Hold point - No physical works are to be commenced until noise control practices are implemented |  | Richard Taare
Preliminary Works
Shoulder Stripping |  | Visual check | On site |  | Shoulder stripping completed | W | Nikhil Mishra |  |  | Akhil Mohan
Compaction Equipment | Compaction | Inspection | RQP 17.1.2 | Prior to commencement | Compaction equipment is sufficient to achieve compaction | V | Nikhil Mishra | Required by appendix 6.3 |  | Akhil Mohan
Digout Repairs
Material |  | Lab Test | NZTA M/4 - Grading, broken faces, fines properties | Most frequent - Every 500m³ or 2 months | Confirming Lab report AP50 | H | Nikhil Mishra | Lab Report |  | Akhil Mohan/Richard Taare
Depth | = | Visual | According QMP | every 10 m | Depth within +25 mm -5 mm | H | Nikhil Mishra | QC Form |  | Akhil Mohan/Richard Taare
Subgrade Testing |  | Site Test | Scala (DCP) | every 10 m | > 3 blows /100 mm | H | Nikhil Mishra | QC Form |  | Akhil Mohan/Richard Taare
Geofabric |  | Visual | Site Inspection | Per Digout | Cirtex Duraforce AS410 Laid at 550 mm depth from surface | H | Nikhil Mishra | CBP |  | Akhil Mohan/Richard Taare
Geotextile |  | Visual | Site Inspection | Per Digout | Cirtex Tenax 3D-T laid at 300 mm depth from surface | H | Nikhil Mishra | CBP |  | Akhil Mohan/Richard Taare
Water Content |  | Visual | Squeeze test | Each Site | Material clumps together | I | Nikhil Mishra | QC Form |  | Akhil Mohan/Richard Taare
Compaction | = | Visual | Measurement | every 10 m | Compact in layers not exceeding 150 mm (compacted height) | I | Nikhil Mishra | QC Form |  | Akhil Mohan/Richard Taare
Density (as required) | = | Site Test | Nuclear Densometer - Maximum Dry Density | Each Programme | Subbase: Average ≥ 95% MDD Minimum ≥ 92% MDD | H | Nikhil Mishra | QC Form |  | Akhil Mohan
Surface |  | Visual | Straight Edge | Each Site | Repair edge - Max 50mm in 1m Depressions - Max 6mm in 2m straight edge Swept, tight surface - no dust | I | Nikhil Mishra | QC Form | = | Akhil Mohan
Pavement
Shape | Surface shape/profile | Inspection | Sting line/ Straight edge | 1 per 20 m | ≤10mm variance from 3m straight edge. +- 20 mm from string line | V |  |  |  | Renwals Manager / NZTA Representative
Construction QA
Water |  | Visual Inspection | TNZ B/5 | ongoing | Water for stabilisation, construction and curing is free from impurities, 10 m3 allowed per day from natural source if resource consent obtained | W | Nikhil Mishra | Water quality should be continually observed as clean, when impurities are observed a new source may be required |  | Akhil Mohan/Richard Taare
Weather Limitations | Temperature | Measure Temperature | TNZ B/5 | Daily | Minimum ambient air temp. Use weather report as evidence Cement 5°C Lime 10°C | W | Nikhil Mishra | Work shall not be started if temperature is below the respective minimums. |  | Akhil Mohan/Richard Taare
| Wind | Assessment | TNZ B/5 | Daily | Maximum wind speed of 25km/hr. Use weather report as evidence | W | Nikhil Mishra | Work shall not be started if wind speed exceeds the maximum |  | Akhil Mohan/Richard Taare
Imported Basecourse Materials Testing |  | Comply with project specification | Refer project specification | Refer project specification | Refer project specification in pavement report | V | Nikhil Mishra | Hold Point – All production and source testing results to be provided prior to placement of material on road for a source |  | Richard Taare
[6 empty] | H | Nikhil Mishra |  |  | Richard Taare
[7 empty] | Nikhil Mishra |  |  | Richard Taare
[7 empty] | Nikhil Mishra |  |  | Richard Taare
Imported Basecourse Materials Testing | Particle Size Distribution | Sieving Test | TNZ M/4: 2006 NZS 4407 :1991 Test 3.8.1 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Particle size distribution fits within the AP50 envelope upper and lower limits | V | Nikhil Mishra |  |  | Richard Taare
[6 empty] | v | Nikhil Mishra |  |  | Richard Taare
[7 empty] | Nikhil Mishra |  |  | Richard Taare
| California Bearing Ratio | CBR Test | NZS 4407:1991 Test 3.15 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | The soaked CBR of the basecourse aggregate shall not be less than 80% | V | Nikhil Mishra | = |  | Richard Taare
|  |  | TNZ M/4:2006 |  |  | v | Nikhil Mishra |  |  | Richard Taare
[7 empty] | Nikhil Mishra |  |  | Richard Taare
[7 empty] | Nikhil Mishra |  |  | Richard Taare
| MDD | Test |  | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | According to Design | V | Nikhil Mishra | = |  | Richard Taare
Stabilisation agents | Cement | See NZS 3122 | NZS 3122 | per batch produced by supplier | Cement must comply with NZS 3122 | V | Nikhil Mishra | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier |  | Richard Taare
[6 empty] | H | Nikhil Mishra |  |  | Richard Taare
| Delivery | Visual Inspection | TNZ B/5 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W | Nikhil Mishra | Certificate of loading to be checked on site |  | Richard Taare
Water |  | Visual Inspection | TNZ B/5 | ongoing | Water for stabilisation, construction and curing is free from impurities, 10 m3 allowed per day from natural source if resource consent obtained | W | Nikhil Mishra | Water quality should be continually observed as clean, when impurities are observed a new source may be required |  | Richard Taare
Weather Limitations | Temperature | Measure Temperature | TNZ B/5 | Daily | Minimum ambient air temp. Use weather report as evidence Cement 5°C Lime 10°C | W | Nikhil Mishra | Work shall not be started if temperature is below the respective minimums. |  | Richard Taare
| Wind | Assessment | TNZ B/5 | Daily | Maximum wind speed of 25km/hr. Use weather report as evidence | W | Nikhil Mishra | Work shall not be started if wind speed exceeds the maximum |  | Richard Taare
| Rain | Check forecast | TNZ B/5 | Daily | Zero likelihood of rain. Use weather report as evidence | W | Nikhil Mishra | Spreading shall not commence if rain is forecast |  | Richard Taare
Spreading | Cement/lime | Mat Test 1m² canvas | TNZ B/5 | Every 400m² | Within ±0.5 kg/m² of the specified rate | V | Nikhil Mishra | Tonnage/m² records shall be kept, including mat results |  | Richard Taare
|  | Average usage test | TNZ B/5 | Upon emptying the spreader and bulk tanker | Within ±2.5% of the specified rate | V | Construction Engineer: Jack/Waven Hapi |  |  | Richard Taare
Time Limitations | Cement/lime | The maximum time period from mixing to primary compaction | TNZ B/5 | post stabilisation | 2 Hours | H | Nikhil Mishra | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Richard Taare
In-Situ Mixing | Cut Depth | Depth measurement |  | at both ends of cut and every 100m | +- 20 mm of design depth | W | Nikhil Mishra |  |  | Richard Taare
| Depth of STAB | Depth measurement |  | Random locations | Meet desgn depths | V | Nikhil Mishra |  | ` | Akhil Mohan/Richard Taare
| Join Overlap | Inspection | TNZ B/5 | Continuous | 100mm overlap | W | Nikhil Mishra | All cuts shall overlap by the minimum acceptance criteria |  | Richard Taare
| Particle breakdown | Visual Inspection | TNZ B/5 | within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W | Nikhil Mishra | Where breakdown is excessive, method of milling should be altered to avoid such breakdown |  | Richard Taare
[6 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print name) | incl NCR ref
[6 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
| Client Acceptance | Inspection |  | Per Site | Client to be present during stabilisation, photographic evidence shall be provided if the client is unable to attend | H | Mark Joblin / Nikhil Mishra | Hold Point - Client shall be notified prior to stabilisation so they have the opportunity to be present upon commencement of stabilisation |  | Mark Joblin / Nikhil Mishra/ Akhil Mohan
Construction QA
Construction STAB OLAY | Compaction | NDM – maximum dry density | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Base: Average ≥ 98% MDD Minimum ≥ 95% MDD | V | Mark Joblin / Nikhil Mishra | Hold Point – no surfacing layer is to be applied until passing results are achieved (i.e. average & minimum MDD) |  | Mark Joblin / Nikhil Mishra/ Richard Taare
[5 empty] | Subbase: Average ≥ 95% MDD Minimum ≥ 92% MDD | H
| Degree of Saturation (DOS) | DOS | NZS 4407: 1991 Test 4.2.2. TNZ B/2: 2005 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | DOS ≤ 80% from Solid Density and %W | V | Jack Lewis/Ian Symons/ Akhil Mohan | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Richard Taare
[6 empty] | H | Nikhil Mishraa |  |  | Richard Taare
| Particle Size Distribution | PSD | NZS 4407:2015 Test 3.8.1 | 1 tests per homogeneous lot of up to 1000m2 of laid pavement | comparison to the upper and lower limits of M/4 Specification | H | Jack Lewis/Ian Symons/Akhil Mohan |  |  | Richard Taare
| Unconfined Compressive Strength (UCS) | UCS | NZS 4407:2015 Test 2.4.8.2a | 1 tests per homogeneous lot of up to 1000m2 of laid pavement | Test to confirm compressive strength obatined relative to pavement design | V | Nikhil Mishra | UCS 1 - 2 lightly bound pavement > 2 bound pavements |  | Richard Taare
| Surface shape/profile Layer thickness | TNZ B/2 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge. | V | Mark Joblin / Nikhil Mishra |  |  | Mark Joblin / Nikhil Mishra/ Richard Taare
Gradual deviations
No ponding if crossfall < 1%
v
-5mm +15mm or ±5mm at lip of concrete channel
| Tolerances: width unconstrained | TNZ B/2 | Confirm offset from lift pegs | 1 at every lift peg or per 180 m2 | - 20mm + 100mm | V | Nikhil Mishra |  |  | Akhil Mohan
[6 empty] | v | Nikhil Mishra
| Tolerances: width constrained | TNZ B/2 | Stringline/lift pegs | 1 at every lift peg or per 180 m2 | Zero | V | Nikhil Mishra |  |  | Akhil Mohan
[6 empty] | v | Nikhil Mishra |  |  | Akhil Mohan
| Visual appearance | TNZ B/2 | Visual inspection after sweeping | Immediately prior to sealing | No loose material remaining, Photo as evidence | h | Nikhil Mishra | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Akhil Mohan
[6 empty] | h | Nikhil Mishra |  |  | Akhil Mohan
Pavement finished surface
Pavement finished surface | Ride quality | Owner acceptance test | NZTA TM 7003-v1, 6.1.2 of Contract Documents Maintenance Specification | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality |  | Renewals Manager
H
| Mosaic surface / Compacted shoulders | Visual inspection / Downer Survey | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping, Client must sign QA sheet provided, if client is unable to attend photographic evidence must be provided. | W | Mark Joblin / Nikhil Mishra | Hold Point – no surfacing layer is to be applied until passing results are achieved and client has been notified |  | Mark Joblin / Nikhil Mishra/ Richard Taare
H
Shoulders
Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent | V | Nikhil Mishra | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Akhil Mohan
[6 empty] | H | Nikhil Mishra
Compaction |  | Visual check | Drive over 4T, check wheel tracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V | Nikhil Mishra | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Akhil Mohan
[5 empty] | Driver operated rollers must not come within 1 m of the sloped shoulder > 1:5 slope |  | Nikhil Mishra
Site Reinstatement / Clearance
Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual inspection | All signs/markers | Replaced in same position, height etc. | V | Nikhil Mishra | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Akhil Mohan
[6 empty] | H | Jack Lewis/Ian Symons/Waven Hapi
Nikhil Mishra
Nikhil Mishra
Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W | Nikhil Mishra | Hold Point – TMP cannot be removed until site Audited |  | Richard Taare
Site left clean & tidy |  | Visual check |  | After vacating site | · Stockpiles removed, EMP installed | H | Mark Joblin / Nikhil Mishra |  |  | Mark Joblin / Nikhil Mishra/ Richard Taare
· Plant removed, clear litter
As Built Records
Collect asset data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected. | V | Nikhil Mishra |  |  | Nikhil Mishra
Enter asset data into RAMM and/or register(s) |  | SHDOM (SM050) | RAMM | At completion of work. | All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Paul Grant
Quality Assurance Close Out by: | _______________________________________________ |  | Date: _____________
(signature)
________________________________________________
(name)
This record to contract file.

## Sealing ITP
| PAVEMENT RENEWALS INSPECTION AND TEST PLAN – SEALING | [6 empty] | Doc No: Pavement Renewals
| Site Name: | [6 empty] | Rev: 1 Pages: 2
| Location – | [6 empty] | Prepared: | Nikhil Mishra | Date: | 2023-10-18
[8 empty] | Approved: |  | Date:
ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | Responsible Person | RECORDS / REMARKS
[6 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print name) | incl NCR ref
[6 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
Seal Design
Surfacing design |  | Request for surfacing | Appendix 15 of contract specific MMP | Each surfacing establishment | Quantity, location, bitumen grade, diluents', target application rate, chip grade, asphalt type, asphalt depth. | H |  | Hold point - No work is to commence until designs have been provided |  | Nikhil Mishra
Preparation for surfacing |  | Visual check | Inspection/ Downer Survey | Each surfacing establishment | Shape, ride, surface, saturation, (Client, Foreman and Site Engineer must sign QA form provided) | H | Mark Joblin / Nikhil Mishra | Hold point - No work is to commence until inspection of pavement base layer has been inspected and logged via Downer Survey |  | Mark Joblin / Nikhil Mishra
Chip Sealing
Bitumen components |  | Lab test | Volume metering or weighing device, CoP RNZ 9803:2013 | Each surfacing establishment | Bitumen blending certificate | V
Plant |  | Visual | Documentation | Each Site | Each vehicle to produce - Warrant of Fitness, Driver eligibility and calibration of machinery | H | Nikhil Mishra | Hold point - No sealing is to commence until weather has been confirmed safe to seal |  | Akhil Mohan /Nikhil Mishra
Weather |  | Visual | SIS | Each Site | Check SIS prior to sealing | H | Nikhil Mishra | Hold point - No sealing is to commence until weather has been confirmed safe to seal |  | Akhil Mohan /Nikhil Mishra
Spray Bar Check |  | Overlap Test | RQP 17.3 | Each Site | Ensure no overlap or gaps between bitumen from sprayers | H | Nikhil Mishra | Hold point - No sealing is to commence until weather has been confirmed safe to seal |  | Akhil Mohan /Nikhil Mishra
|  | Bucket Test | RQP 17.3 | Each Site | Ensure all buckets under each sprayer contain the same amount of bitumen | H | Nikhil Mishra | Hold point - No sealing is to commence until weather has been confirmed safe to seal |  | Akhil Mohan /Nikhil Mishra
Application rate of binder |  | Insitu | NZTA P/17 or "Chipsealing in New Zealand NZTA (NZTA 2005)" | As required by the design | Application rate within tolerance of the seal design spray rate. Longitudinal overlap of spray runs as per design. | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
Aggregate | Quality | Lab Test | NZTA M/6 | 1 / 500m³ | Shape, size, cleanliness | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
| Skid Resistance | Lab Test | NZTA M/6 NZTA T10 | 1 / 1000m³ | Refer to NZTA T10 requirements | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
| Crushing Resistance | Lab Test | NZTA M/6 NZS 4407 Test 3.10 | 1 / 1000m³ | 10% fines under 230 kN load | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
| Weathering Resistance | Lab Test | NZTA M/6 NZS 4407 Test 3.11 | 1 / 1000m³ | Shall have a quality index of AA or BA | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
Rolling |  | Visual | NZTA P/3 | Each Site | Ensure chip has good contact with binder in all areas not just in wheel path | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
|  | Plant | RQP | Each Site | Pneumatic Tyre Roller (PTR) is to be used to roll sealed surface | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
|  | Time | NZTA P/3 Section 22 | Each Site | Calculate required rolling time as per equation in section 22 | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
Post construction seal protection / Seal life |  | Physical | "Chipsealing in New Zealand NZTA (NZTA 2005)" | Each site | Extended rolling time and/or provide positive traffic management to assist compaction, chip embedment and to avoid early stripping | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
Disestablishment
Removal of surplus chip |  | Visual |  | Within 48 hours of rolling the site | Not more than 20 loose chip within any 2m2 | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
[7 empty] | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
Pavement marking |  | Request for roadmarking |  | Within 48 hours of rolling the site | Request made when item programmed | V | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
|  | Visual |  | Within 48 hours of rolling the site | Markings follow tabs or new markings installed according to MOTSAM | W | Nikhil Mishra |  |  | Akhil Mohan /Nikhil Mishra
TMP |  | Visual | CoPTTM | Within 48 hours of rolling the site | Traffic control in place to protect new surface and removed following sweeping and pavement marking | H | Nikhil Mishra | Hold point - No TM is to be removed until linemarking has been completed |  | Akhil Mohan /Nikhil Mishra
Quality Assurance
Site Recording |  | Visual |  | Each Site | Video evidence of site (seal finish) once it has been swept | H | Nikhil Mishra | Hold point - Failures within seal surface must be rectified before site can be confirmed complete |  | Akhil Mohan /Nikhil Mishra
Post seal Inspection |  | Inspection | Downer Survey | Each Site | NZTA representative is satisfied with finished pavement surface, photograhic evidence shall be supplied if client is unable to attend. Inspection to be logged via Downer Survey | H | Mark Joblin / Nikhil Mishra | Hold point - Client must have opportunity to be present on site to complete inspection of finished surface. |  | Mark Joblin / Nikhil Mishra
Final Measurement check |  | Physical | Check and measure site and confirm on as-built | Each site | Once site has been completed and checked as as-built will be uploaded into RAMM Contractor | W | Nikhil Mishra |  |  | Akhil Mohan
Quality Assurance Close Out by: | _______________________________________________ |  | Date: _____________
This record to contract file. |  | (signature) | ________________________________________________

## Drainage ITP
| PAVEMENT RENEWALS INSPECTION AND TEST PLAN – Drainage | [6 empty] | Doc No: Pavement Renewals
| Site Name: | [6 empty] | Rev: 1 Pages: 1
| Location – | [6 empty] | Prepared: | Nikhil Mishra | Date: | 2023-10-18
[8 empty] | Approved: |  | Date:
ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQ. | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | Responsible Person | RECORDS / REMARKS
[6 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | (print name) | incl NCR ref
[6 empty] | Type | Assessor | Description |  |  | Sign & date if appropriate
Preliminary
Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H | Richard Taare | Hold point - No excavation is to be commenced until services are located and accounted for |  | Pat Thompson
Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H | Richard Taare | Where risk of cultural discovery |  | Pat Thompson
Notification of intention to start work |  | Notification |  | Before work commences | Notification to stakeholders minimum 48 hrs before commencement, minimum 2 weeks notice for sensitive site (SWAMP) | H | Richard Taare | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. |  | Pat Thompson
Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H | Richard Taare | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Pat Thompson
Traffic Management | TMP | Visual check | CoPTTM | Before traffic management set up | TMP checked and approved - Plans approved - Current CAR | H | Richard Taare | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | Pat Thompson
| Setup | Visual check | Traffic Management Plan | Before work commences | Traffic management complies with TMP | H | Richard Taare | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | Pat Thompson
Pipe Type |  | Material selection | TNZ F/2 Section 2.1 | Each Subsoil drain | 110 mm Perforated novaflow or similar | H | Richard Taare | Hold point - No physical works are to be commenced until subsoil pipe material has been selected |  | Pat Thompson
Filter Material |  | Grading Test | NZS 4402: Part 2:1986 | Per stockpile/ Job | Filter material shall be clean, durable stone having a crushing resistance of not less than 100 kN when tested and comply with Grading limits | V | Richard Taare |  |  | Pat Thompson
Geotextile |  | Verification | NZTAF7 | Per installation | Strength class B and filtration class 1 | V | Richard Taare |  |  | Pat Thompson
Sediment Control |  | Physical | ESMP | Before Excavation Commences | Place silt fence, earth bund or other sediment contol device around area to protect nearby waterways | H | Richard Taare | Hold point - No physical works are to be commenced until sediment control measure is in palce |  | Pat Thompson
Construction
Excavation for culvert realignment Culvert No26 & No 27 |  | Slope Checks | TNZ F/2 Section 3 | Every 20 m of subsoil bedding layer | Levels to show that a minimum of 1:100 (1%) fall is being achieved using Rotating laser level, theodolite or other surveying device | V | Richard Taare |  |  | Pat Thompson
|  | Depth Checks | TNZ F/2 Section 3 NZS 2566:1998 | Every 20 m of excavated area | Minimum cover for flexible pipes - 750 mm unsealed roads, 600 mm sealed roads, 450 mm outside road carriageway | V | Richard Taare |  |  | Pat Thompson
|  |  |  | Every 20 m of excavated area | Invert shall not be less than 800 mm below finished road level | V | Richard Taare |  |  | Pat Thompson
|  |  | TNZ F/2 Section 3 | Every 20 m of excavated area | Trench shall have vertical sides at a minimum of 300 mm above the top of pipe | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Upon completion of excavation | Photograph excavation upon completion of thereof (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Bedding |  | Quantity Check |  | Every 20 m of Subsoil drain | Shall have a minimum of 50 mm filter material underneath the pipe | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Upon completion of bedding | Photograph bedding upon completion of thereof (evidence) | V | Richard Taare |  |  | Pat Thompson
filter Material |  | Quantity Check | TNZ F/2 Section 6 | Every 20 m of Subsoil drain | Filter material shall be placed to a minimum depth of 150 mm above the top of pipe, filter material shal be compacted in layers not exceeding 150 mm (see design) | V | Richard Taare |  |  | Pat Thompson
Backfill |  | Density | ASTM D5874-95 | 1 sample per 2m² lot or at least 5 samples | Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer | V | Richard Taare |  |  | Pat Thompson
|  | Level Control | None | None | Tie-in flush with adjacent road surface +20mm mound in middle of road crossing | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Upon completion of basecoarse | Photograph basecourse upon completion of thereof (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Existing Level Control for culvert realignment Culvert No26 & No 27 |  | Level Control | Physical survey check | Before work commences | Survey and stake out lift pegs for existing inlet and outlet positions and elevations | H | Richard Taare | Hold point - No physical works are to be commenced until existing pipe inlet and outlet position and elevation is recorded |  | Pat Thompson
Work Space Restrictions |  | Fencing | As per existing | Where required | Open adequate section in existing fencing to allow for required work space where required, documented and signed permission must be received prior | H | Richard Taare | Hold Point - Documented and signed permission received prior |  | Pat Thompson
Pre-construction Photo Diary |  | Site Diary Photos | Take Photos | Before work commences | Photographs the full extent of the work area / site | H | Richard Taare | Hold point - No work is to be commenced until site photos are taken |  | Pat Thompson
Qarry Aggregate - AP65 |  | Aggregate Grading | NZS 4407 Test 3.8.1 | 1 per 400m³ | Grading in accordance with WSP Lab Gisborne Standard grading curve | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
|  | Crushing Resistance | NZS 4407 test 3.10 | 1 per 10,000m3 or per visual change | >130 kN | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
|  | Linear Shrinkage | NZS 4402 | 1 per 400m³ | Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
Qarry Aggregate - AP40 |  | Aggregate Grading | NZS 4407 Test 3.8.1 | 1 per 400m³ | Max particle size ≤37.5mm. Not more than 57% by mass shall pass the 9.5mm sieve. Not more than 19% by mass shall pass the 0.6mm sieve | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
|  | Crushing Resistance | NZS 4407 test 3.10 | 1 per 10,000m3 or per visual change | under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced. | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
|  | Linear Shrinkage | NZS 4402 | 1 per 400m³ | Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
|  | Cement Reactivity | NZS 4407 Test 3.15 | 3 per source, Sampling shall be carried out in accordance with NZS 4407:1991 Part 2 | Set of 3 with all UCS >3 MPa | H | Richard Taare | Hold point - No physical works are to be commenced until proof of compliance is in place |  | Pat Thompson
Excavation |  | Quantity Checks |  | Per site | Earth works must not exceed 10 m3 | H | Richard Taare | Hold point - Earth works must not exceed 10 m3 |  | Pat Thompson
|  | Slope Checks | TNZ F3 Section 3.2 | Every 5 m of subsoil bedding layer | Levels to show that a minimum of 1:80 (1.25%) fall is being achieved using Rotating laser level, theodolite or other device | V | Richard Taare |  |  | Pat Thompson
|  | Depth Checks | TNZ F3 Section 3.2 | Every 5 m of excavated area | Depth between top of pipe and finished surface above the minimum requirement specified in AS/NZS 3725 and AS/NZS 2566 | V | Richard Taare | See charts on minimum cover AS/NZS 3725:2007 and AS/NZS 2566 |  | Pat Thompson | Record Estimated Cover values: - Left edge of Road = ________________mm - Middle of Road = ________________mm - Right edge of Road = ________________mm
|  | Deep Excavation Safety Measures ( >1m) | CoPSESF | Every excavation >1.0 m in depth | Excavation checked and approved, Excavations exceeding 1m in depth to be benched | H | Richard Taare | Hold point - No persons may enter the trench until it is adequately benched and deemed to be safe as per the Safety in Exccavations and Shafts for Foundatons |  | Pat Thompson
|  | Unsuitable Foundation | TNZ F3 Section 3.5 | Every 5 m of excavated area | Unsuitable foundation material shall be removed to a minimum depth of 600 mm within carriageway and replaced with suitable material and compacted in 150 mm layers. | V | Richard Taare | Unsuitable foundation (very soft = scala < 3 blows/100 mm or expandable clays, irregular or fragmented rock and saturated soils) |  | Pat Thompson
|  | Level Control | None | Every 1m along length of culvert | String line between existing inlet and outlet invert elevations with tolerance -25mm + 5mm | V | Richard Taare |  |  | Pat Thompson
|  | Level Marks | None | 3 locations along one side of excavated trench | Layer depth markings visible on photo diary. | V | Richard Taare | Hold point - No physical works are to be commenced until white/yellow spray paint markings indicating backfill material layers are visible on one side of trench for photo record |  | Pat Thompson
|  | Site Diary Photos/ inspections | Physical / Visual check | Before removal of unsuitable material | Photograph unsuitable foundation material prior to removal of material (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Bedding |  | Bedding Material | TNZ F3 Section 3.6 AS/NZS 3725:2007 | Per Site | All bedding material shall satisfy the requirements in AS/NZS 3725:2007 and AS/NZS 2566 | V | Richard Taare |  |  | Pat Thompson
|  | Level Control | None | Every 1m along length of culvert | String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Physical / Visual check | Before pipe installation | Photograph bedding material after placement and compaction (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Pipe Installation |  | Inspection | Physical / Visual check | Before pipe Jointing | Verify culvert alignment (straightness) | V | Richard Taare |  |  | Pat Thompson
Jointing |  | Visual/Physical | Physical / Visual check | Per Join | All joins must be watertight and present a smooth invert surface | V | Richard Taare |  |  | Pat Thompson
|  | Mortar | TNZ F3 Section 2.4 NZS 3103: 1990 | Per Bag | Mortar shall comply with NZS 3103: 1990 | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Physical / Visual check | Before Backfilling | Photograph pipe and joins after installation (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Backfilling (Layers of 150mm) |  | Fill Material | TNZ F3 section 6.3 | Per Stockpile | Any material that is not type W or type U defined in TNZ F1:1997 | V | Richard Taare |  |  | Pat Thompson
|  | Density | ASTM D5874-95 | 1 sample per 5m² lot or at least 5 samples | Compaction requirements using the Clegg Impact Hammer tests CIV>25 per 150mm layer | V | Richard Taare |  |  | Pat Thompson
|  | Level Control | None | Every 1m along length of culvert | String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Before placing sub base | Photograph backfilling after installation of each 150mm layer (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Sub base - AP65 |  | Density | ASTM D5874-95 | 1 sample per 5m² lot or at least 5 samples | Compaction requirements using the Clegg Impact Hammer tests CIV>32 per 150mm layer | V | Richard Taare |  |  | Pat Thompson
|  | Level Control | None | Every 1m along length of culvert | String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Before placing base | Photograph sub base after installation of each layer (evidence) | H | Richard Taare | Hold point - No physical works are to be commenced until photos are taken |  | Pat Thompson
Basecourse - AP40 |  | Density | ASTM D5874-95 | 1 sample per 2m² lot or at least 5 samples | Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer | V | Richard Taare |  |  | Pat Thompson
|  | Level Control | None | None | Tie-in flush with adjacent road surface +20mm mound in middle of road crossing | V | Richard Taare |  |  | Pat Thompson
|  | Site Diary Photos/ inspections | Take Photos | Upon completion of basecoarse | Photograph basecourse upon completion of thereof (evidence) | V | Richard Taare |  |  | Pat Thompson
Ancillary Concrete | Head/wing wall | Visual/Physical | NZS 3114:1987 | Per Structure | All concrete faces should comply with NZS 3114:1987 and NZS 3101: Part 1: 2006 | V | Richard Taare |  |  | Pat Thompson
| Concrete cover | Visual/Physical | NZS 3114:1987 | Per Structure | All reinforcing bar/mesh shall have a minimum of 40 mm cover | V | Richard Taare |  |  | Pat Thompson
Timber Structure | Head/wing wall | Visual/Physical |  | Per structure | All timber in contact with the ground must be at minimum H4 treated | V | Richard Taare |  |  | Pat Thompson
Sandbag Structure | Headwall/wingwall | Visual/Physical |  | Per Structure | Install sandbag headwall at inlet | V | Richard Taare |  |  | Pat Thompson
Manhole |  | Visual/Physical | NZTA P46 5.5 | Per structure | To comply with minimum requirements of NZTA stormwater system design | V | Richard Taare |  |  | Pat Thompson
Catchpit |  | Visual/Physical | NZTA P46 5.3 | Per structure | To comply with minimum requirements of NZTA stormwater system design | V | Richard Taare |  |  | Pat Thompson
Flume |  | Visual/Physical |  | Per structure | 10 m flume Secured in place with iron standards every 2 m, minimum 250 mm flume lap required. Minimum 500 mm rock embedment | V | Richard Taare |  |  | Pat Thompson
Rip Rap |  | Visual/Physical |  | Per structure | 200 mm Rip Rap located to provide scour protection at Inlet (1 m wide x 2 m long x 0.4 m deep) with A19 Geotextile | V | Richard Taare |  |  | Pat Thompson
Sandbag Structure, At culvert 26 |  | Headwall/wingwall | Visual/Physical |  | Per Structure | Install sandbag headwall at inlet | Richard Taare |  |  | Pat Thompson
Site Reinstatement / Clearance
Clean Culvert No26 & No27 |  | Visual check |  | Along openned sections | Remove all debris from within culvert | V | Richard Taare |  |  | Pat Thompson
Drainage, if applicabe |  | Table Drains | As per existing | Where required | Clean andgrade table drains as required upstream of culvert inlets | V | Richard Taare |  |  | Pat Thompson
Traffic Services | Marker pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual inspection | All | Replaced in same position, height etc | V | Richard Taare | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Pat Thompson
Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W | Richard Taare |  |  | Pat Thompson
Drainage |  | Table Drains | As per existing | Where required | Regrade table drains as required upstream of culvert inlets (minimum 30 m either side) | V | Richard Taare
Reinstate seal |  | Visual check |  | Per worksite | Seal reapired where it has been damged or removed | H | Richard Taare | Hold Point - TM to remain until surface has been sealed |  | Pat Thompson
Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W | Richard Taare |  |  | Pat Thompson
Site left clean & tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V | Richard Taare |  |  | Pat Thompson
[5 empty] | · Plant removed |  | Richard Taare |  |  | Pat Thompson
[5 empty] | · Litter cleared from site |  | Richard Taare |  |  | Pat Thompson
Quality Assurance Close Out by: | _______________________________________________ |  | Date: _____________
This record to contract file. |  | (signature) | ________________________________________________

## Sheet2
PAVEMENT RENEWALS INSPECTION AND TEST PLAN SIGNATURE LIST
Name | Signature | Date
Pat Thompson
Richard Taare
Nikhil Mishra
Akhil Mohan
Kapil Vashisht
Mark Joblin