## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Stabilisation ITP | itp |  |  |  |  | Stabilisation ITP
section | Preliminary & General
checkpoint | Approved RQP
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3 TRWNOC
label | TYPE - H
label | ASSESSOR - Mark Joblin
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | RESPONSIBLE PERSON - Nikhil Mishra
checkpoint | Design Acceptance
label | VERIFICATION ACTIVITY - Confirmation
label | METHODS OR REFERENCE - Contract Specification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3 TRWNOC
label | TYPE - H
label | ASSESSOR - Mark Joblin
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | RESPONSIBLE PERSON - Nikhil Mishra
section | Set-out / Site preparation
checkpoint | Setout
label | METHODS OR REFERENCE - Best Practice
label | FREQ. - Per installation
label | ACCEPTANCE CRITERIA - According to existing road profile and alignment
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Zero service strikes
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Cultural/Heritage Risk Assessment
label | VERIFICATION ACTIVITY - Notification
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Where risk of cultural discovery
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Notification of intention to start work
label | VERIFICATION ACTIVITY - Notification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Letter drop to local residents
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 48 hours of establishing on site.
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Archaeological Risk
label | VERIFICATION ACTIVITY - Toolbox meeting
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Traffic Management - TMP
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - CoPTTM
label | FREQ. - Before traffic management set up
label | ACCEPTANCE CRITERIA - TMP checked and approved - Plans approved
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Traffic Management - Setup
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Traffic Management Plan
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Sediment Control
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - ESMP DN-ZH-GU074.1
label | FREQ. - Before Excavation Commences
label | ACCEPTANCE CRITERIA - Sediment and erosion control measures aligning with DN-ZH-GU074.1 and ESMP
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No physical works are to be commenced until sediment control measure is in place
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Dust Control
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - ESMP
label | FREQ. - During Execution
label | ACCEPTANCE CRITERIA - Complies with ESMP
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No physical works are to be commenced until dust control practices are implemented
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Noise Control
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - ESMP
label | FREQ. - During Execution
label | ACCEPTANCE CRITERIA - Complies with ESMP
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No physical works are to be commenced until noise control practices are implemented
label | RESPONSIBLE PERSON - Richard Taare
section | Preliminary Works
checkpoint | Shoulder Stripping
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - On site
label | ACCEPTANCE CRITERIA - Shoulder stripping completed
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Compaction Equipment
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - RQP 17.1.2
label | FREQ. - Prior to commencement
label | ACCEPTANCE CRITERIA - Compaction equipment is sufficient to achieve compaction
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Required by appendix 6.3
label | RESPONSIBLE PERSON - Akhil Mohan
section | Digout Repairs
checkpoint | Material
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/4 - Grading, broken faces, fines properties
label | FREQ. - Most frequent - Every 500m³ or 2 months
label | ACCEPTANCE CRITERIA - Confirming Lab report AP50
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Lab Report
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Depth
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - According QMP
label | FREQ. - every 10 m
label | ACCEPTANCE CRITERIA - Depth within +25 mm -5 mm
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - QC Form
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Compaction
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - Measurement
label | FREQ. - every 10 m
label | ACCEPTANCE CRITERIA - Compact in layers not exceeding 150 mm (compacted height)
label | TYPE - I
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - QC Form
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Density (as required)
label | VERIFICATION ACTIVITY - Site Test
label | METHODS OR REFERENCE - Nuclear Densometer - Maximum Dry Density
label | FREQ. - Each Programme
label | ACCEPTANCE CRITERIA - Subbase: Average ≥ 95% MDD
label | ○ Minimum ≥ 92% MDD
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - QC Form
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Surface
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - Straight Edge
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Repair edge - Max 50mm in 1m
label | ○ Depressions - Max 6mm in 2m straight edge
label | ○ Swept, tight surface - no dust
label | TYPE - I
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - QC Form
label | RESPONSIBLE PERSON - Akhil Mohan
section | Pavement
checkpoint | Water
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - ongoing
label | ACCEPTANCE CRITERIA - Water for stabilisation, construction and curing is free from impurities, 10 m3 allowed per day from natural source if resource consent obtained
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Water quality should be continually observed as clean, when impurities are observed a new source may be required
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Weather Limitations - Temperature
label | VERIFICATION ACTIVITY - Measure Temperature
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Minimum ambient air temp. Use weather report as evidence
label | ○ Cement 5°C
label | ○ Lime 10°C
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Work shall not be started if temperature is below the respective minimums.
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Weather Limitations - Wind
label | VERIFICATION ACTIVITY - Assessment
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Maximum wind speed of 25km/hr. Use weather report as evidence
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Work shall not be started if wind speed exceeds the maximum
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | Imported Basecourse Materials Testing (1)
label | VERIFICATION ACTIVITY - Comply with project specification
label | METHODS OR REFERENCE - Refer project specification
label | FREQ. - Refer project specification
label | ACCEPTANCE CRITERIA - Refer project specification in pavement report
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Imported Basecourse Materials Testing (2)
label | VERIFICATION ACTIVITY - Comply with project specification
label | METHODS OR REFERENCE - Refer project specification
label | FREQ. - Refer project specification
label | ACCEPTANCE CRITERIA - Refer project specification in pavement report
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Imported Basecourse Materials Testing - Particle Size Distribution
label | VERIFICATION ACTIVITY - Sieving Test
label | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.8.1
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - Particle size distribution fits within the AP50 envelope upper and lower limits
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Imported Basecourse Materials Testing - California Bearing Ratio
label | VERIFICATION ACTIVITY - CBR Test
label | METHODS OR REFERENCE - NZS 4407:1991 Test 3.15, TNZ M/4:2006
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - The soaked CBR of the basecourse aggregate shall not be less than 80%
label | TYPE - v
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Imported Basecourse Materials Testing - MDD
label | VERIFICATION ACTIVITY - Test
label | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
label | ACCEPTANCE CRITERIA - According to Design
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Stabilisation agents - Cement (1)
label | VERIFICATION ACTIVITY - See NZS 3122
label | METHODS OR REFERENCE - NZS 3122
label | FREQ. - per batch produced by supplier
label | ACCEPTANCE CRITERIA - Cement must comply with NZS 3122
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Stabilisation agents - Cement (2)
label | VERIFICATION ACTIVITY - See NZS 3122
label | METHODS OR REFERENCE - NZS 3122
label | FREQ. - per batch produced by supplier
label | ACCEPTANCE CRITERIA - Cement must comply with NZS 3122
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Stabilisation agents - Delivery
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Upon delivery
label | ACCEPTANCE CRITERIA - Stabilising agents to be delivered in tanks or trucks with Certificate of Loading
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Certificate of loading to be checked on site
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Weather Limitations - Wind
label | VERIFICATION ACTIVITY - Assessment
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Maximum wind speed of 25km/hr. Use weather report as evidence
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Work shall not be started if wind speed exceeds the maximum
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Weather Limitations - Rain
label | VERIFICATION ACTIVITY - Check forecast
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Daily
label | ACCEPTANCE CRITERIA - Zero likelihood of rain. Use weather report as evidence
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Spreading shall not commence if rain is forecast
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Spreading - Cement/lime
label | VERIFICATION ACTIVITY - Mat Test, 1m² canvas
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Every 400m²
label | ACCEPTANCE CRITERIA - Within ±0.5 kg/m² of the specified rate
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Time Limitations - Cement/lime
label | VERIFICATION ACTIVITY - The maximum time period from mixing to primary compaction
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - post stabilisation
label | ACCEPTANCE CRITERIA - 2 Hours
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | In-Situ Mixing - Cut Depth
label | VERIFICATION ACTIVITY - Depth measurement
label | FREQ. - at both ends of cut and every 100m
label | ACCEPTANCE CRITERIA - +- 20 mm of design depth
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | In-Situ Mixing - Depth of STAB
label | VERIFICATION ACTIVITY - Depth measurement
label | FREQ. - Random locations
label | ACCEPTANCE CRITERIA - Meet desgn depths
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
checkpoint | In-Situ Mixing - Join Overlap
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - Continuous
label | ACCEPTANCE CRITERIA - 100mm overlap
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - All cuts shall overlap by the minimum acceptance criteria
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | In-Situ Mixing - Particle breakdown
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - TNZ B/5
label | FREQ. - within the first 20m of each run, and where ever material changes
label | ACCEPTANCE CRITERIA - Well mixed material with acceptable particle size distribution
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Where breakdown is excessive, method of milling should be altered to avoid such breakdown
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | In-Situ Mixing - Client Acceptance
label | VERIFICATION ACTIVITY - Inspection
label | FREQ. - Per Site
label | ACCEPTANCE CRITERIA - Client to be present during stabilisation, photographic evidence shall be provided if the client is unable to attend
label | TYPE - H
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | DESCRIPTION - Hold Point - Client shall be notified prior to stabilisation so they have the opportunity to be present upon commencement of stabilisation
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Akhil Mohan
checkpoint | Construction STAB OLAY - Compaction
label | VERIFICATION ACTIVITY - NDM – maximum dry density
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - Base: Average ≥ 98% MDD, Minimum ≥ 95% MDD
label | TYPE - V
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (i.e. average & minimum MDD)
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
checkpoint | Construction STAB OLAY - Compaction
label | VERIFICATION ACTIVITY - NDM – maximum dry density
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - Subbase: Average ≥ 95% MDD, Minimum ≥ 92% MDD
label | TYPE - H
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (i.e. average & minimum MDD)
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
checkpoint | Construction STAB OLAY - Degree of Saturation (DOS) (1)
label | VERIFICATION ACTIVITY - DOS
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - DOS ≤ 80% from Solid Density and %W
label | TYPE - V
label | ASSESSOR - Jack Lewis/Ian Symons/ Akhil Mohan
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Construction STAB OLAY - Degree of Saturation (DOS) (2)
label | VERIFICATION ACTIVITY - DOS
label | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
label | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - DOS ≤ 80% from Solid Density and %W
label | TYPE - H
label | ASSESSOR - Nikhil Mishraa
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Construction STAB OLAY - Particle Size Distribution
label | VERIFICATION ACTIVITY - PSD
label | METHODS OR REFERENCE - NZS 4407:2015, Test 3.8.1
label | FREQ. - 1 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - comparison to the upper and lower limits of M/4 Specification
label | TYPE - H
label | ASSESSOR - Jack Lewis/Ian Symons/Akhil Mohan
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Construction STAB OLAY - Unconfined Compressive Strength (UCS)
label | VERIFICATION ACTIVITY - UCS
label | METHODS OR REFERENCE - NZS 4407:2015, Test 2.4.8.2a
label | FREQ. - 1 tests per homogeneous lot of up to 1000m2 of laid pavement
label | ACCEPTANCE CRITERIA - Test to confirm compressive strength obatined relative to pavement design
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - UCS 1 - 2 lightly bound pavement, > 2 bound pavements
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Construction STAB OLAY - Surface shape/profile Layer thickness (1)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Visual inspection
label | ○ Cut/fill tolerance check
label | ○ String records
label | ○ Straight edge
label | FREQ. - 1 test per 20m
label | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge.
label | ○ Gradual deviations
label | ○ No ponding if crossfall < 1%
label | TYPE - V
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
checkpoint | Construction STAB OLAY - Surface shape/profile Layer thickness (2)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Visual inspection
label | ○ Cut/fill tolerance check
label | ○ String records
label | ○ Straight edge
label | FREQ. - 1 test per 20m
label | ACCEPTANCE CRITERIA - -5mm +15mm or ±5mm at lip of concrete channel
label | TYPE - V
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
checkpoint | Construction STAB OLAY - Tolerances: width unconstrained (1)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Confirm offset from lift pegs
label | FREQ. - 1 at every lift peg or per 180 m2
label | ACCEPTANCE CRITERIA - -20mm
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Construction STAB OLAY - Tolerances: width unconstrained (2)
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Confirm offset from lift pegs
label | FREQ. - 1 at every lift peg or per 180 m2
label | ACCEPTANCE CRITERIA - +100mm
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Construction STAB OLAY - Tolerances: width constrained
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Stringline/lift pegs
label | FREQ. - 1 at every lift peg or per 180 m2
label | ACCEPTANCE CRITERIA - Zero
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Construction STAB OLAY - Visual appearance
label | VERIFICATION ACTIVITY - TNZ B/2
label | METHODS OR REFERENCE - Visual inspection after sweeping
label | FREQ. - Immediately prior to sealing
label | ACCEPTANCE CRITERIA - No loose material remaining, Photo as evidence
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
label | RESPONSIBLE PERSON - Akhil Mohan
section | Shoulders
checkpoint | Slope (1)
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Visual inspection with smart level
label | ACCEPTANCE CRITERIA - Slopes consistent
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Slope (2)
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Visual inspection with smart level
label | ACCEPTANCE CRITERIA - Slopes consistent
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Compaction (1)
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Drive over 4T, check wheel tracks
label | FREQ. - All shoulders
label | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Compaction (2)
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Drive over 4T, check wheel tracks
label | FREQ. - All shoulders
label | ACCEPTANCE CRITERIA - Driver operated rollers must not come within 1 m of the sloped shoulder > 1:5 slope
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
label | RESPONSIBLE PERSON - Akhil Mohan
section | Site Reinstatement / Clearance
checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (1)
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All signs/markers
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc.
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (2)
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All signs/markers
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | RESPONSIBLE PERSON - Akhil Mohan
checkpoint | Traffic Management Removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - When safe, after all physical works completed
label | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited
label | RESPONSIBLE PERSON - Richard Taare
checkpoint | Site left clean & tidy
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - After vacating site
label | ACCEPTANCE CRITERIA - Stockpiles removed, EMP installed, Plant removed, clear litter
label | TYPE - H
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
section | As Built Records
checkpoint | Collect asset data
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | FREQ. - During construction
label | ACCEPTANCE CRITERIA - All relevant as built information collected.
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Nikhil Mishra
checkpoint | Enter asset data into RAMM and/or register(s)
label | VERIFICATION ACTIVITY - SHDOM (SM050)
label | METHODS OR REFERENCE - RAMM
label | FREQ. - At completion of work.
label | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
label | TYPE - H
label | DESCRIPTION - Hold Point – project cannot be closed until data entered.
label | RESPONSIBLE PERSON - Paul Grant