## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Civil - Drainage Checklist |  | Civil - Drainage |  | 124d2cb2-dde2-42b4-b954-8e1ca2a4c11d
| section | Pre-start
| checkpoint | Locates done on site – confirm no clash with pre-existing underground services
| checkpoint | Appropriate permits in place
| checkpoint | GL and datum provided
| checkpoint | Upload drawings / check services depths, confirm location, filling/digging
| checkpoint | Clear work area
| section | Trenching
| checkpoint | Delineation of area
| checkpoint | Benching appropriate for ground conditions
| checkpoint | Safety of trenching conditions and edge protection
| checkpoint | Civil Eng inspection report received and close-out if unsuitable subgrade conditions exist
| section | Installation
| checkpoint | Confirm correct bedding material being used and spot check RL’s
| checkpoint | Manhole installation
6cd6e903-e416-4d0c-ad82-38ffba52e1ff | tickbox | Confirm MH diameter
b20e33ff-fc40-4a16-8b7c-42ee5e2617e2 | tickbox | Reo
e2f4d1fa-78bc-40c5-9bec-31016f9be862 | tickbox | Joint sealing (if precast)
7add8d48-662a-43f2-befd-1db905d9cf23 | tickbox | Invert level
523ada56-529e-428b-8752-17e6d2d0b8e3 | tickbox | Confirm concrete grade
| checkpoint | Pipes installed and correct junctions/connections
| checkpoint | Civil Eng inspection report received and close-out for first pipe run
| checkpoint | Council inspection report received and close-out
| section | Backfilling
| checkpoint | Appropriate backfill material
| checkpoint | Backfill at 150mm lifts and compact as per Civil spec
| section | Post Backfilling
| checkpoint | Internal manhole works
c86e0894-36d8-5186-a72f-a7a7428cfd3e | tickbox | Civil Eng Splitter weir manholes – weir pre-pour inspection (first manhole)
c3a67ff4-f316-5eb8-94c4-e8e2570875ab | tickbox | Splitters and benching completed
| checkpoint | Soakholes
48fd210a-d850-52e2-942a-7ba870883371 | tickbox | Civil Eng Inspection of selection of rock bore installation report received and close-out
4a6d677c-9c3b-5c2a-8e83-9eba1b8a40c8 | tickbox | Civil Eng inspection of selected of soakage testing
51f0e36e-6c5e-5e7c-8c74-38d8b2b34328 | tickbox | Council inspection report received and close-out – as-built plan required
| checkpoint | Drainage QA received and as built
| checklist | Civil - Roads |  | Civil - Roads V2 |  | 59a6e795-9b21-4190-b83d-0ac4478999c7
| section | Pre-Hand Over
| checkpoint | In ground services QA and testing received
42a61e44-440d-5a1e-8068-c1e9e48ae635 | tickbox | Electrical
c68df2b7-adde-5b3a-871a-292154477b66 | tickbox | Hydraulic
41cee28b-f4b3-51ac-9062-3d755d000c7f | tickbox | Coms, Chorus
854c83c4-5873-545f-8281-2e122731b927 | tickbox | Façade works completed
| checkpoint | Drainage works complete
3f8ea192-45de-53b4-86d1-d3de021e33b9 | tickbox | Cess pits, manhole benching and final RL, all ORG installed
| checkpoint | Road clear and ready for hand over
| section | Road Build-Up
| checkpoint | Ensure road is built up in GP65
| checkpoint | Ensure testing is completed.
5a09b68e-2b8f-53da-9a15-a11867047b21 | tickbox | CRB 6 and proof rolled
| section | Channel Drains Install
| checkpoint | Correct RL to slab
| checkpoint | Sumps installed
| checkpoint | Channel drains QA
| checkpoint | Channel drains encased on concrete
| section | Kerb Install
| checkpoint | Layout/pre-pour
a3fd0010-c33f-53e3-8302-9d006e7704fc | tickbox | Spot Check RL’s
935bd2ec-153b-5ab7-8887-048730a75c82 | tickbox | Confirm mix
ad61d071-1033-5b5b-a8c6-fe63e323d767 | tickbox | Check kerb location
80f1a504-1b67-5992-9f12-cd9d1cf99401 | tickbox | Check kerb type
| checkpoint | Saw cuts 4m spacing
| checkpoint | Chip/cracks
| section | Concrete Loading Bays
| checkpoint | Build Up
32257c5f-a1f3-501d-b026-6a7135041c38 | tickbox | 100mm GP40
033f8ade-ee8f-551f-9de5-385cab926729 | tickbox | Sand/fines
| checkpoint | 1 layer 661 mesh 60mm top cover
| checkpoint | Trimmer bars at corners 2*D16 1200mm long
ab0bf92e-decc-51a5-90b7-49c07d569f45 | tickbox | Unless corner coincides with sawcut
| checkpoint | Trimmers around manholes
| checkpoint | Refer Civil drawing 115
| checkpoint | 175mm 30MPa
| checkpoint | Chamfer at asphalt transition asphalt to sit 5mm proud.
| checkpoint | Broom finish
| checkpoint | Saw cuts
| section | Walkway Install
| checkpoint | Water cure 7 days
| checkpoint | Chorus Tuds
69b3d83d-440c-5d71-84a3-d0f9fd1c77e4 | tickbox | Set out to correct height and slope
| checkpoint | Build Up/Falls
8c3f67fa-10b2-548d-9d8a-99d03e7592b3 | tickbox | 150mm GP40 or 200mm GP65 and 100mm GP40
1618d43a-cad7-525f-93f2-4013179c6ac0 | tickbox | Check RL’s at critical points
c242b2c7-f965-50de-a6ab-67a15fba6772 | tickbox | 25mm asphalt thickness
| checkpoint | Lay Walkway
7bef1887-1151-5472-8988-40fb83664587 | tickbox | Visual check finish/transitions
| section | Manhole Lids Install
| checkpoint | Set to proper RL and grade
| section | Road Install
| checkpoint | 100mm GP 40
02eb2810-ff33-5624-9420-eaa67a0206f4 | tickbox | 3% slope from crown
4972956e-2b55-537e-a605-fe849f6e775c | tickbox | 35mm Asphalt thickness
| section | Line Marking
| checkpoint | Layout as per Drawings
| checklist | Civil – Buildings Subgrade |  | Civil – Buildings Subgrade |  | 89ad418b-6828-4f01-ac3c-f092ee049816
| section | Subgrade base
| checkpoint | Geotech Eng inspection report received- and close-out
| checkpoint | Geotech Eng Inspection of subgrade and proof rolling prior to filling
| section | Building Subgrade build-up
| checkpoint | GL and datum provided
| checkpoint | Placement of hardfill layer compacted as per design
| checkpoint | Drainage piping installed under foundation level
| checkpoint | Platforms spot checks heights and location
| section | Subgrade Sign-off
| checkpoint | Subgrade QA and test results received
| checkpoint | Geotech Eng Inspection of subgrade and proof rolling report received and close-out
| checklist | Civil – Footpath In Ground Services |  | Civil – Footpath In Ground Services |  | 935eee73-0071-4b5d-9fc2-aefe02fd9712
| section | Pre-start
| checkpoint | Stormwater laterals exposed and extended to sump locations
| checkpoint | Trench formed and sand bed completed
| checkpoint | Conduits underslab completed
| section | Services trench
| checkpoint | Electrical cables running from DB location to each unit
| checkpoint | Electrical cables top covered and cable slab installed and covered
| checkpoint | Hydraulic service joined and water tested
| checkpoint | Chorus pits & tuds located and levels agreed
| checkpoint | Fire alarms conduits and cables completed
| checkpoint | Conduits crossing roads where required
| section | Post-services
| checkpoint | Fines cover
| checkpoint | Chorus pits to final RL
| checkpoint | Final backfill & compacted
| checklist | Consultant Inspection |  | Consultant Inspection |  | f4453121-a2db-4f7b-966a-44b91112b9b7
| section | Details
| checkpoint | Inspection completed, attached and any relevant observations closed out
85d5c57f-5087-594a-9409-ad4a5f8cf854 | textbox | Date of inspection
d22c574d-b540-5c25-bcde-870e97bc0a2b | textbox | Type of inspection
056b2541-4a8b-5b2c-9acb-bfec89374578 | textbox | Area of inspection
540522ff-0a02-5422-9757-c4e19e4bf71c | tickbox | Inspection report attached
| signoff | Sign off
| checkpoint | All relevant observation closeout evidence attached here if applicable
88bdd135-f1c4-58ad-8725-aad5bdc3811f | textbox | Corrective action required
| checklist | Council Inspection |  | Council Inspection |  | 799e78b0-0f0a-4cc9-8f0f-6cd2d91081f2
| section | Details
| checkpoint | Inspection completed, attached and any relevant observations closed out
a811dc5b-ac83-5470-8e22-e6605df80fcd | textbox | Date of inspection
eaa36b12-dd05-5534-9855-79c4bd6c0898 | textbox | Type of inspection
bc8f8242-678a-5cb5-861d-6fb07e05967b | textbox | Area of inspection
46b42bf2-dfd2-563b-b4d1-592bae41d634 | tickbox | Inspection report attached
bd8c65cf-b0da-509c-8292-66c15022fdc4 | dropdown | Inspection outcome | Fail, Partial Pass, Pass
| signoff | Sign off
| checkpoint | All relevant observation closeout evidence attached here if applicable
747abae4-11b7-5603-bb0c-287329ec618b | textbox | Corrective action required
| checklist | Council Inspection - Observations |  | Observation # |  | 21347c87-1b03-4f76-8d61-76570d8d245b
| checkpoint | All relevant observation closeout evidence attached here if applicable
747abae4-11b7-5603-bb0c-287329ec618b | textbox | Corrective action required
| checklist | Facade - Below Ground Waterproofing |  | Facade - Below Ground Waterproofing |  | 450919e1-d57a-4d4d-962b-9d92d78c1874
| section | Pre-start
| checkpoint | Panel QA received
| checkpoint | Block wall QA received
| checkpoint | Panel joints grouted/sealed
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| checkpoint | Safe access
| section | Installation
| checkpoint | Waterproofing as per architectural drawings
| checkpoint | Council inspection report received and close-out
| section | Post install
| checkpoint | Protective layers
| checkpoint | Tanking QA received
| checklist | Façade – Eave and Roof |  | Façade – Eave and Roof |  | cc471d2d-f573-4042-92f3-c435598922f3
| section | Pre-start
| checkpoint | Steel QA received
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| checkpoint | Safe access
| section | Eaves
| checkpoint | Framing - DPC between timber and steel
| checkpoint | Framing -Timber frame fixings to steel frame/purlins
| section | Services
| checkpoint | Services signoff/QA including nogs
| section | RAB
| checkpoint | HOLD POINT - Council pre-line inspection report received and close-out
| checkpoint | RAB signoff/QA
| section | ACP
| checkpoint | ACP installed as per shop drawings
| checkpoint | Services cables pulled through – check builders work
| checkpoint | Sealants
| checkpoint | ACP signoff/QA
| section | Roof
| checkpoint | Framing - DPC between timber and steel
| checkpoint | Framing - Timber frame fixings to steel frame/purlins
| checkpoint | Gutter waterproofing sign-off/QA
| checkpoint | ILD Testing
| checkpoint | Mesh and underlay installed
| checkpoint | Check roof sheets fixings
| checkpoint | Service penetrations installed
| checkpoint | Proper septation
| checkpoint | Roof finishes
| checkpoint | Painting panels
| checkpoint | Cap flashings
| checkpoint | Apron flashings
| checkpoint | Services penetrations
| checkpoint | EPDM tape / termination bar and sealants installed
| checkpoint | Gutter and downpipe installed
| checkpoint | Roof signoff/QA
| section | Roof safety anchors
| checkpoint | Check layout (positioning)
| checkpoint | Roof anchors tagged
| checkpoint | Roof anchors signoff/QA
| checklist | Facade – Shop Front |  | Facade – Shop Front |  | aaedfc85-0acc-4cdf-b0bc-498b79bff4ca
| section | Pre-start
| checkpoint | Site measure complete
| checkpoint | Steel QA received
| checkpoint | Carpentry sign-off received
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| checkpoint | Waterproofing sign off as per details
| section | Install
| checkpoint | Prime surfaces
| checkpoint | Seismic frames
| checkpoint | Inserts
| checkpoint | Glazing
| checkpoint | Air seals completed
| checkpoint | Bespoke flashings measured
| section | Post install
| checkpoint | Protection 1.5m high
| checkpoint | AAMA 501 water test completed and passed – results received
| checkpoint | QA subby and consultant (inspection requirements?)
| checklist | Fitout - Carpentry Framing |  | Fitout - Carpentry Framing |  | e8ced4e5-c36a-43b0-9cc4-927b8c90733f
| section | Mezzanine
| checkpoint | Framing complete as per Arch details
| checkpoint | DPM between timber and beam
| checkpoint | Balustrade 150x150mm 19mm packer.
| checkpoint | Framing/beam packing continuous to receive the Balustrade posts
| checkpoint | Stair measure complete
| checkpoint | Stairs received on site and installed
| checkpoint | 70mm min width of stringer against precast
| checkpoint | Inside stringer notching clear
| checkpoint | Base of stair detail correct
| checkpoint | Battens to receive Fireline installed correctly
| checkpoint | All nails flush within framing to receive GIB
| checkpoint | Fireline installed as per Spec
| checkpoint | AC inspection No.1 Post line Fireline
| section | Bathroom
| checkpoint | DPC between timber and concrete
| checkpoint | Framing as per Arch drawings
| checkpoint | Fixings to concrete panel and slab correct
| checkpoint | Door opening Correct
| checkpoint | Service nogs / stud exclusion zones
| checkpoint | Set out confirmed by EXP and accepted by ZYJ
| checkpoint | All nails flush within framing
| checkpoint | AC inspection No.1 Pre-line inspection
| checkpoint | GIB install to walls
| checkpoint | Ceiling Grid installed – services accounted.
| checkpoint | Services installed – TRF, AM, TC
| checkpoint | Ceiling GIB installed
| checkpoint | AC inspection No.2 Post line
| checklist | Fitout - Installation |  | Fitout - Installation |  | 6cf7a78b-9d80-4611-b8a1-b48b3df71d34
| section | Mezzanine
| checkpoint | Balustrade measure
| checkpoint | Stairwell opening and location as per arch dwg 1701
| checkpoint | Order stairwell
| checkpoint | Check detail for balustrade (3302 – interior details)
| checkpoint | Stair details as per arch and SD
| checkpoint | Handrail site measure
| checkpoint | Install eco-ply ceiling
| signoff | Line/stop internal service penetration prior to eco ply
| section | Bathroom Walls/Ceilings
| checkpoint | Bathroom Lining
| signoff | Bathroom are lined and fire stopped before bathroom framing
| section | High Level Services
| checkpoint | Services sign-off
| checkpoint | Pre-line photos
| signoff | Council Pre-Line Inspection
| section | Set / Sand / Paint
| checkpoint | Plasterboard fixings as per requirements (aqualine x standard)
| section | Tiling and Waterproofing
| checkpoint | Stopping complete
| checkpoint | Sealants installed
| checkpoint | Waterproofing QA
| checkpoint | Tiling QA
| checklist | Fitout - Prestart |  | Fitout - Prestart |  | 8b6081c1-5601-4967-a12b-c1d415cf113f
| checkpoint | Slab poured and curing complete
| checkpoint | Mezzanine steel QA/Sign-off
| checkpoint | Intumescent paint to mezzanine steel (beams and posts)
| checkpoint | GL and datum provided
| checkpoint | Sealant complete between precast panels
| checklist | Footings |  | Footings |  | 03df9a4d-289c-40ca-94c7-3818f40e1645
| section | Pre-start
| checkpoint | GL and datum provided
| checkpoint | Geotechnical Eng subgrade inspection report received and closed-out
| checkpoint | Check for clash
| checkpoint | Upload drawings, detail /Mark up plan
| section | Pre-Pour
| checkpoint | Service trade sign off/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Formwork signoff/QA
| checkpoint | Check levels
| checkpoint | GN inspection- Prepour
584da06d-898d-523c-b9f4-22a18cbc177b | tickbox | Reo details checked
f7bd4f24-eb8c-5624-b00a-362ef018334b | tickbox | Any CAN, Engr requirements
74cbf223-aa2a-5067-a82a-359ef2f7a809 | tickbox | Starters, scabbling, cover checked
53503008-e82f-5299-ab6d-bed590ee638f | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Stop-End checked
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Pour QA received
| checklist | In Situ Concrete |  | In Situ Concrete |  | 721e2360-cf50-40b7-95b7-5a6a52a57f06
| section | Pre-Pour
| checkpoint | GL and datum provided
| checkpoint | Check for clash
| checkpoint | Waterproofing done & QA received
| checkpoint | Waterstop Gasket installed
| checkpoint | GN inspection
c31276a5-e3cc-5427-b5e5-4f3f8d8cfbed | tickbox | Reo Details checked
3d26fa73-8b45-5781-be3f-1905a0217edd | tickbox | Any CAN, Engr requirements
a42ed4d2-d222-5bcc-a79f-e257428bf835 | tickbox | Starters, scabbling, cover checked
43b259f3-fe49-5fd6-8e90-d68fad2d1c45 | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Upload drawings, detail /Mark up plan
| section | Access/safety
| checkpoint | Access for pump
| checkpoint | Check TA
| checkpoint | Safe access to all areas of spray
| checkpoint | Exposed reo capped
| section | Spray / Pour
| checkpoint | Confirm mix & test
| checkpoint | Confirm Finish
| section | Post pour
| checkpoint | Formwork removed
| checkpoint | Pour QA received including concrete dockets
| checkpoint | Mill certis received
| checklist | Insitu Piles |  | Insitu Piles |  | 6c8786c0-c580-4d09-8ca4-5921f832d21b
| section | Details
| checkpoint | Pile location marked and confirmed
| checkpoint | Pile Cage dimension and specification checked
1ebc5b73-a0a5-50a2-b26f-fa90f8f31aac | note | Attach Docket
| checkpoint | Pile drilling Card - refer details with the approved pile schedule
| checkpoint | Engineer Inspection
| checkpoint | Concrete pour & docket received
| checkpoint | Mill Certificate received
| checkpoint | Surveyworks Asbuilt check
| checklist | Insitu Piles Checklist | itp | Insitu Piles |  | a88129a9-94f4-4f1a-bac4-b416889401c8
| section | Preliminary Tasks
| checkpoint | Confirm Pile installation plan including methodology, material and equipment submitted
aad92bda-2664-5684-85d8-ac46105d5e3f | note | Sub-Contract signing
| section | Site Start Up Tasks
| checkpoint | Confirm full services and utilities check by subcontractor. Permit to work in place
1ff69a78-304f-5ff1-bef9-2327ab135518 | note | Prior to mobilization
| checkpoint | Confirm an adequate site surface has been established for a safe working platform and check periodically once installation is underway.
274e4199-4609-5c0e-bcf0-af268e3c000a | note | 1 week prior and intermittently after
| checkpoint | Confirm all piles to be set out in accordance with design requirements and appropriate procedures taken to protect adjacent services, structures etc.
39b65b1d-06eb-5451-9329-ee7c0c1ba814 | note | Prior to installation of 1st pile
| section | Construction Tasks
| checkpoint | Confirm correct equipment is in place to check the verticality and position of rig, and that the mast is vertical in both axes prior to construction of each pile
8f90764a-26a5-54fd-ad0e-41520fa86710 | note | Prior to installation of 1st pile and periodically after
| checkpoint | Confirm pile construction has not been carried out within the specified distance of newly cast piles until concrete has attained the strength specified. Refer to installation methodology provided.
70b4018e-e24d-5d43-afcf-77c7e21de1c2 | note | Each pile
| checkpoint | Confirm that pile depth has been checked at completion of boring. Toe level to at or below target depth
1d929ece-f6f1-5a54-b680-7583325fbe41 | textbox |  |  |  | m depth
31fa7856-713f-5a2e-8d38-fd9bc67d051c | note | Each pile
| checkpoint | Sight delivery dockets to confirm all in accordance with engineers specification.
5b01ba3e-dffa-5ac4-a11f-64a1cae3968d | note | Each concrete delivery
| checkpoint | Confirm that subcontractor has checked that steel is not excessively rusted, cage has been sturdily constructed and that the correct cage has been installed for each pile.
7af01921-38cc-575c-8eb4-2f2e9815a008 | note | Each reinf. Cage batch
| checkpoint | Dimensional check, length, bar diameter, nr of bars. Make sure compliant with technical package.
61f8d457-3081-5c32-935f-e095776a9b7f | note | Random control check
| checkpoint | Check cage has been installed at the correct level and is centralised, ensure cover requirements are met. All as per specification and documents.
c9a27d0a-9e00-544c-af03-c5f0e10465a1 | note | Random control check
| checkpoint | Obtain Engineers site reports and signoff as required.
a8d66440-d4f6-56dc-ac2c-85f4087b08a3 | note | As per Contract
| checkpoint | Confirm top of piles have been trimmed to elevations indicated on design drawings prior to construction of pile caps.
a1f5f14b-1587-5c9c-84f9-c2d8b78ae80c | note | After completion of installation
| section | Post Construction Tasks
| checkpoint | Obtain as-built drawings to confirm grid layout is completely in accordance with all drawings and specifications (all within tolerance)
937c4592-d188-5c57-9c64-385a32ef5100 | note | After completion
| checkpoint | All data and records required provided to Structural Engineer after completion of pile installation (as per required contract specification). Include any Engineer’s site reports and sign off.
157dad8c-3e70-5546-b991-bcbd5b78a21e | note | After completion of works
| checkpoint | Dynamic pile testing (if required by the contract) carried out as per specification requirements. Written pile test results submitted for acceptance. Obtain sign off from Structural Engineer. (Attach certificate)
269a9bb3-f1c9-5664-a58f-17b5ac3698af | note | As per contract requirements
| checkpoint | Confirm all inspections as identified on the cover page have been undertaken
06600b44-5607-5b42-b8d8-ad2c9d51181e | note | After Completion
| checkpoint | Subcon QA received including pilecards and dockets
| checklist | ITP - Pole Retaining Wall |  | ITP - Pole Retaining Wall |  | 6a958e3c-e1f2-4ec3-ac1e-79e8975f6ebb
| section | 1. Pre-start
| checkpoint | GL and datum provided
| checkpoint | Clear work Area
| checkpoint | Review construction drawings and set-out
| checkpoint | Geotechnical Eng inspection report received and closed-out
| section | 2. Set up/ Pre-pour
| checkpoint | Service trade sign off/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Check RL levels
| checkpoint | Subcon sign off/QA
| checkpoint | GN inspection
8e7bec4b-3b08-5d71-a637-6c83dc3ef847 | tickbox | i. Details checked
8ff39581-c639-5c71-b7f4-0a428ffb4e4c | tickbox | ii. Verify materials and check poles for visible defects or damage
badded84-0aae-59a2-91e0-3b1d197072b7 | tickbox | iii. Poles are placed according to alignment and levels.
16407ff3-4abe-59c0-a6a6-9fa0fcfa095f | tickbox | iv. Ensure poles are secured and ready for pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | 3. Access/Safety
| checkpoint | Clear access for trucks/pump/rigs
| checkpoint | Safe access to all areas of pour
| section | 4. Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | 5. Post pour
| checkpoint | Backfilling (200mm in layers)
| checkpoint | Levels
| checkpoint | Pour QA received including dockets
| checklist | ITP - Structure - Slab on Grade |  | ITP - Structure - Slab on Grade |  | 701beb82-28f0-45b9-a79f-b3685dc5afa0
| section | Pre-start
| checkpoint | Columns/GB sign-off/QA received
| checkpoint | Services sign-off
2db17213-52f0-5fcf-82fe-bac71a4e8033 | tickbox | i. Electrical
5dafd3d9-ca0f-5e88-95c1-1b002d6ef3a0 | tickbox | ii. Fire
7a5cb49b-941c-5367-9781-1d50b178e975 | tickbox | iii. Hydraulic
bbb45f58-32b2-5d21-ad4d-ac5a73bc5821 | tickbox | iv. Comms and Fibre
| checkpoint | Subgrade sign-off/QA received
b8181f2e-bd2c-5271-a8e7-38744f074124 | tickbox | i. Backfill and blinding
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-Pour
| checkpoint | Waterproofing sign-off/QA
2da6d233-ca40-5197-b8b3-6a70ba58b2f4 | tickbox | i. DPM including tapes and laps
26241039-dfa7-5037-8cf3-fd1b17fff318 | tickbox | ii. Waterstop where applicable
| checkpoint | Formwork signoff/QA
d8bc15f1-9368-533a-b4de-67dc94a2345c | tickbox | i. Step down/ falls
0c082847-d6dd-5e98-a5a9-c2f4481df9bf | tickbox | ii. Ties, propping, seal formworks
01bbc981-d2d5-58cc-9b04-bbb0fc919928 | tickbox | iii. Seismic gap/expansion joints
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
af1066b9-f756-508b-b045-1a1110ff77b2 | tickbox | i. Details checked
c328f3ae-58d7-55bf-97b8-881d55c3cffe | tickbox | ii. Any CANs
600c7ed6-7566-55fe-8c80-fe17623ba846 | tickbox | iii. Check starters, scabbling, cover checked, thickenings
732e662e-c306-5272-9f02-7beb1257f24b | tickbox | iv. Reinforcement size, spacing, supports.
1b8ababd-265e-5b51-babf-f0b8eb13583e | tickbox | v. Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/safety/protection
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| checkpoint | Panel and steel protection
| checkpoint | Skip clean and ready
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Finish
| checkpoint | Levels
| checkpoint | Curing agent
| checkpoint | Saw cuts within 24h of pour and slurry removed
| checkpoint | Pour QA received including concrete dockets
| checklist | ITP Structure - Footing |  | ITP Structure - Footing |  | 4a136c02-8eaa-46c8-9361-c7d85a4cf773
| section | 1. Pre-start
| checkpoint | QA for sub-grade and relevant services received
| checkpoint | i. Site concrete allowed for in cut.
| checkpoint | GL and datum provided
| checkpoint | Clear work Area
| checkpoint | Review construction drawings and set-out
| checkpoint | Geotechnical Eng inspection report received and closed-out
| section | 2. Pre-pour
| checkpoint | Service trade sign off/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Formwork signoff/QA
| checkpoint | Check RL levels
| checkpoint | Check foundation width for propping
| checkpoint | Sump position check and block-off foundation if clash
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
| checkpoint | i. Details checked
| checkpoint | ii. Starters, scabbling, cover checked
| checkpoint | iii. Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | 3. Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | 4. Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | 5. Post pour
| checkpoint | Finish
| checkpoint | Levels
| checkpoint | Starters
| checkpoint | Pour QA received including dockets
| checklist | ITP Structure - In Situ Concrete (RC beam) |  | ITP Structure - In Situ Concrete (RC beam) |  | 7a5e815d-937f-46f2-9114-3a1446ce3438
| section | Pre-start
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | 2. Pre-pour
| checkpoint | Formwork signoff/QA
ef670c48-dd41-58db-8dbc-dd945f5516a5 | tickbox | i. Check RL levels
59eddef0-00da-5f22-a2ab-30a529c82e76 | tickbox | ii. Check Dimensions and alignment
bdefe7ea-878a-596b-aeb3-149950ee53bf | tickbox | iii. Check form ties and propping as per design
80b1ee4d-6fd6-57a1-9ced-097408f47914 | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
4e5d82a3-f934-5139-8283-73ce2bc1f737 | tickbox | i. Details checked
73f10c1c-277e-5c04-a6a9-7e931fee4a14 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
f5731e97-5ca3-56f6-8c3c-6af68c52ff6f | tickbox | iii. Check reinforcements size, spacing and cleanliness
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/safety
| checkpoint | Access for sprayer/pump
| checkpoint | Safe access to all areas of pour
| checkpoint | Exposed reo capped
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Checks
96130089-885a-5f11-b19d-965309b31ae8 | tickbox | i. Finish
70429381-23b3-5218-8f98-dc19683a3743 | tickbox | ii.Levels
| checkpoint | Pour QA received including concrete dockets
| checklist | ITP Structure - In Situ Concrete (RC Column) |  | ITP Structure - In Situ Concrete (RC Column) |  | b6b283c2-7f31-40da-9bfd-0103cd1d2e9d
| section | Pre-start
| checkpoint | Footing sign-off/QA received
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | GN inspection
8685dbce-2133-5d07-8902-bf433aa93781 | tickbox | i. Details checked
4aa88abf-c69b-52a2-bdfa-35c68e892550 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked and cast in items
1902df8e-3afa-5e19-98df-9adcf3cb7f9b | tickbox | iii. Check reinforcements size, spacing and cleanliness
| checkpoint | Formwork signoff/QA
8300dac9-f555-52cb-a65e-86f5edebee79 | tickbox | i. Check RL levels and benchmarks
09c13d34-cb05-5209-aef2-cdcf91e72529 | tickbox | ii. Check Dimensions and alignment
ea780471-ca3d-5fad-b208-36d8c3777237 | tickbox | iii. Check form ties and propping
125efa4b-7a4d-5650-8cc1-1622edd5f5a0 | tickbox | iiii. Overall Cleanliness and Seals and ready to Pour
| checkpoint | Reo sign off/QA
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/safety
| checkpoint | Access for sprayer/pump
| checkpoint | Safe access to all areas of spray
| checkpoint | Exposed reo capped
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Checks
8b38a299-6686-54d9-b015-fa67395355b5 | tickbox | i. Finish
b522fb61-afcb-571e-bf33-915efc435e9e | tickbox | ii.Levels
| checkpoint | Pour QA received including concrete dockets
| checklist | ITP Structure - Lift Pit |  | ITP Structure - Lift Pit |  | d22ba7ea-f017-4e3c-bf45-6a376e3c8ec7
| section | 1. Pre-start
| checkpoint | Clear work Area
| checkpoint | QA for sub-grade and relevant services received (if applicable)
| checkpoint | GL and datum provided
| checkpoint | Geotechnical Eng inspection report received and closed-out
| section | 2. Pre-pour
| checkpoint | Waterproof sign off/QA
92757ad1-c7d4-5289-93e1-b6ca644f4f95 | tickbox | i. DPM including tapes and laps
| checkpoint | Formwork signoff/QA
5c0b3054-469b-5a0e-852a-4dfcd210ec41 | tickbox | i. Check RL levels
484ccc91-c87a-5d5a-852a-6ff7ab5f7053 | tickbox | ii. Check Dimensions and alignment
e1fa039b-647d-5d68-bba0-cc1bf9ffdaa7 | tickbox | iii. Check form ties and propping
07fe1de6-af71-50d4-aa88-4dbb505d32ce | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
8e58b85f-60d0-5646-885f-7cfd1888f2d9 | tickbox | i. Details checked and shop drawings
9fdc42d8-3094-5449-b9ac-8a92ce69478a | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
e38adc7c-ab46-5e17-a5b8-78140768f6c8 | tickbox | iii. Check reinforcements size, spacing and cleanliness
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | 3. Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| section | 4. Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | 5. Post pour
| checkpoint | Checks
99706468-0534-5ca0-941b-8e2c2bc50909 | tickbox | i. Finish
1f07d691-ac0a-5ce2-a552-485cc3bdba43 | tickbox | ii. Levels
| checkpoint | Pour QA received including dockets
| checkpoint | Starters
| checkpoint | Pour QA received including dockets
| checklist | ITP Structure - Pre-cast Beams |  | ITP Structure - Pre-cast Beams |  | 51099cd6-4aac-48d6-8d06-67f04d1e2db0
| section | Pre-start
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| checkpoint | Propping onsite and in place
| section | Delivery Inspection
| checkpoint | Check for damage/defects on arrival
| checkpoint | Measurement checks in line w/ IFC dwg
| section | Installation
| checkpoint | Check alignment and leveling meet specs. before placement
| checkpoint | Ensure proper connection and anchoring
| checkpoint | Check positioning and orientation
| checkpoint | Structural Eng inspection report received and close-out
| section | Post installation
| checkpoint | Verify final positioning and alignment
| checkpoint | Check for damage to the beams
| checkpoint | Monitor and control grouting/backfilling processes
| checkpoint | Beam installation QA
| checklist | ITP Structure - shotcrete |  | ITP Structure - shotcrete |  | fe568e6f-031f-44b2-ad74-2beb40b09cfa
| section | Pre-start
| checkpoint | Review IFC dwgs
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | Check surface preparations (adjacent wall protection)
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
a053b812-1f9a-5567-891f-0856b5eb84b9 | tickbox | i. Details checked
0297003d-fcce-59ed-8be7-4876944fbc9c | tickbox | ii. Any CAN, Engr requirements
5a82d12c-dcaf-5106-b87e-fda684f23168 | tickbox | iii. Scabbling, support bars, reinforcement quality
3e5ecf69-6791-58ec-a4e5-9c43f2683c19 | tickbox | iv. Check reinforcements size, lapping, covers and starters
5a0ee8e1-8fec-5550-8b20-0e61e012f745 | tickbox | v. confirm waterstop
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/safety
| checkpoint | Access for sprayer/pump
| checkpoint | Safe access to all areas of spray
| section | Spray
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | shotcrete placement timing (within 90 mins)
| section | Post spray
| checkpoint | Checks
e52b6789-823d-5af1-b530-ec7c2ebf4452 | tickbox | i. Finish
dba42595-6eef-5ed9-bfc5-9adb4a7da99c | tickbox | ii. Levels
| checkpoint | Pour QA received including concrete dockets
| checklist | ITP Structure - Structural Steel - Column and Beams |  | ITP Structure - Structural Steel - Column and Beams |  | 0a17e8aa-8714-45cf-8930-c3656c254b63
| section | Pre-Start
| checkpoint | RL for support beams/ Plinth
| checkpoint | Plate support/ bolts surveyed and checked as built
| checkpoint | Slab QA received
| checkpoint | checked tolerances, packing space
| checkpoint | Area clean/clear for access equipment
| section | Safety
| checkpoint | review weights and lifting gears inspected
| checkpoint | taglines secured
| checkpoint | Work space demarcation
| section | Erection
| checkpoint | GN inspection
d5e46124-5087-5abb-a7e7-b9289c4e2258 | tickbox | i. Welds, bolts, plumb, alignment, etc. as per design
2062daf2-f74a-5bc5-b458-2ffc50f7d9d5 | tickbox | ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Post erection
| checkpoint | Propping where required
| checkpoint | Spot check RL’s and plumb
| checkpoint | Primer touch-ups
| checkpoint | Steel QA received
| checkpoint | Grout under columns
| checklist | ITP Structure - Suspended Slab |  | ITP Structure - Suspended Slab |  | 3cc12c14-c9fe-4949-8901-403ced61ee78
| section | Pre-start
| checkpoint | Beam/Precast/Steel QA/ signoff
| checkpoint | Edge protection in place
| checkpoint | Access provided
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | Propping sign-off/QA received
| checkpoint | Services marked out and double mesh
| checkpoint | Waterproofing sign-off/QA
1caa78bc-8ed9-557b-8f33-1ec4503824f2 | tickbox | i. DPM including tapes and laps
| checkpoint | Formwork signoff/QA
4b9b77da-c578-5a93-adee-3a3e1885bd45 | tickbox | i. Step down/ falls
855ba951-2aa7-5f5f-aa2a-8b0a785a5985 | tickbox | ii. Ties, propping, seal formworks
f3290555-49ca-5b51-8fcc-13585372ce5b | tickbox | iii. Seismic gap/expansion joints
| checkpoint | Reo sign-off/QA received
| checkpoint | GN inspection
a21af35b-d2f6-5044-94b3-f053e1cf4cb4 | tickbox | i. Details checked
2ed8943e-837f-5cf8-9056-06772db590c6 | tickbox | ii. Openings checked
17a02416-3245-5104-8fb5-04b101f39fab | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
9b619e67-ccb0-5e99-abc8-014d903de047 | tickbox | iv. Clean and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Finish
| checkpoint | Levels
| checkpoint | Curing agent and canvas protection (standby)
| checkpoint | Pour QA and dockets received
| checklist | ITP Structure - Suspended Slab - comflor |  | ITP Structure - Suspended Slab - comflor |  | bf23e088-91d7-4158-a380-84a33bacb782
| section | Pre-start
| checkpoint | Beam QA/ signoff
| checkpoint | Edge protection in place
| checkpoint | Access provided
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | Comflor sign-off/QA received
d3910e96-7c62-5bd0-b1e2-e015d3c01040 | tickbox | i. Stud testing completed
| checkpoint | Propping sign-off/QA received
| checkpoint | Services marked out and double mesh
| checkpoint | Formwork signoff/QA
82d8dbd1-2a07-57ad-8159-dad012c040e7 | tickbox | i. Step down/ falls
19f28f3b-ec5c-5841-84ac-a88deb13f20a | tickbox | ii. Ties, propping, seal formworks
| checkpoint | Reo sign-off/QA received
| checkpoint | GN inspection
d1542daf-d937-5502-a197-deb99b3d7e66 | tickbox | i. Details checked
22227eb9-bf7f-56e8-8da3-62a88b5829d4 | tickbox | ii. Openings checked
2f2e36ca-b90e-55e0-9539-6d4ecfdfb2af | tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
4a43084e-b270-544f-9f77-a82293ef9f96 | tickbox | iv. Clean and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Finish
| checkpoint | Levels
| checkpoint | Curing agent and canvas protection (standby)
| checkpoint | Pour QA and dockets received
| checklist | ITP Structure – Foundation (Crane base) |  | ITP Structure – Foundation (Crane base) |  | 26701de4-4e32-4d0c-b3e1-ebff14593646
| section | Pre-start
| checkpoint | Clear work Area
| checkpoint | QA for sub-grade and relevant services received
| checkpoint | GL and datum provided
| section | Pre-pour
| checkpoint | i. attached mark-up
| checkpoint | Formwork signoff/QA
caa5a581-0247-5ae3-a6ae-ba78c45bbfd4 | tickbox | i. Check RL levels and benchmarks
0d929532-cb83-5ce2-9c4a-99f84d97ad7e | tickbox | ii. Check Dimentions and alignment
2db0a076-be0b-5fe3-b3ff-f9bd5b82720e | tickbox | iii. Check form ties and propping
105cfc37-7d29-5a64-9bf9-6df0b7ab4b1b | tickbox | iv. Overall Cleanliness and Seals and ready to Pour
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
f7d80b5f-94df-5167-a34e-ca29973e1737 | tickbox | i. Details checked
b8e8bf08-9677-5afa-abb0-4bfa03dba012 | tickbox | ii. Scabbling, Starters/ embedment depth, cover checked
806dbf34-39b2-5a2b-a318-55c666bc54f2 | tickbox | iii. Check reinforcements size, spacing and cleanliness
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post pour
| checkpoint | Checks
9ab2fa7e-dbc3-5e17-ad7e-2852a62afc11 | textbox | i. Finish
0274814d-3ec3-5b97-8e1f-9f44841a5539 | textbox | ii. Levels
| checkpoint | Pour QA received including dockets
| checklist | QA - Toe Footings Checklist |  | Toe Footings |  | 315e1716-cf52-4aa5-a3d6-e5ed632c234e
| section | Pre-start
| checkpoint | Panel QA received
| checkpoint | GL and datum provided
| checkpoint | Backfill to foundation level completed
| checkpoint | Clean work area
| section | Pre-Pour
| checkpoint | Service trade sign off/QA
| checkpoint | Formwork signoff/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Photo of water bar installed (TBC if required)
| checkpoint | DPM where required
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
| checkpoint | Details checked
| checkpoint | Any CANs
| checkpoint | Starters, scabbling, cover checked
| checkpoint | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post Pour
| checkpoint | Finish
| checkpoint | Levels
| checkpoint | Starters
| checkpoint | Pour QA received including dockets
| checklist | Shotcrete |  | Shotcrete |  | b67a81cc-d62c-4f7b-baf9-97110bc0608e
| section | Pre-Check
| checkpoint | Upload drawings, detail /Mark up plan
| checkpoint | Check surface preparations (adjacent wall protection)
| checkpoint | Check for Clash
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
e17f1116-c3b1-592f-a9fc-5ba687779390 | tickbox | i. Details checked
b6bcd0ef-b0f3-52b9-8c63-631fbf5da9d2 | tickbox | ii. Any CAN, Engr requirements
40147bf3-7837-5dfd-ab62-17317835a3fb | tickbox | iii. Scabbling, support bars, reinforcement quality
8d334495-f3d8-5afe-9019-e69ccb613ee1 | tickbox | iv. Check reinforcements size, lapping, covers and starters
14e04bfe-e5ac-5181-a975-8bd0fd229f18 | tickbox | v. confirm waterstop
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Access/safety
| checkpoint | Access for sprayer/pump
| checkpoint | Safe access to all areas of spray
| section | Spray
| checkpoint | Confirm mix and test
| section | Post spray
| checkpoint | Checks
d002f88d-fbd8-5e82-b425-1eaa68af7032 | tickbox | i. Finish
1816daa7-45d3-5219-8834-d8735325ba67 | tickbox | ii. Levels
| checkpoint | Pour QA received including concrete dockets
| checklist | Structural Steel |  | Structural Steel |  | 0477c018-6e6c-4537-8106-d00607510b7e
| section | Pre-Start
| checkpoint | GL and datum provided
| checkpoint | Panel sign-off/QA received
| checkpoint | Slab QA received
| checkpoint | Area clean/clear for access equipment
| checkpoint | Any CAN, Engr requirements
| section | Erection
| checkpoint | GN inspection
9a69e85d-69aa-5d6d-b5d9-aec8a4c3061d | tickbox | Welds
914bfb02-e308-57f9-826f-cd832af9781e | tickbox | Bolts
e6e31638-59f9-5938-b041-99004963d4a2 | tickbox | Tensioning
e42e0477-975d-5519-9f35-3d20a40f0deb | tickbox | Spot check RL’s and plumb
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Propping where required
| section | Post Erection
| checkpoint | Primer touch-ups
| checkpoint | Steel QA received
| checkpoint | Grout under columns
| checklist | Structure – In Situ Concrete |  | Structure – In Situ Concrete |  | 5438386e-45fe-4a16-8fa7-0f0eb8198930
| section | Pre-start
| checkpoint | Toe footing sign-off/QA received
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| checkpoint | Formwork signoff/QA
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
f4afdd8a-c977-5bbd-b2ce-5603d1cb8cd5 | tickbox | Details checked
cf7a75f9-6ea0-5598-ae03-be89634b63a1 | tickbox | Starters, scabbling, cover checked
efc2b0ba-3b9a-5e7e-b881-f150eed948f2 | tickbox | Clean formwork and ready to pou
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Pour sequence mark-up
| section | Access/safety
| checkpoint | Access for sprayer/pump
| checkpoint | Check TA
| checkpoint | Safe access to all areas of spray
| checkpoint | Exposed reo capped
| section | Spray / Pour
| checkpoint | Confirm mix
| checkpoint | Confirm concrete is being tested (slump and cylinders)
| checkpoint | Weather recorded
| section | Post spray / pour
| checkpoint | Checks
ce5936fb-8e0e-5442-9801-fffd5c95e226 | tickbox | Finish
992922c9-907d-5778-9509-70522abec791 | tickbox | Levels
| checkpoint | Pour QA received including concrete dockets
| checklist | Structure – Pre-cast Panels |  | Structure – Pre-cast Panels |  | fae014ad-46b3-4504-a117-8a4187ad453e
| section | Pre-start
| checkpoint | PrePour PCP inspection done
| checkpoint | Timber guides installed – including spacers
| checkpoint | Deadmen on site and in position
| checkpoint | Check for clash
| checkpoint | Any CAN, Engr requirements
| section | Delivery & Install
| checkpoint | Check for damage/defects on arrival
| checkpoint | Props & propping bolts onsite
| checkpoint | Panels unloaded correctly
| checkpoint | Measure internal dimensions
| checkpoint | Panels Plumb & Flush
| checkpoint | Props Installed
| section | Grouting & Sealant
| checkpoint | Drypacking done
| checkpoint | Grouting pumped
| checkpoint | Sealed between panels
| section | Post Checks
| checkpoint | PCP supplier QA received
| checkpoint | Subs installation QA received
| checkpoint | Grouting, Drypacking & Sealing QA received
| checkpoint | Vertical check done
| checklist | Structure – Retaining Wall |  | Structure – Retaining Wall |  | 2b812d04-680a-4d7d-a098-f5d27f7be596
| section | Pre-start
| checkpoint | Foundation QA
| checkpoint | GL and datum provided
| checkpoint | Check starters
| checkpoint | Clean work area
| checkpoint | Confirm expansion joints
| section | During works
| checkpoint | Check reo details
| checkpoint | Expansion joints
| checkpoint | Bottom clean-outs for inspection
| checkpoint | Check set-out
| checkpoint | Pointing of joints
| section | Pre-pour (blocks infill)
| checkpoint | Reo sign off/QA
| checkpoint | GN inspection
1733e04a-f19f-5584-a5a9-7eb75ff06c37 | tickbox | Details checked
d8c18b7e-707b-5a67-afe9-58da36c6cba6 | tickbox | Any CANs
982c83d1-b708-5ac3-b00c-ed885b316b9b | tickbox | Starters, cover checked
f8b24e9c-b2d0-5f99-a8cd-42c63a3a96da | tickbox | Clean-outs free of debris and ready to inspect/pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Form work and clean-out covers in place
| checkpoint | Pour sequence mark-up
| checkpoint | Max 2.4m lifts
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Post pour
| checkpoint | Checks
27c6c37a-5ec7-5664-87ab-a652d1114885 | tickbox | Finish
034ad420-9149-5e49-b324-c847c9642e0e | tickbox | Levels
32270be0-e164-556a-93f8-2b51de5a11b4 | tickbox | Starters
| checkpoint | Block and pour QA received
| checklist | Structure – Slab on Grade |  | Structure – Slab on Grade |  | fbec105e-50ce-4b67-99ec-cd0d3fc19cfd
| section | Pre Start
| checkpoint | Subgrade sign-off/QA received
920bc35f-d666-5dbf-86e8-a97fd4b59177 | tickbox | Backfill and blinding
| checkpoint | GL and datum provided
| checkpoint | Clean work area
| section | Pre-Pour
| checkpoint | Civil works completed and signed off
| checkpoint | Waterproofing sign-off/QA
9b821986-1f19-5864-afe6-2391d16f3a8d | tickbox | DPM including tapes and laps
34fe5df3-7b48-530e-bdfb-4155a4e61fed | tickbox | Waterstop where applicable
| checkpoint | Formwork signoff/QA
| checkpoint | GN inspection- Prepour
b540d169-596c-5b0d-a603-c52370d5f225 | tickbox | Reo details checked
8841750a-2cce-55f1-96cc-16bc1d2cbae2 | tickbox | Any CAN, Engr requirements
d5de0619-d849-506e-881e-9331423cbc37 | tickbox | Starters, scabbling, cover checked
435eb7d8-eb8f-5bd9-953d-ac4092576598 | tickbox | Check for clash
eeb91ea3-1781-5014-b095-325112390032 | tickbox | Clean formwork and ready to pour
| checkpoint | Stop-End check
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Upload drawings, detail /Mark up plan
| section | Access/safety/protection
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| checkpoint | Panel and steel protection
| section | Pour
| checkpoint | Confirm mix & test
| checkpoint | Confirm Finish
| checkpoint | Levels Checked
| section | Post pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Saw cuts within 24h of pour and slurry removing
| checkpoint | Pour QA received
| checklist | Structure – Structural Steel - Roof, Mezzanine & Shopfront |  | Structure – Structural Steel - Roof, Mezzanine & Shopfront |  | 20ab7197-068e-4285-9dcf-b94a9cc9f84c
| section | Pre-Start
| checkpoint | Panel sign-off/QA received
| checkpoint | Check shopfront opening with Lancom - Key members location
| checkpoint | Slab QA received (not required for roof steel install)
| checkpoint | GL and datum provided
| checkpoint | Area clean/clear for access equipment
| section | Erection
| checkpoint | GN inspection
00ed825a-c6f5-5270-bf27-1e7703c2fc11 | tickbox | Welds, bolts, tensioning, etc. as per design
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| section | Post Erection
| checkpoint | Propping where required
| checkpoint | Spot check RL’s and plumb
| checkpoint | Primer touch-ups
| checkpoint | Steel QA received
| checkpoint | Grout under columns
| checklist | Structure – Suspended Slab |  | Structure – Suspended Slab |  | c2e733ab-4fee-49b2-b526-f172cf2df727
| section | Pre-Check
| checkpoint | Structural Steel sign-off for TT/ comflor install
| checkpoint | PCP wall installation sign-off/QA received
| checkpoint | Services sign-off/QA received
f90b520e-5359-5c06-93e8-c26208810539 | tickbox | Electrical
99dbef99-587b-580f-a6af-f7d77645737a | tickbox | Fire
85695f0f-aaf4-5399-8774-5d677d5289ed | tickbox | Hydraulic
2d259985-4707-5933-8546-1f08542568d1 | tickbox | Comms and Fibre
| checkpoint | GL and datum provided
| checkpoint | Double Tee QA/ inspection done and signed off
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | Double Tee's checked on arrival & installed
| checkpoint | Comflor laid and Studs welded
| checkpoint | Formwork/Edge Trim installed
e7b40caf-8f42-5907-ad24-d6daf16f0b7e | tickbox | Service penetration marked & sealed
| checkpoint | GN inspection- Prepour
c1ea84d2-d018-5f05-81da-0d6073cb1bc1 | tickbox | Reo details checked
f398323f-c24d-5ea5-bb87-0446afbb8b2c | tickbox | Any CAN, Engr requirements
2e3f3436-1c52-59f3-b1e6-bd8b44e8d19f | tickbox | Starters, scabbling, cover checked
0438ade7-61b1-5182-9fc6-b506720ea07b | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| checkpoint | Panel and steel protection
| section | Pour
| checkpoint | Confirm mix & test
| checkpoint | Confirm Finish
| checkpoint | Levels Checked
| section | Post pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Saw cuts within 24h of pour and slurry removing
| checkpoint | Pour QA received