## Structure
Id | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 | Tier 1: Footings | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e

## Checklists
Id | Location | Checklist Name | Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Passed | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings

## Checkpoints
Checklist Id | Location | Checklist Name | Section Name | Checkpoint Name | Checkpoint Status | Signoff Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-start | GL and datum provided | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-start | Geotechnical Eng subgrade inspection report received and closed-out | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-start | Check for clash | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-start | Upload drawings, detail /Mark up plan | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Service trade sign off/QA | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Waterproof sign off/QA | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Formwork signoff/QA | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Check levels | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | GN inspection- Prepour | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Structural Eng inspection report received and close-out | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Council inspection report received and close-out | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Stop-End checked | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pre-Pour | Pour sequence mark-up | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Access/Safety | Clear access for trucks/pump | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Access/Safety | Exposed reo capped | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Access/Safety | Safe access to all areas of pour | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pour | Concrete Dockets and test report received | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pour | Curing agent | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings
cl:38b0271a-38f6-4cce-b9d9-23420ba35774 |  | Footings | Pour | Pour QA received | Passed |  | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e | Tier 1: Footings

## Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
ac50d2dc-3697-420e-9ddb-9b487abb0f3f | checklist | Footings |  | Footings | 0 | 03df9a4d-289c-40ca-94c7-3818f40e1645
e3fd7d6b-de91-4d5c-886c-89c4f888da79 | section | Pre-start
f3f1f504-0ab7-43c2-a7e6-c9f8c5cb260c | checkpoint | GL and datum provided
91cd82ea-95d7-4517-80d3-481cc99a8d26 | checkpoint | Geotechnical Eng subgrade inspection report received and closed-out
0fff6910-f538-4c1a-98e7-56108511ac86 | checkpoint | Check for clash
be0c8fd5-5c4c-4a5a-ac3e-51a4814548af | checkpoint | Upload drawings, detail /Mark up plan
ec0e13e4-cc4c-411a-a21f-7115024d73cb | section | Pre-Pour
4cadd912-2642-4b42-8cea-1877bb375db5 | checkpoint | Service trade sign off/QA
5209afc6-8b30-4394-87bd-f011cba32bfc | checkpoint | Waterproof sign off/QA
7caf3bc3-5943-4104-a0da-099d95d2b84d | checkpoint | Formwork signoff/QA
97156b33-751f-4009-8d5a-3cd49661fff5 | checkpoint | Check levels
068b2050-9e48-4272-8660-12e6e3bb48c1 | checkpoint | GN inspection- Prepour
584da06d-898d-523c-b9f4-22a18cbc177b | tickbox | Reo details checked
f7bd4f24-eb8c-5624-b00a-362ef018334b | tickbox | Drawings UpToDate, check for CAN’s
74cbf223-aa2a-5067-a82a-359ef2f7a809 | tickbox | Starters, scabbling, cover checked
53503008-e82f-5299-ab6d-bed590ee638f | tickbox | Clean formwork and ready to pour
018ed17e-140a-428a-81c4-ef95136e68a7 | checkpoint | Structural Eng inspection report received and close-out
af1a0b3c-03ab-4d06-8644-a5cd5c74864e | checkpoint | Council inspection report received and close-out
fbf2b076-9dbd-4d17-ae70-ebb5a3ff8fc1 | checkpoint | Stop-End checked
5c7eb242-c1be-475a-9690-60d452837f5e | checkpoint | Pour sequence mark-up
bc545227-6a4c-4e05-9670-85e176cb4387 | section | Access/Safety
33fe267c-a0a0-4c7d-a0b3-78df8dafcee3 | checkpoint | Clear access for trucks/pump
04442fb1-8fe8-425b-a5f2-288f2250eab6 | checkpoint | Exposed reo capped
ffd9101e-a7bc-4114-82f9-33a574508469 | checkpoint | Safe access to all areas of pour
0919157f-c5fe-447e-86e0-fbaeaa0ee14c | section | Pour
ccc5ad0a-02f0-4130-b0c6-3bc8317a7913 | checkpoint | Concrete Dockets and test report received
2907ca3a-d8f9-4b05-8796-33c3e251b8b1 | checkpoint | Curing agent
a8f19c41-c9b9-4c65-a6b6-216d882a5446 | checkpoint | Pour QA received
| checklist |  |  |  | 1 | 03cc377ab361cd9bfed4355ef3e15cd588391d0986fef581c586ac2b68d8db0e
| section | Pre-start
| checkpoint | GL and datum provided
| checkpoint | Geotechnical Eng subgrade inspection report received and closed-out
| checkpoint | Check for clash
| checkpoint | Upload drawings, detail /Mark up plan
| section | Pre-Pour
| checkpoint | Service trade sign off/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Formwork signoff/QA
| checkpoint | Check levels
| checkpoint | GN inspection- Prepour
584da06d-898d-523c-b9f4-22a18cbc177b | tickbox | Reo details checked
f7bd4f24-eb8c-5624-b00a-362ef018334b | tickbox | CAN's
74cbf223-aa2a-5067-a82a-359ef2f7a809 | tickbox | Starters, scabbling, cover checked
53503008-e82f-5299-ab6d-bed590ee638f | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Stop-End checked
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Pour QA received