## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Structure – Suspended Slab |  | Structure – Suspended Slab |  | c2e733ab-4fee-49b2-b526-f172cf2df727
| section | Pre-Check
| checkpoint | Structural Steel sign-off for TT/ comflor install
| checkpoint | PCP wall installation sign-off/QA received
| checkpoint | Services sign-off/QA received
f90b520e-5359-5c06-93e8-c26208810539 | tickbox | Electrical
99dbef99-587b-580f-a6af-f7d77645737a | tickbox | Fire
85695f0f-aaf4-5399-8774-5d677d5289ed | tickbox | Hydraulic
2d259985-4707-5933-8546-1f08542568d1 | tickbox | Comms and Fibre
| checkpoint | GL and datum provided
| checkpoint | Double Tee QA/ inspection done and signed off
| checkpoint | Clean work area
| section | Pre-pour
| checkpoint | Double Tee's checked on arrival & installed
| checkpoint | Comflor laid and Studs welded
| checkpoint | Formwork/Edge Trim installed
e7b40caf-8f42-5907-ad24-d6daf16f0b7e | tickbox | Service penetration marked & sealed
| checkpoint | GN inspection- Prepour
c1ea84d2-d018-5f05-81da-0d6073cb1bc1 | tickbox | Reo details checked
f398323f-c24d-5ea5-bb87-0446afbb8b2c | tickbox | Drawings UpToDate, check for CAN’s
2e3f3436-1c52-59f3-b1e6-bd8b44e8d19f | tickbox | Starters, scabbling, cover checked
0438ade7-61b1-5182-9fc6-b506720ea07b | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Safe access to all areas of pour
| checkpoint | Panel and steel protection
| section | Pour
| checkpoint | Confirm mix & test
| checkpoint | Confirm Finish
| checkpoint | Levels Checked
| section | Post pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Saw cuts within 24h of pour and slurry removing
| checkpoint | Pour QA received
| checklist | Footings |  | Footings |  | 03df9a4d-289c-40ca-94c7-3818f40e1645
| section | Pre-start
| checkpoint | GL and datum provided
| checkpoint | Geotechnical Eng subgrade inspection report received and closed-out
| checkpoint | Check for clash
| checkpoint | Upload drawings, detail /Mark up plan
| section | Pre-Pour
| checkpoint | Service trade sign off/QA
| checkpoint | Waterproof sign off/QA
| checkpoint | Formwork signoff/QA
| checkpoint | Check levels
| checkpoint | GN inspection- Prepour
584da06d-898d-523c-b9f4-22a18cbc177b | tickbox | Reo details checked
f7bd4f24-eb8c-5624-b00a-362ef018334b | tickbox | Drawings UpToDate, check for CAN’s
74cbf223-aa2a-5067-a82a-359ef2f7a809 | tickbox | Starters, scabbling, cover checked
53503008-e82f-5299-ab6d-bed590ee638f | tickbox | Clean formwork and ready to pour
| checkpoint | Structural Eng inspection report received and close-out
| checkpoint | Council inspection report received and close-out
| checkpoint | Stop-End checked
| checkpoint | Pour sequence mark-up
| section | Access/Safety
| checkpoint | Clear access for trucks/pump
| checkpoint | Exposed reo capped
| checkpoint | Safe access to all areas of pour
| section | Pour
| checkpoint | Concrete Dockets and test report received
| checkpoint | Curing agent
| checkpoint | Pour QA received