## Checklist Templates
Id | Type | Name | Values | Prompting Name
a79d5182-4b77-453e-aa8c-6f16f5f695ad | checklist | Add Pre Start Meeting Checklist |  | Pre Start Meeting
2bcda5fd-e342-46c6-9d75-1ca983557bf6 | checkpoint | Details
108d9c54-fa00-58d9-aad6-55a00435e049 | textbox | Conducted by
11f7eced-d7c4-5634-9a5b-42f40edbf45b | textbox | Area
2a772b97-a2e6-407f-ac1c-352712648302 | checkpoint | Any Safety Concerns from last meeting - add comments if required
68b55c49-bcfc-5353-b223-3ea6c2bbb94c | textbox | Today's weather
ff44e96d-6d1d-57ad-905b-ae776dc13388 | textbox | Today's work is
82614f96-d108-5771-ab4d-517bc6edebe9 | textbox | Newly Identified Hazards Are
0285b4c0-52cd-543e-9c11-6619e7279637 | textbox | Control measures are
cc4ab476-a5fd-452c-9d61-7beb3f3b485e | checkpoint | Scope of work for the day was discussed and understood
27f95047-d008-45ce-ac8f-1522c08a3214 | checkpoint | Major High Risk Activities are understood and controlled in a SWMS
1b535f32-f037-4929-b81f-a3ea2a3f0a0a | checkpoint | Relevant SWMS were reviewed, understood and signed by all workers
27f0b807-bea5-4dd2-a088-c840880ca08e | checkpoint | Relevant Permits to Work are in place and understood
f63cc9d6-0565-4af1-9229-148bdbc6c3b3 | checkpoint | Tools and equipment are in good working order
22dda3f1-b6af-40dd-822c-b61355ae23ec | checkpoint | All electrical equipment displays current test tags
bdf7bf5f-a9b8-4c6c-9130-0cdedfe05ddd | checkpoint | Appropriate PPE for tasks is understood and available
b2a04cc9-de5d-41ea-a7a3-7944cbe44b25 | checkpoint | Housekeeping and clean-up has been discussed and is understood
8bb10d80-163b-5f69-bb6f-caca3f26139e | tickbox | David Interligi
ec73d7df-388f-59f0-a2c7-1e243e52ac28 | tickbox | Michael Borg
917c3df5-0a15-53d4-95f3-fc073c5919c4 | tickbox | Rob Pellegrino
6fb2ddfc-a104-5f1c-a2c4-8eb13d082fd3 | tickbox | Adrian Sibbing
447990f2-a013-5b7f-b6a7-5d6eabdf724b | tickbox | John Wolosz
a8c1cdd2-7ab8-5da5-a1d3-bd7614a0a4db | tickbox | Lochy Brannelly
8388cee1-2dbe-5fa3-a3c0-7ea71429b08f | tickbox | Damon Guy
95076296-e4b4-5521-84a0-1515b90d463f | tickbox | Jake Condon
0a10a9af-0730-5f8c-91b0-5bda05a74329 | tickbox | Julian Cannata
355b6eb0-45c2-5194-bc72-3d7c2a3d4521 | tickbox | Devilliers Duvenage
41f83a5d-ec84-5a4d-8f53-c1cd532fee3d | tickbox | David Currie
b6eae548-8509-554e-9e1f-5b27a8e36ee5 | tickbox | Steve Price
79a176fe-5859-4023-a0ad-5027fc7f7424 | checkpoint | Signed off by Supervisor
e505717a-25ea-4a3f-adb6-feba9e65f6b1 | checklist | Apprentice Contract of employment |  | Apprentice Contract of employment
e7732d71-6869-4b0e-a903-185684fbe6d0 | checkpoint | Attach Document
43840691-3640-42d7-81f1-4e45c6824dbc | checklist | Documents |  | Documents
0d32b920-3b40-4aac-aa40-13e45a1c0c35 | checkpoint | Attach Document
7085805e-42f9-4474-a336-773714ef10a4 | checklist | Drawings / Documents |  | Drawings / Documents
571c2731-68da-4b3a-8f3c-1b8846d05b5c | checkpoint | Attach Drawings / Document
bd6d83ca-8f35-4ed7-935a-b807bec739e6 | checklist | ITP No. 07 - Structured Cabling Rough In |  | ITP No. 07 - Structured Cabling Rough In
20a3eb16-146a-4a4d-962c-f4758c3623b5 | checkpoint-no-value | DRAWINGS AND SPECIFICATION
37fefb0b-686a-51a4-8fb2-5d3ead916375 | note | REFER APPROVED DRAWINGS AND SPECIFICATION.
ba526e23-3196-40c3-bce5-4fed81c973f5 | checkpoint | INSTALL CABLE SUPPORT OR CONDUIT WHERE REQUIRED.
338fa167-dc62-4f09-9aea-ec69033c4764 | checkpoint | VERIFY CORRECT CABLE TYPE.
34e11497-d461-494b-b902-c1a56f5e41f2 | checkpoint | REFER TO APPROVED DRAWINGS FOR CABLE NUMBERING SEQUENCE RELEVANT TO FINAL FIT OFF SEQUENCE & RECORD
a588913a-fb1c-41f2-a742-10f468db5c32 | checkpoint | INSTALL CABLE WITHIN OR ON CABLE SUPPORT SYSTEMS MAINTAINING MIN SEGREGATIONS, ENSURE VELCRO CABLE TIES ARE USED AS PER SPECIFICATION
82a43b15-70bf-4bb6-831a-89ffda393a3c | checkpoint | FORM CABLES INTO RELEVANT FIT-OFF GROUPS AT THE CABINET END.
2fd8493f-71fc-4ed6-81a1-06ab3137c6cc | checklist | ITP No. 08 - STRUCTURED CABLING FIT OFF |  | ITP No. 08 - STRUCTURED CABLING FIT OFF
2fb62b20-38a8-4bcf-ba0c-92bf775175ce | checkpoint | VISUAL CHECK ENSURING CABLE TO BE FITTED OFF IN CORRECT POSITION.
fc71581c-d2f8-4cd3-9aec-aaf6c22f78c5 | checkpoint | SELECTION OF CORRECT TOOL TO BE USED FOR TERMINATION TYPE.
2db76069-0072-4a05-9638-5c17694195bb | checkpoint | ENSURE CABLES ARE STRIPPED NO MORE THAN THE SPECIFIED DISTANCE. CHECK TERMINATIONS AT COMPLETION FOR COLOUR CODE AND SEQUENCE.
73fd8de4-4603-46ee-ab16-ecf32f7bb2c5 | checkpoint | ATTACH WRAP AROUND LABEL TO CABLE NO MORE THAN 60MM FROM THE JACK. ENSURING CORRECT NUMBER SEQUENCE.
e3578cd5-48d6-4955-8fa4-86d1429dce7f | checkpoint | DRESS CABLES TO FINAL LOCATION. ENSURE VELCRO STRAPS FOR CAT 6 CABLING
81509bef-12de-419b-b9c9-2360141c853d | checkpoint | INSTALL JACK INTO WORKSTATION OR WALL OUTLET.
b0670256-ca03-4a57-a023-f08a46956db4 | checkpoint | INSTALL PATCH PANEL INTO CABINET LOOM CABLES TO THE BACK OF THE PATCH PANEL. TIE INTO POSITION USING VELCRO STRIP AND/OR CABLE TIES SUPPLIED.
9737738f-39f0-4927-967e-e9269e8130e1 | checkpoint | PATCH OUTLETS TO HARDWARE DEVICES WHERE APPLICABLE AND CHECK FOR CORRECT OPERATION.
a0d960a4-c3e7-48d2-8685-854ee480e572 | checkpoint | LABEL OUTLET ENSURING CORRECT NUMBER SEQUENCE
9a828025-5977-4d64-a4f4-0dc13ac439d1 | checkpoint | COMPLETE CERTIFICATION AS REQUIRED
b34c02ed-68de-492b-b857-a966db5c2fb1 | checklist | ITP No. 09 - STRUCTURED CABLING TESTING CERTIFIED SYSTEM |  | ITP No. 09 - STRUCTURED CABLING TESTING CERTIFIED SYSTEM
975866ea-3337-4d6b-aff7-0e9eac28fd12 | checkpoint | REFER TO INSTALLED DRAWINGS
e97fbbb7-9125-48b0-946d-5286bab77096 | checkpoint | test terminations using COPPER STRUCTURED CABLING tester AND LOG RESULTS
f12c2b05-44ff-4a82-b74f-8dae96594be9 | checkpoint | RECTIFY ANY FAILED RESULTS, RE-TEST AND LOG
8428f47b-7fc2-4de4-aa7e-dfb3770443f2 | checkpoint | LABEL FRAMES AND PATCH PANELS
626f0689-7b65-4ffc-a4e3-39b884fce281 | checkpoint | COMPLETE PATCH PANEL SCHEDULE
d1ba025d-d723-4130-b6bb-7cab7a54276b | checkpoint | DOWNLOAD RESULTS FROM TESTER TO PROJECT FOLDER
34ad9634-46f9-4969-aeb5-99495782bf87 | checklist | ITP No. 13 - SUB-CIRCUIT CABLING FIT OFF |  | ITP No. 13 - SUB-CIRCUIT CABLING FIT OFF
fafb2efb-7486-48b6-ac9c-a9cabeef1214 | checkpoint | COMPLETE WALL OR CEILING CUT OUT WHERE REQUIRED
ba8b9a38-7a1c-4dd9-a4fb-adea558301f8 | checkpoint | TEST & ENSURE SUB CIRCUIT CABLING IS NOT LIVE PRIOR TO FIT OFF
db95970d-13cc-4f9f-baf7-9b3c8824f220 | checkpoint | TERMINATE CABLE TO OUTLET OR PLUG BASE, CHECK CORRECT CONNECTIONS AND FIX TO SURFACE, IF CIRCUIT CAN NOT BE FULLY TERMINATED A JUNCTION BOX MUST BE INSTALLED WHERE REQUIRED
4179048d-0073-439e-999a-99b01c1d3dc4 | checkpoint | CLEAN AREA AS REQUIRED
fecf365f-e41b-4d77-b751-099afdd480e8 | checkpoint | RECORD ANY RELEVANT INFORMATION ON DRAWINGS.
5efa3b1a-0595-45c6-8198-f18d81fb3a00 | checklist | ITP No. 14 - Construction Wiring, Installation, Test and Tag & Removal |  | ITP No. 14 - Construction Wiring, Installation, Test and Tag & Removal
09ad02e6-ea76-452e-b3be-6927b3ed3861 | checkpoint | Area accessible & ready
4bad160c-d118-403e-8122-93661141452e | checkpoint | Refer to temporary wiring setout plan
ec172ecb-e839-5127-9204-037dbed6914b | note | CABLING MUST BE SUPPORTED AND PROTECTED FROM DAMAGE. CONSTRUCTION WIRING TAPE MUST BE FITTED AT EVERY 5 METRES. TEMPORARY WIRING MUST NOT BE INSTALLED WITH PERMANENT CABLING
b95b06e7-d31f-48ed-b648-a008e8651ae2 | checkpoint | Fit off plug base and or powerpoint/isolator
6ed52689-e700-40de-a3ec-995609460cd4 | checkpoint | Install light fitting, exit/emg, power
20d060f2-499e-40fa-a321-c24fa4136036 | checkpoint | Terminate cable to temp board. Ensure temp board is isolated! Test Test Test
fa965bd4-7143-4ea7-abc2-6d66a2afe403 | checkpoint | Test & commission
59062c43-aec6-559a-8f59-f2da854213f1 | note | Lodge non prescribed certificate of electrical safety
f20b557d-ed1c-4523-80ae-61fcb66c278e | checklist | ITP No. 16 - EXIT & EMERGENCY INSTALLATION & TESTING |  | ITP No. 16 - EXIT & EMERGENCY INSTALLATION & TESTING
0385e491-50e8-4369-b851-a635b4aba508 | checkpoint | DELIVERY CHECK FOR DAMAGE AND CORRECT QUANTITIES
fba6b52d-3b5f-431c-a122-4aaadb7be30e | checkpoint | COORDINATE LOCATIONS WITH OTHER SERVICES
b780ed81-6242-458a-b5b7-1db289a7a1b4 | checkpoint | MARKING OUT (IF REQUIRED) REFER TO DRAWINGS FOR LOCATIONS
2a8088b6-7b3c-44a3-95d7-740853f6d552 | checkpoint | PLUG IN OR FIT OFF LIGHT, FIT OFF DATA CABLE IF REQUIRED
bb19977d-2e70-4001-b929-0ab024689f4e | checkpoint | INSTALL LAMP & DIFFUSER AND CLEAN FITTING
c854deb1-d0f5-4f11-b7d4-1c91f6446828 | checkpoint | INSTALL EMERGENCY BARCODE TO FITTING AND TO DRAWINGS (IF REQUIRED) OR,
15c7e9f1-0b6b-4d7f-8c74-364b8ff85cf1 | checkpoint | NUMBER FITTINGS AS PER VAST SHOP DRAWINGS.
2882fce1-4052-4d9a-8d5b-407d9af08990 | checkpoint | UPDATE ANY CHANGES FOR AS BUILTS
c272477e-1f5c-4c2e-b5a8-4b9f73314461 | checkpoint | COMPLETE LOG BOOK
ce254f02-3b5a-401d-bb93-cd6ed9633d59 | checkpoint | COMPLETE INITIAL 2 HOUR TEST
db0a4530-2e5c-447c-9c50-0b84ab7a62af | checkpoint | RECORD RESULTS
35d22421-c4da-4906-97a4-eef451f6b667 | checklist | ITP No. 19 - Installation of Temporary Power Board |  | ITP No. 19 - Installation of Temporary Power Board
31ca0e13-3207-4a00-b17e-72ba9b714e3d | checkpoint | Area accessible & ready
af10d653-05cf-46fc-a622-ad4a8f7d5301 | checkpoint | Locate & fix into position, bolt temporary board down with at least 2 fixings
04cb07ea-c571-477b-b42d-4eac18afdfcd | checkpoint | Install submains cabling as appropriate eg: glands/tray/duct
5112153e-408e-4f86-a7ba-1f8bf3358fd2 | checkpoint | Install lugs and terminate
cc9d5148-17d5-4d4e-9fc0-d38cd40f3904 | checkpoint | Any cables not terminated prior to energisation must be removed from cubicle at origin and have ends covered in heat shrink. At destination cables must be covered in heat shrink and be contrained in a junction box
521d2919-7471-4a1b-a012-e3c0ad8d3477 | checkpoint | Clearly identify services
b454c25e-3dac-4428-a1c6-121442b97724 | checkpoint | When ready to energise proceed in accordance with energisation procedure
c0ff9f1f-91ca-40c2-9464-df63f6f8a5ba | checkpoint | Energise & record results on Vast RCD test sheet
1ba90963-21e4-4b51-a7e4-32b8a4191aa1 | checkpoint | Install A3 laminated sign on face of temp board with floor plan and where the board is fed from
d8a869d2-ecaa-4c5a-b655-0781a36157ab | checkpoint | Update Temporary Power Board register & save to project folder/design control/temp const.
464683fd-f13c-5876-8225-943b63e808ae | note | Lodge non prescribed certificate of electrical safety
6870efd7-8ee2-5215-8553-de177125dc95 | note | RCBO'S must be fully tested initially and then tested every month with results recorded and c/b’s labelled
297f0b9e-fe3f-4fcf-bac5-dd776f0c8a06 | checklist | ITP No. 20 - Decommission Temporary Power Board |  | ITP No. 20 - Decommission Temporary Power Board
7153f6de-8c68-4326-9aa1-d66b54f1d7cc | checkpoint | Determine what the temporary board is controlling and confirm what action is required before board can be decommissioned.
62d4567c-c90d-5ece-8772-fb894ddc849e | note | De-commission form issued to builder, 48 hours notice to be given
fb05b4ed-1b26-4fc4-a7c9-5ab1b8619cc9 | checkpoint | Sign off builders checklist
09c570ca-55f7-4c0d-ab8a-309b8a53bb83 | checkpoint | Safety Committee Inspection
219ae6b5-60b5-4183-9208-467d9c0e7e9c | checkpoint | Final approval to be given by builder
90e1ada9-2fbf-45e3-ac4c-ccfa2d3e57e4 | checkpoint | Perform voltage test to ensure power supply has been isolated
ca38936f-5029-4d85-8f81-ebe3e83814dc | checkpoint | Disconnect supply cables
08fde8a0-a973-42d8-90b5-90b1c8457d3b | checkpoint | Fire sealing of penetrations
9f5b1e43-325d-4212-9b27-0c624de78fef | checkpoint | Remove temporary board
57560635-eb5c-4774-b645-753bc54bd64c | checkpoint | Update temporary power board register
328fa057-a5e5-4a3f-8194-962c355df084 | checklist | ITP No. 29 - Installion of Electrical & Communication Pits |  | ITP No. 29 - Installion of Electrical & Communication Pits
839a7f3f-e7c2-4366-9304-12d2703c85a4 | checkpoint | Inspect pits for any damage on arrival to site
fb83ecde-0ebf-448b-be3b-5ce9bf77ed02 | checkpoint | Mark out pit locations and alignment/arrangement
c33329c6-abf0-423b-8541-590f3f5455b5 | checkpoint | Check finished heights of pits against civil drawings/finished floor height
168d6c5b-36fd-4e76-b800-a50bea613726 | checkpoint | Erect pedestrian barricading
86763822-00dd-4671-a00a-0645d6b1836f | checkpoint | Excavate ground around pits as required
47401818-cf9a-4e96-a625-be902ecdbc8c | checkpoint | Place bedding material as per pit installation requirements
a9f36b64-6b04-4c8c-876f-ea74abf7c1b7 | checkpoint | Cut out pit entry as required
aadce7ec-722e-4887-bb7c-6b49fd466e8e | checkpoint | Install puts in ground (using correct lifting equipment)
733cacd9-91dd-48d1-a8dd-4cb148849856 | checkpoint | Check finished heights of pits against civil drawings
8bab7132-58ea-425d-b986-3aaedb1ba7d7 | checkpoint | Install relevant conduits
4f3338bf-4106-46c5-ae9b-3ef465658138 | checkpoint | Backfill and reinstatement of ground
2d03415b-54cf-449d-8eeb-f72b3e2e6278 | checkpoint | Check stabilised FCR backfill 200mm below proposed road level, compacted FCR above that
672845dc-9077-43ce-9540-79c941140317 | checklist | ITR No. 02 - Cutout of Ceilings & Walls |  | ITR No. 02 - Cutout of Ceilings & Walls
46c1f944-3dc6-4ee9-9502-96b599c11acb | checkpoint | Confirm sizes off all fittings prior to cut out
36d31b39-7df8-4131-ab34-1b28f5bb82b4 | checkpoint | Cut out for all sensors, light fittings
d8d9e204-01a5-4c02-ba93-ee951147db2f | checkpoint | Cut out smoke detectors
75a305c6-55c2-4ad6-9777-dc48b7b4127a | checkpoint | Cut out kitchen to kitchen plan
29e7fe67-a054-4ef8-b37e-c1f6d16d1c2c | checkpoint | Cut out switches, GPO's
da99a89f-34ce-4663-af8c-d6c60e927375 | checkpoint | Cut out Bathroom and Study Led Strips Fig 8
caa56542-593b-40ba-b9fb-d1eb9cb83e66 | checkpoint | Ensure AC isolator is in correct position
82a8dfd5-fcc4-4568-87da-9c82b725f055 | checkpoint | Ensure Wall light is in correct position
82540e80-e002-4f1a-bbf3-d40c91b8545d | checkpoint | Ensure kitchen outlets are in correct position (where applicable)
0ab78d8d-bd28-4f95-8ede-394273c90fa5 | checkpoint | Locate all cables ( including Smoke Detectors & Pendants )
6e202f8e-d6a8-4208-bdfd-24bd367d51f6 | checkpoint | Install Fire Boxes and hit all 4 tabs in
fe54592c-8a86-4f54-9f22-ab7b7097a5a4 | checkpoint | Fire caulk kitchen cables ( if applicable )
c614463c-907d-4a1a-9f5f-7f3471c746f7 | checklist | ITR No. 05 - Rough in |  | ITR No. 05 - Rough in
5afd74fa-5745-4ae5-86f9-04cb328201c0 | checkpoint | Area clear, tidy and accessible
296eae97-dd65-4d03-9125-e677d7a6ddc8 | checkpoint | Rough in of all lighting circuits- inc Emg/Exits and sensors
e90dd9fa-c64c-4814-a3ef-925591781829 | checkpoint | Rough in of all external lights
27693a88-2e4c-4702-b040-34ef10fefdab | checkpoint | Rough in of all power circuits
c566eb6d-5da4-46e3-ac7a-8dac9bf7e323 | checkpoint | Check for clashes with other services
968abc8b-4766-474b-86a6-28c6e2e22d58 | checkpoint | Level fire caulked by contractor
fdc99e90-6dc8-491b-a6f0-aa0908fe064d | checkpoint | Ensure area is left clean
30079d87-dfe9-4151-b783-0ca8f9e451ea | checklist | ITR No. 7 - Ground Fit Off |  | ITR No. 7 - Ground Fit Off
dd5b63dd-7969-4b5f-bc43-05c9daf96534 | checkpoint | Area clear, tidy and accessible
e932541e-c1c6-4bc3-8281-cc2afb0a65a5 | checkpoint | Ensure danger tags have up to date contact & isolation details
b9eef6fb-7079-4e7a-9c0e-1c6956573591 | checkpoint | LOCK OFF & TAG circuits that require isolation (Ensure key is with supervisor)
771f595f-c55f-4260-8a37-336994263619 | checkpoint | Test circuits to ensure they are isolated
5f654857-95bb-41c8-b8f8-a2a38167b0c4 | checkpoint | Area clear, tidy and accessible
b48f0550-2fad-4184-8b7d-d90564aa226f | checkpoint | Fit off all Lights
79da0b68-9984-4589-b53f-a3fdb549356c | checkpoint | Fit off of 4 pin plug
5b549223-ed2b-48fe-b6d6-6a09567c0f40 | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
a7872de9-89d5-46b2-bf49-4e4515049d29 | checkpoint | Fit off all EX/EMG’s
fd9ec66b-8b7c-4832-ab38-3f9e75ef84c9 | checkpoint | Label all EX/EMG’s as per plan number
ec3da091-2f8b-42ac-9fa6-7d663646d239 | checkpoint | Fit off all GPOs
eed85940-0357-4bda-b1fa-48b1c300e03d | checkpoint | Fit off of all isolators (signs, hand dryers, hws)
fb0be678-1016-439e-a59b-2271a76b9e59 | checkpoint | Ensure all fit off has been ticked off on plans once completed
baa46a21-802c-473f-a246-246435558a56 | checkpoint | Ensure area is left clean
8ecee1c5-2e7d-4e47-a67e-e61306e7777f | checklist | ITR No. 8 - Basement Light and Power fit off |  | ITR No. 8 - Basement Light and Power fit off
d6c3f9f5-ac5a-4f22-841a-779c0d62be19 | section | Basement Light and Power fit off
a3d53b46-3592-4c18-bc24-d05037813999 | checkpoint | CHECK DRAWINGS FOR QUANTITY, BRAND TYPE AND COLOUR
b9285de5-dab1-4f07-acd5-44793cf03896 | checkpoint | LOCATION/COMPLIANCE WET AREAS, HAZARDS ETC. MOUNTING HEIGHTS,
d38c5ad5-756a-4664-a458-bf4d559753ec | checkpoint | FIT OFF AND FIX SWITCHES, WHERE MULTI GANG SWITCHES WITH MULTI CIRCUITS ARE INVOLVED USE SHROUDS ON EACH SWITCH. EACH CIRCUIT MUST BE FITTED OFF COMPLETELY.
0c0f08e6-c21a-4b38-bf43-0bacb4ab7a04 | checkpoint | FIT OFF AND FIX GPO’S, WHERE A GPO IS LOCATED WITHIN 150mm OF A METAL STUD, USE SHROUD. EACH CIRCUIT MUST BE FITTED OFF COMPLETELY.
b2a36ff1-2569-4637-95db-7853335bfe82 | checkpoint | FIT OFF FINAL APPLIANCES
d0a0fde3-1259-4772-bd07-925b9364082e | checkpoint | COVER PLATES (IF REQUIRED)
fee5a06f-707d-5948-80f5-c559045d2a9d | note | INSTALL LABEL (IF A SPECIFIED REQUIREMENT)
ff280b87-ade6-4f24-9f15-66e511061982 | section | Light Fittings
daecf09d-9394-493f-9aca-2c09d58b636f | checkpoint | DELIVERY CHECK FOR DAMAGE AND CORRECT QUANTITIES
dde49ce8-9885-4268-9047-3aad3a85cb07 | checkpoint | LOCATIONS CO ORDINATE WITH OTHER SERVICES
54e5dfda-d682-4d39-962f-da9643dd3edc | checkpoint | MARKING OUT IF REQUIRED - REFER TO REFLECTED CEILING PLAN FOR SET OUT
c6a708af-9753-44e9-b492-8fd99c40bd29 | checkpoint | PLUG IN OR FIT OFF LIGHT / PLUG BASE
39280e6c-6c31-43d3-858d-54139eb6f16a | checkpoint | INSTALL LIGHT FITTING
353b1c10-b840-4b95-ad78-3fd080d1f8da | checkpoint | INSTALL LAMPS AND DIFFUSER
259b6f32-e3c9-4ae9-a69a-aba25a1cc73f | checkpoint | CLEAN FITTING, LAMP DIFFUSER
220f23c3-4688-4a64-92fa-8846970ca0e7 | checklist | ITR No. 9 - Apartment Rough In of Electrical Services |  | ITR No. 9 - Apartment Rough In of Electrical Services
16eae579-6eee-4355-8ad0-7adc70e3244f | checkpoint | Area clear, tidy and accessible
df273579-aff0-4339-a2bb-5b2ada8044e4 | checkpoint | Rough in Hard Actives to all switches
757843b8-0370-46e4-b711-2bc34cba787e | checkpoint | Rough in of Switched Actives from switches to lights & Fit off Quick connects whilst on ladder
a4139b26-b01f-4da8-b348-7dd55ad3e58a | checkpoint | Rough in GPOs
38f2b678-05de-49a2-a5c2-ede01f986de0 | checkpoint | Rough in of all kitchen general power (including island bench) above bench, gas cooktop, fridge, microwave, rangehood & dishwasher
ab823201-ee44-4723-9871-4fc6653f4dba | checkpoint | Rough in A/C & Oven
c9065673-9b8f-4a0c-80fc-1b97a3506686 | checkpoint | Rough in single tail island bench Pendant to the nearest downlight
b4871d72-be02-46c1-9735-06a49877f2a4 | checkpoint | Rough in a loop from Pendant to LED strip at rangehood
f18eac7e-faed-4371-b1e7-968427b7d3e6 | checkpoint | Rough in bathroom LED Fig 8 downight location and switch separately
a478e7ee-90e9-4e2f-928a-e9d76edf526e | checkpoint | Rough in LED fig 8 to study desk to nearest downlight
02025d88-b185-4f7d-9463-9b134771cfd1 | checkpoint | Rough in all internal lights
2705e3dc-285e-4f7c-a4d7-6675cd6a6e8e | checkpoint | Rough in Balcony wall light- If 2 lights, bring 2 switch wires back to switch
b3013b0a-a4d8-4747-bca8-74f8de4138a1 | checkpoint | Rough in smoke detector and interconnect to other detectors.
1d24c1d9-54b4-4508-8e37-1b8e92ade67e | checkpoint | Rough in bathroom fans off power circuit and HA loop at fan
ee92ff8d-6664-4597-b1c4-6a90f098cd4c | checkpoint | Rough in WM/DR and install SDI from dryer gpo to laundry switch
abd519fa-4fc0-410e-88ae-b21c06df459b | checkpoint | Rough in WP GPO to balcony if applicable
833075f7-d1f2-4f8b-8f0c-88a35b315409 | checkpoint | Rough in intercom patch lead to LBNCO hub
eab829ac-9e01-4b20-850a-071474312be3 | checkpoint | Rough in tv points to LBNCO hub
2f8f34a1-7266-4ba2-b633-55bc026f5ded | checkpoint | Rough in data points to LBNCO hub
5fe1c7ea-29ba-42a2-baaa-099fd8ea5e10 | checkpoint | Rough in sub main to switchboard
8176cf70-1c08-58c2-8e7f-e480481509a9 | note | Ensure LBNCO draw string is in
ef971409-1dd4-5f9a-9b39-3719893ef903 | note | Ensure Sub Mains are at Switchboard Location
263f8c8c-3a4d-4119-841e-15b99455f724 | checkpoint | Install switchboard & fit off
72e1c9cb-3f6d-4956-9138-1fdde5eafba8 | checkpoint | Install 150mm stud protecting sub main and earth with nut & bolt
3ad9d461-70ff-45bb-887d-6759f3e5e115 | checkpoint | Install 2.5mm earth tags
38354673-8735-4295-b003-6292e88717b5 | checkpoint | Fire caulk sub main into DB and all cable entries
ee328518-b38c-4dae-b17d-2e97cd10a9bb | checkpoint | Fit off 4 pin plug base
f0061b3d-84df-49ed-bc72-8b122eebaf5e | checkpoint | Ensure all Quick Connects are fit off
30b70814-5c74-47bb-9b47-ac9d5aa93e70 | checkpoint | Ensure all cables are neat, taped to studs and easily accessible for cut out
bbbbad60-be1e-4464-a44c-02b4dfc637d3 | checkpoint | Ensure all cables are clearly labelled at DB and at party walls
9d2d079c-dffc-4e8c-a033-b6cd553df93e | checkpoint | Ensure area is left clean
c3107cf1-36ab-45e1-a57d-72298b6bc4fe | checklist | ITR No. 09 - Basement In Slab Conduits |  | ITR No. 09 - Basement In Slab Conduits
c11db79c-dc29-4c42-8fea-b24c9c02f62c | checkpoint | Determine origin and destination
4a3c196c-1e08-46bb-bfcd-cdcd71c98fad | checkpoint | Check clear of other services, penetrations etc
b2a05d3b-9144-4522-af22-44575805fa40 | checkpoint | Check cable size to verify conduit size
2dabe948-6078-4415-9ab1-7672e31d13e4 | checkpoint | Check if expansion joints are required
97bdabbe-e737-4498-81ad-9e8408a449e2 | checkpoint | Mark out positions of junction boxes and penerations whee necessary
84646b7c-fb64-4d7f-9ad1-b0d0c84e2642 | checkpoint | Install bar chairs where necessary
70d659e9-67e4-4cf7-812d-f15ad7c7bdc4 | checkpoint | Install junction boxes and penetrations where necessary
1230a864-86fa-4aeb-8804-c9f069b93b37 | checkpoint | Install junction boxes and conduits glue
9dd2e740-5bc3-4af5-a747-c8aa9341a21d | checkpoint | Tie conduits securely at all joints and midpoints
70c839cd-47ab-4010-a75b-39d9ab0e1bc9 | checkpoint | Ensure all conduits are 50mm above deck
59f2bf60-f627-4b68-ab73-513e2f06cc9e | checkpoint | Mark up drawing of conduit runs (if required)
0560376e-4c4c-478e-a69f-498eaf0335f7 | checkpoint | Observe conduits when concrete is being poured
d49f2788-e2c2-4974-9d5d-eded76ba0d02 | checklist | ITR No. 10 - Cable Tray Installation |  | ITR No. 10 - Cable Tray Installation
7a7452ab-d5b7-4cb0-badc-68cc63e48631 | checkpoint | CO-ORDINATE WITH OTHER SERVICES (CHECK FOR ANY CLASHES)
06438f50-a05f-40dd-b0dc-2d4c22969605 | checkpoint | CONFIRM SIZE OF CABLE TRAY
d970184c-fe60-4e27-bf2f-527d53c8189b | checkpoint | INSTALL FIXINGS AND SUPPORTS AS NEEDED
621ce5ca-ef1c-4c85-80fe-6a26c7c1c266 | checkpoint | INSTALL CABLE TRAY
f3b4b70d-439c-4e20-8b5b-8f1fa3ca14a9 | checkpoint | COMPLETE SKETCH/MARK UP DRAWING FOR FUTURE AS BUILTS
ba967613-9bc0-4e75-ae3f-b43b91eda21d | checklist | ITR No. 12 - Switchboard Commissioning |  | ITR. 12 Switchboard Commissioning
dabe5109-75ab-4e03-a768-a78553a69ced | checkpoint | Prior To Energising All Personnel Involved To Be Inducted Into Energisation Procedure And All Steps Undertaken To Ensure Compliance With This Procedure
da875066-6a00-46e5-bb12-c9fd42b534c3 | checkpoint | Refer To As Installed Drawings
c605eb7e-95f8-4ed2-bcf5-d6913a2270d1 | checkpoint | Obtain Copy Of Switchboard Schedule And Schematic Drawings
a03b0c26-023f-400b-80f0-8f90ce881f5a | checkpoint | Mark Up Any Additions Or Deletions Found Whilst Commissioning
051385c7-72b5-421f-bdf2-157b48a6a09d | checkpoint | Complete Visual Checks
4a70b87f-c78e-4c5f-a9a7-ec2f02f5a5aa | checkpoint | Refer To Mandatory Testing From As/Nzs 3000:2018 8.3.3 Below
b4707604-fe35-451a-aa04-1cf9b32bb11f | checkpoint | Complete Mandatory Tests Using Metrel Tester, Save And Log Results On Tester
1c5dc74b-5658-445c-bca0-854b16f00e85 | checkpoint | Any Failed Results To Be Rectified Saved And Logged On Tester
d6862efe-05fd-4f0d-84d0-920bcefb6391 | checkpoint | Ensure Correct Operation Of All Control/Equipment Installed In Switchboard
04799e5e-c890-4b24-bfe0-aec2a80832bf | checkpoint | Ensure Vast Witness Test Has Been Completed
0ad01f7d-3d21-4217-a91a-9ff7a2cec649 | checkpoint | Ensure Escutcheons, Pole Fillers, Fixing Screws Are Reinstated
2ed3314c-e830-4f38-8533-3281f20c5fe8 | checkpoint | Ensure No Access To Live Parts
9b1d6401-7923-4f48-878e-98876014b948 | checkpoint | Complete Switchboard Schedules On Vast Template, Install And Fix To Allocated Position In Switchboard
94045449-1bcf-496d-9a41-4fd7d38d4d1b | checkpoint | Download Test Results From Metrel Tester And Save To Project Folder
ac4b1a86-09b9-4c43-9501-c3622aecaaf4 | checkpoint | Complete Certificate Of Electrical Safety And Save To Project Folder
2d8404dc-336b-4122-911d-9ef7834006c9 | checkpoint | Take photo's of all Switchboard internals without escutcheon
9195794a-bd70-4b8b-b46a-cefdb2e5c433 | checklist | ITR No. 13 - Hallway Cutout Ceilings & Walls |  | ITR No. 13 - Hallway Cutout Ceilings & Walls
e386df72-2893-45da-9d2a-f6b5cf0f67d2 | checkpoint | Confirm sizes off all fittings prior to cut out
fd77592b-1927-4599-8b19-ee760da648e5 | checkpoint | Cut out for all sensors, EX/EMG, light fittings
e6d5e06e-4c52-4389-9f09-649ac73a380a | checkpoint | Cut out all cleaners GPO’s, Comms Riser GPO’s
a85919c6-cb69-4539-a55b-a887317656be | checkpoint | Cut out any CCTV cameras
c5ed6664-6d27-4539-b31a-00a7e68e357a | checkpoint | Ensure Electric Strike cable is inside the pressed metal frame cut out
855d2be6-f25c-43b3-9160-9992ed7bb679 | checkpoint | Locate all Cables
7e499598-7824-484c-a4d8-7e489dcfd4bd | checkpoint | Install Firebox’s
95c32134-13be-427d-882d-bb43e9570213 | checkpoint | Clean Up
634c9a04-f212-4a78-ae20-99c2b2cfecb5 | checklist | ITR No. 14 - Mains and Sub Mains |  | ITR No. 14 - Mains and Sub Mains
55c80f1a-70c9-4d92-96a0-71125ced7125 | checkpoint | Measure cable runs with appropriate accurate measuring instrument eg: tape measure, wheel, rope in conduit
3e47214d-270f-4df6-a649-618d97ff5b2b | checkpoint | Confirm length of cable
83e59557-dce7-412a-9d3c-3b2595529a70 | checkpoint | Install cable in applicable method eg: cable stands, electric winch, pulleys etc
bf8e2f3e-9ba7-56a0-bf28-5ef01bcc54cd | note | Any cable not terminated immediately must have the end taped covering the bare copper
19f1227a-5e99-4244-855e-2c18eb69a0a0 | checkpoint | Trefoil (refer to details on back for all options) cables and tie cables to support system
97efeb87-6dd0-48cf-83cd-a0b513544767 | checkpoint | Check cable requirements for cable identification and install
6db4f398-f677-4bcb-9887-5f60445dbe56 | checklist | ITR No. 16 - Switchboard Installation and Terminate Submains |  | ITR No. 16 - Switchboard Installation and Terminate Submains
7b90dc71-275b-4808-b320-bc0685aa6490 | checkpoint | DELIVERY CHECK FOR DAMAGE, PAINT FINISH, DIMENSIONS AND DOORS AGAINST APPROVED SHOP DRAWING
b7ac08ef-596c-424c-af27-3df5954988e7 | checkpoint | LOCATE & FIX INTO POSITION
f9740ae8-de2a-4a33-bf7a-69dd39bb0540 | checkpoint | INSTALL SUBMAINS CABLING AS APPROPRIATE EG. GLANDS, TRAY, DUCT
f66709f2-4148-4b7a-84f3-623b583a9566 | checkpoint | INSTALL LUGS AND TERMINATE
11344ffc-e7ec-4e24-b368-739bddf2376d | checkpoint | ANY CABLES NOT TERMINATED PRIOR TO ENERGISATION MUST BE REMOVED FROM CUBICLE AT ORIGIN AND HAVE ENDS COVERED IN HEATSHRINK. AT DESTINATION CABLES MUST BE COVERED IN HEATSHRINK AND BE CONTAINED IN A JUNCTION BOX
94261b9f-b4cf-478d-9101-966010e568d3 | checkpoint | CLEAN & VACUUM
247f630e-bca5-4cc0-adbc-742c1c379e4f | checkpoint | ORGANISE INPECTION BY INSPECTOR. LODGE PRESCRIBED / NON PRESCRIBED (AS APPLICABLE) CERTIFICATE OF ELECTRICAL SAFETY (IF REQUIRED).
4316fa59-48a9-4c34-8305-2b884240508f | checkpoint | CLEARLY IDENTIFY SERVICES
90002d16-4a94-4a9b-9a7c-badd19ceaf69 | checkpoint | WHEN READY TO ENERGISE PROCEED IN ACCORDANCE WITH ENERGISATION PROCEDURE
b5b381d7-1cf5-4f6d-9d74-9b04e087d677 | checkpoint | ENERGIZE & RECORD RESULTS
8006b7d6-12e5-4218-9981-754fd25418f5 | checkpoint | CHECK SWITCHBOARD AS INSTALLED MATCHES SHOP DRAWING. IF NECCESARY MODIFY SHOP DRAWING TO MATCH INSTALLED & RETURN TO OFFICE
8cdd5507-6d67-4d11-890a-1f7376f2cbdf | checkpoint | CLEAN SWITCHBOARD CUPBOARD
f02f9011-50e9-49a3-9089-1fd7d22edf69 | checkpoint | INSTALL SUB CIRCUIT CABLING IN ACCORDANCE WITH DB SCHEDULE AND TERMINATE. if circuit not complete at the other end, it must not be terminated BUT PLACED IN A JUNCTION BOX AT FIELD END AND IN CONNECTORS AT dISTRIBUTION BOARD END.
d66746fa-ce09-43fd-a0fb-50fae8ea4165 | checkpoint | CLEAN & VACUUM
308709b6-be74-4903-9da2-ad3f22d203ba | checkpoint | RECORD RELEVANT INFORMATION AND ANY CHANGES ON DB SCHEDULE. AND RETURN TO ADMINISTRATOR/OFFICE FOR COMMISSIONING TEAM
efbea822-59da-4227-b65d-6db62ca7cd85 | checklist | ITR No. 18 - Hallway - Fit Off Electrical (High Level & Walls) |  | ITR No. 18 - Hallway - Fit Off Electrical (High Level & Walls)
ce5265e6-48e1-4903-a5ab-b9a61144014c | checkpoint | Fit off all plug bases
7a2d485c-5541-467e-a55a-14e3bf28dd0e | checkpoint | Fit off all Lights
d121b12a-cf07-4d26-8c2a-7c61dab60c8c | checkpoint | Fit off all Sensors and SET TIME TO MINIMUM
1ab55802-1c03-45fe-8fbd-02b12225119c | checkpoint | Fit off all EX/EMG’s
be32b353-ab85-45e4-b6de-4ef1b6a443b7 | checkpoint | Label all EX/EMG’s as per plan number
942a22e5-628d-458f-9008-3a9589e8d3f4 | checkpoint | Fit off all Cleaners GPO’s
ed31b0b5-c316-46a3-afaa-bd8a25d964ad | checkpoint | Fit off all Comms Riser GPO’s
21c05c3a-cf63-41e7-85eb-614f29d93255 | checkpoint | Clean Up
8400dd3b-40fe-4ae4-bc08-953017136c0e | checklist | ITR No. 18 - Light and Power Fit Off |  | ITR No. 18 - Light and Power Fit Off
c3eeb8ea-5a5e-49b9-952c-397e59455115 | section | Bakelite & Power
73737ca1-62e8-47ba-8385-a6e519dcb0bc | checkpoint | CHECK DRAWINGS FOR QUANTITY, BRAND TYPE AND COLOUR
581173b5-8474-4d06-97a8-99a25ad161c6 | checkpoint | LOCATION/COMPLIANCE WET AREAS, HAZARDS ETC. MOUNTING HEIGHTS,
2b35b921-fd74-4dea-bf30-67590b73c517 | checkpoint | FIT OFF AND FIX SWITCHES, WHERE MULTI GANG SWITCHES WITH MULTI CIRCUITS ARE INVOLVED USE SHROUDS ON EACH SWITCH. EACH CIRCUIT MUST BE FITTED OFF COMPLETELY.
68597c25-f2ae-461b-b7a6-e1667b1572d0 | checkpoint | FIT OFF AND FIX GPO’S, WHERE A GPO IS LOCATED WITHIN 150mm OF A METAL STUD, USE SHROUD. EACH CIRCUIT MUST BE FITTED OFF COMPLETELY.
1f6a3824-e6d2-47c1-8993-0b902c8d0823 | checkpoint | FIT OFF FINAL APPLIANCES
ce0325bb-9654-4d08-b85b-c9d152cfd91a | checkpoint | COVER PLATES (IF REQUIRED)
c43c132d-f1fb-4e30-a502-81cd8a1d5ba2 | checkpoint | INSTALL LABEL (IF A SPECIFIED REQUIREMENT)
9931bea5-23c8-4512-aef0-3d8da310f637 | section | Light Fittings
e49b6a6b-89c8-44b3-9021-73f4d94592a8 | checkpoint | DELIVERY CHECK FOR DAMAGE AND CORRECT QUANTITIES
def2f30d-fdf4-4faf-ad89-742a8c94a984 | checkpoint | LOCATIONS CO ORDINATE WITH OTHER SERVICES
965007a7-5747-4385-a105-2a4cc735dfec | checkpoint | MARKING OUT IF REQUIRED - REFER TO REFLECTED CEILING PLAN FOR SET OUT
a105dbae-1666-484e-bf8f-3402fb01e8d7 | checkpoint | PLUG IN OR FIT OFF LIGHT / PLUG BASE
efed6123-2d83-46d0-9189-b034fab1dd07 | checkpoint | INSTALL LIGHT FITTING
2401eb4f-9fa0-4931-aaa0-7ad79cb86704 | checkpoint | INSTALL LAMPS AND DIFFUSER
5a41a402-5187-4e40-b853-bfc4a79d0bff | checkpoint | CLEAN FITTING, LAMP DIFFUSER
ea660af4-2152-48c1-8eda-c571b37c92f6 | checklist | ITR No. 19 - APARTMENT- Electrical Fit Off |  | ITR No. 19 - APARTMENT- Electrical Fit Off
430bab81-5dc0-4edb-be36-2af34733857c | checkpoint | Fit Off Downlights
f88c2366-c68a-454d-9677-5974a4a81152 | checkpoint | Fit Off Smoke Detectors ( leave tab & dust cover on )
a7dfdf1a-cd7f-460c-a4c8-fe5214f88415 | checkpoint | Fit off general GPOs
ffab8e89-7dcb-442f-920e-de6a9e7af45d | checkpoint | Fit off kitchen joinery GPOs and install cover plate
1dc94887-f222-4ae0-b73c-88c3fca199ab | checkpoint | Fit off laundry GPOs & Switch
9ae3426e-8229-4869-b8c6-451156440f19 | checkpoint | Fit off dishwasher GPO
7873bc77-6990-4702-bf40-6b7893919922 | checkpoint | Fit off shave cabinet GPOs
3e6a325c-1e38-40b5-a4d5-eaab5ea2962a | checkpoint | Fit off light switches
5cc1b141-8ad1-412b-ba1b-92358fb89dad | checkpoint | Fit off TV Point
7943b47d-a868-42fc-95db-37fb380c17d0 | checkpoint | Fit Off Data Points
67f22961-ddf9-4c17-8652-233ec6b263f7 | checkpoint | Fit off Balcony Light
1cab49df-0f84-4bf5-9a19-c25336fd750d | checkpoint | Fit off AC Isolator
d48e45b7-5f8f-4ead-b028-aa8eec6ff729 | checkpoint | Fit Off WP GPO ( if applicable )
9cc096cc-719a-4a84-b5bc-f2b8fea91abc | checkpoint | Fit Off LED Strips
515449ea-fc79-4b98-99b9-a59a61b04612 | checkpoint | Fit Off Pendent
113111f5-6049-4d2f-a05c-66e4718f8f38 | checkpoint | Install Oven ( take photo )
8c10175f-9c40-431c-b1c6-791a6fe5ea55 | checkpoint | Clean Up
36bb8346-0dc6-4068-a214-03024d894622 | checklist | ITR No. 26 - Hallway - Commissioning Electrical & Permanent Power |  | ITR No. 26 - Hallway - Commissioning Electrical & Permanent Power
d29e20f3-29b6-49aa-80e1-1b1f532cb2c4 | checkpoint | Energisation permit completed prior to energisation
f4c9d5e8-341b-4fdc-8e87-0e6dcdc60639 | checkpoint | Visual Check (against most current plan)
c6a47693-b683-454f-9f10-109e24d93fbb | checkpoint | Dead Testing
d42a68c1-a052-46e1-99c9-3b0b98228fab | checkpoint | Live Testing
f7a99b22-6c0d-41c6-b8db-66291fc8427e | checkpoint | Record Metrel Results
b316a183-8d07-4f16-8f52-c7cdc879e6e7 | checkpoint | Check operation of all sensors (individually on minimum time setting )
6e2e136e-547e-47a5-ac68-6455093542f9 | checkpoint | Check sensors are set to specified time and lux
42ea1ea2-0cf9-479e-8b39-65f1215bc4cd | checkpoint | Check operation of all EX/EMG, perform 120 min test ( initial )
7d214308-6070-4028-86b4-06fd1a73f3ea | checkpoint | Fit cover plates to all GPO’s and Exit signs
46e8fe43-0ab6-476f-9f94-f0528700c7f1 | checkpoint | Clean Up
305af9e2-5f59-4f64-a826-8205a629f14f | checklist | ITR No. 27 - Commission Electrical & Permanent Power |  | ITR No. 27 - Commission Electrical & Permanent Power
6316b645-3a0f-4a0a-a25c-ce1749adde77 | checkpoint | Energisation permit completed prior to energisation
4a5dee1d-59b8-4eb4-a2a3-c8e592661bb5 | checkpoint | Visual Check all items
4c71cf4d-a4a2-48a3-872d-f9bfce43e7d8 | checkpoint | Dead Testing
5e24851f-2eb3-4861-b7a7-a2a6d76d77f6 | checkpoint | Live Test
e1cbec48-5075-40e5-85b7-a9d9bdb27cf4 | checkpoint | Record Metrel Results and log
acc2a819-0306-4367-94a1-692d5fd6511a | checkpoint | Test 4 pin plug base for switching
4b0ad419-3a8c-47b1-969c-b879cda83c71 | checkpoint | Check light switches for correct switching functions
30131e82-bc46-4366-beef-93672eb95509 | checkpoint | Fit Cover Plates to GPOs & Switches (take photos)
c08dc5a2-9197-42ba-975f-88aa4051d156 | checkpoint | Install switchboard cover / label (take photos)
a6e786b9-8422-4ac3-b158-7eacb2fc71f3 | checkpoint | Remove battery tabs on smoke detectors ( after MFB certification )
3294d676-a280-424e-ba02-807aeb3eec4f | checkpoint | Clean Up
0daaa412-464d-4190-8b7c-114e7ff23297 | checklist | ITR No. 33 - Installing Underground Services (Electrical) |  | ITR No. 33 - Installing Underground Services (Electrical)
dc1302de-0056-45b0-8877-df884ff3cb71 | checkpoint | Inspect conduit material to check that it meets material specifications
598e3dc9-caf2-475f-8195-94d0946b21e5 | checkpoint | Check conduit alignment as per plans
e0017912-ca19-4f8c-9c19-f485ba85625e | checkpoint | Set out marked, and all services located
1adfbf7c-a138-4328-b10e-b74d002219bb | checkpoint | Erect pedetrian barricading as per plan
678c4176-e530-4ee0-94b1-5f14af4d80ec | checkpoint | Check excavation depth against proposed road level
e44dfb78-52f9-4392-8b6d-75388682e62e | checkpoint | Excavate to the trench as per plan
1ed7c5a2-5085-4ef0-b577-58c149db7789 | checkpoint | Place specified bedding material in trench
6e5abc01-2836-4934-949b-f32d81218927 | checkpoint | Placement of conduit of specified size in accordance with specifications/drawings
68f202d9-caad-4fc3-8557-425743cd8fab | checkpoint | Backfill over conduit to 600mm
146f6d2d-98a1-43f5-93c2-f34ed62cce77 | checkpoint | Install cover slabs over conduit
ddac6081-41cc-478f-a8c5-47c1718ce43a | checklist | ITR No. 33C - Installing Underground Services (Comms) |  | ITR No. 33C - Installing Underground Services (Comms)
2430f3e8-e9e6-433f-afad-cb84dc0136a1 | checkpoint | Inspect conduit material to check that it meets material specifications
9d63f1be-58bc-4a90-851e-8c0f39e40670 | checkpoint | Check conduit alignment as per plans
e2a9570f-acda-4a31-877c-f7bc1edb3b5b | checkpoint | Set out marked, and all services located
99c60d56-4c5a-4c49-9d1e-7d3975f36da1 | checkpoint | Erect pedetrian barricading as per plan
f471595e-f37d-421e-a18e-1665fbe61505 | checkpoint | Check excavation depth against proposed road level
6a8e469c-4df4-484d-8a99-e65f54226acb | checkpoint | Excavate to the trench as per plan
67789a11-2a61-4b77-b01d-f79974b312c4 | checkpoint | Place specified bedding material in trench
a4dda267-3053-4dc7-aea2-bb9505bd0132 | checkpoint | Placement of conduit of specified size in accordance with specifications/drawings
97a765db-b266-46de-8bd4-85d71d210c5d | checkpoint | Backfill over conduit to 300mm
d78fec1d-4569-4d57-85de-b1ba1b825c92 | checkpoint | Install cover slabs over conduit
3c2ba4de-a0c7-478c-988e-314431294f63 | checklist | ITR No. 34 - Installing Light Pole Cages |  | ITR No. 34 - Installing Light Pole Cages
163b28a6-a0ee-4309-a1f7-155bade23c7e | checkpoint | INSPECT CAGES FOR ANY DAMAGE PROIR TO INSTALLATION
4647dc2e-0374-42f2-b442-e6d21a7a5e59 | checkpoint | SET OUT LIGHT POLE LOCATION, ALIGNMENT AND HEIGHT AS SPECIFIED
1a10e3e1-30bb-461c-9138-636397ca66c0 | checkpoint | ERECT PEDESTRIAN BARRICADING AS PER PLAN
cc24f7e0-821a-4b3e-b2b1-4a64c31268fb | checkpoint | EXCAVATE AS PER PLAN
f58da9d2-b559-4b1d-911e-15d145eb4fc9 | checkpoint | PLACE SPECIFIED BEDDING MATERIAL AS PER REQUIREMENT
624893bb-c6e1-41cc-b816-9eb60789be50 | checkpoint | INSTALL LIGHT POLE CAGES AND CONDUITS AS REQUIRED
d376b38d-c09f-4d79-9829-8e29e4f9d3fd | checkpoint | RE-CHECK FINSHED HEIGHT AS PER CIVIL DRAWINGS
9243e207-0c20-4642-b530-19562f4441d5 | checkpoint | POUR CONCRETE FOOTING WITH SPECIFIED MPA
449ab16c-d244-42ea-bf97-168a09294421 | checkpoint | CLEAN UP AND BARRICADE WORK AREA
9c589ea4-ebba-4cbb-ab88-87318d1d1889 | checklist | ITR No. 35 - Installing Underground Pits |  | ITR No. 35 - Installing Underground Pits
01a9299a-bfee-4488-85dc-d18871d9a61c | checkpoint | INSPECT PITS FOR ANY DAMAGE PROIR TO INSTALLATION
b3e04995-29a0-42fa-a8af-7cc52cce68cf | checkpoint | SET OUT PIT LOCATION, ALIGNMENT AND HEIGHT AS SPECIFIED
46a624ae-0e06-4b2e-a6bb-3ed778108833 | checkpoint | ERECT PEDESTRIAN BARRICADING AS PER PLAN
8497fe41-393c-4584-bb49-a8123a3d6471 | checkpoint | EXCAVATE AS PER PLAN
4ad0431a-8e16-4b45-b669-96328a0df825 | checkpoint | PLACE SPECIFIED BEDDING MATERIAL AS PER REQUIREMENT
66992e6d-a16b-46b0-b7cd-9a5ad44b62b5 | checkpoint | INSTALL PIT AND CONDUITS AS REQUIRED
debaa28b-b86c-4ea3-a7bd-6a2ac59eb07e | checkpoint | RE-CHECK FINSHED HEIGHT AS PER CIVIL DRAWINGS
26598cbb-25c0-417d-8ae1-bee2bce1d78d | checkpoint | BACKFILL AND REINSTATE GROUND AS REQUIRED
0f62d89e-57a0-4260-831a-65fe04aeeb47 | checklist | Toolbox Meeting |  | Toolbox Meeting
decd8a96-685e-4f28-8e50-47e2bd93d09d | checkpoint | Details
acd446e9-425e-519b-992d-37c653e93b3a | textbox | Location
584c8b07-1952-52fb-96b1-d33f22ebebe2 | textbox | Supervisor
f2df7993-08bd-55a7-b963-f6a24029d7ac | textbox | Date
86bf3f4c-4b87-5460-95df-79f833b3d475 | textbox | Time
aada1ba2-e42e-522a-ae83-93188c9d606e | textbox | Persons present
2edb7a82-9792-5c51-b090-590b130131a1 | note | Topics discussed
8620ec71-f1d1-5bde-a218-01579e56052b | tickbox | - Injuries, near misses and incidents
dcd8d09c-2b0c-5491-af13-836000890d20 | tickbox | - Management of major hazards
eb62f661-8372-533c-a886-19ced59e43bd | tickbox | - Compliance with our Vast SWMS
109aba20-cfdb-59df-8651-ead89987567b | tickbox | - Safety - E.g., Apply LOTO processes when applicable. When Megger testing ensure that no person is working at the other end of cable being tested.
f3c0de5c-d953-5538-b42c-851b5412762b | tickbox | - Housekeeping
a8f4766f-f8aa-5b17-80ae-f20aa19b7cdc | textbox | Comments from the floor
2a2ffd8d-567e-4961-90eb-7050167c7d58 | checklist | zSYS - ITR No. 12 - Switchboard Commissioning (old version) |  | ITR No. 12 - Switchboard Commissioning
db6e2226-7c0b-45aa-b25e-d19a1565d630 | checkpoint | Prior To Energising All Personnel Involved To Be Inducted Into Energisation Procedure And All Steps Undertaken To Ensure compliance With This Procedure
630e66dc-c846-41c9-9041-25d042f57f66 | checkpoint | Refer To As Installed Drawings
81fdbec0-ab92-462e-8d46-57b5bc46c92a | checkpoint | Obtain Copy Of Switchboard Schedule And Schematic Drawings
a59f6c55-29f9-420e-a645-82ccd54b8ca3 | checkpoint | Mark Up Any Additions Or Deletions Found Whilst Commissioing
3ed86b27-978b-46d0-8d6c-e0b5b78936bb | checkpoint | Complete Visual Checks
450f8ba7-2054-489b-9e73-d9eeb1350360 | checkpoint | Refer To Mandatory Testing From As/Nzs 3000:2018 8.3.3 Below
97a0a4f6-9561-4dfb-bded-cdf6077f4120 | checkpoint | Complete Mandatory Tests Using Metrel Tester, Save And Log Results On Tester
dd8b3e72-9679-44aa-be67-c109fdec22db | checkpoint | Any Failed Results To Be Rectified Saved And Logged On Tester
c5eea5ac-126f-4faa-9c1e-0beec75ebc86 | checkpoint | Ensure Correct Opertation Of All Control/Equipment Installed In Switchboard
952799ec-2640-4867-9919-3b7c6aad3d13 | checkpoint | Ensure Vast Witness Test Has Been Completed
9c1370df-c179-47cd-a4af-71a7be2d34a9 | checkpoint | Ensure Escutcheons, Pole Fillers, Fixing Screws Are Reinstated
fb3e77e4-4d13-4028-aa09-a611d752defc | checkpoint | Ensure No Access To Live Parts
eec9b972-1971-4049-8c36-13bb13563207 | checkpoint | Complete Switchboard Schedules On Vast Template, Install And Fix To Allocated Postion In Switchboard
43abe6d0-35d7-416e-95e3-b3d8a4ee8970 | checkpoint | Download Test Results From Metrel Tester And Save To Project Folder
30db61e7-c1f3-4ca0-88fb-7c3f6476c8c4 | checkpoint | Complete Certificate Of Electrical Safety And Save To Project Folder