## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ENT-009 - Pressure Test Report |  |  |  |  | Yes | ENT-009 - Pressure Test Report | 007a3e4f-620d-4807-a2a7-d05fa896d584
checkpoint-status |  |  | checkpoint | Test Details & Results
select | 3161cd6c-83db-5b0a-a6e4-597388cca8d9 |  | dropdown | Select correct test criteria for Test | TEST CRITERIA HYDRANT HOSEREELS - HYDROSTATIC TEST – 1700kpa 2 HOURS,TEST CRITERIA FIRE SPRINKLERS - HYDROSTATIC TEST – 1700kpa 2 HOURS,TEST CRITERIA GAS SUPPRESSION - PNEUMATIC TEST – 300kpa 10 MINS - PRESSURE DROP SHALL NOT EXCEED 20% (60kpa),TEST CRITERIA WATER MIST - HYDROSTATIC TEST – 3300kpa 2 HOURS,Other (Specify below)
text | 95434dfc-cad7-5337-9ab1-42653f9397c2 |  | textbox | Other (Specify here)
text | bbd185ee-5f46-5d59-be20-1a1858cff47a |  | textbox | Test No.
text | 2bf6ed90-3179-56ee-9dc9-ccc633176b7b |  | textbox | Gauge Reference (or Attach photo below)
text | d7128151-023b-56b5-9243-641c9de48290 |  | textbox | Start Date
text | a6c6b258-d97e-5036-81a2-60374e84053e |  | textbox | Start Time
text | d2fceca1-cf5e-5e78-9791-1c71147cf8bb |  | textbox | Start Pressure
text | 4ab06b22-1495-551e-9ecd-76b164a5b6d8 |  | textbox | Final Pressure
text | e5158398-dd1f-576d-a107-c77537ca831b |  | textbox | finish Time
checkpoint-status |  |  | checkpoint | Sign-Off Test completed to specification/drawings & Area left clean/tidy
label | 9027b859-0871-588f-a97a-e1efd8e14e66 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 0a691a9a-7466-5552-a360-08be05a88d74 |  | button | Entire Fire Signature Sign-Off added below | Yes,No
checklist-sectioned |  |  | checklist | ENT-002 - Gaseous Suppression |  |  |  |  | Yes | ENT-002 - Gaseous Suppression | 0c36539b-ff02-4fae-996f-ea5c58404729
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | 5985e0ad-180d-5333-b631-2802565e0ef6 |  | note | Specification Ref: AS:2414
checkpoint-status |  |  | checkpoint | Pipe, Fittings, Manifolds, Hoses, Nozzles
label | 84aa8366-8a59-5b10-ab5e-f6ef3cb1dc25 |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | Cylinders
label | 8a5d8326-b396-5101-a75a-f9fe724ef4ee |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-group |  |  | section | Installation Rough-In
checkpoint-status |  |  | checkpoint | Mains, ranges & riser pipes
checkpoint-status |  |  | checkpoint | Hangers location & spacing
checkpoint-status |  |  | checkpoint | Cylinders mounted as per manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Cylinder hoses fitted correctly to discharge manifold
checkpoint-status |  |  | checkpoint | Cylinder pressure gauges fitted and indicating correctly
checkpoint-status |  |  | checkpoint | Discharge solenoid fitted
checkpoint-status |  |  | checkpoint | Manual release device fitted
checkpoint-status |  |  | checkpoint | Barometric dampers fitted
checkpoint-status |  |  | checkpoint | Penetrations Sealed
checkpoint-group |  |  | section | Installation Fit-Off
checkpoint-status |  |  | checkpoint | Discharge nozzles fitted
label | 8385df0c-3af5-559e-8f5a-1894805b1ce2 |  | note | Certification AS:14520
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-sectioned |  |  | checklist | ENT-019 - MASDS |  |  |  |  | Yes | ENT-019 - MASDS | 19996b93-1650-4202-83d2-26129bd93b79
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | cc35f7e7-85e1-55bb-86a5-18188324efb9 |  | note | Specification Ref: AS:1670, AS:3000, BCA and drawing
checkpoint-status |  |  | checkpoint | Cable/Conduit/Tray
label | fa7dd89c-3454-5a10-820c-aa24e128898b |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | MASDS Sampling Pipework
label | 3d0eb065-19b3-56ab-a0b2-bfef9b9f65de |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | MASDS Unit
label | 72a12627-f247-57e6-a54d-e8a1596ee4cc |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-group |  |  | section | Installation Rough-In
checkpoint-status |  |  | checkpoint | Correct cable used (eg Fire rated as required)
checkpoint-status |  |  | checkpoint | Cable Support
checkpoint-status |  |  | checkpoint | Segregation from other electrical services
checkpoint-status |  |  | checkpoint | Type of cable fixing & spacing
checkpoint-status |  |  | checkpoint | No cable joins between equipment
checkpoint-status |  |  | checkpoint | Conduit type
checkpoint-status |  |  | checkpoint | Conduit fixings
checkpoint-status |  |  | checkpoint | MASDS
checkpoint-group |  |  | section | Installation Fit-Off
checkpoint-status |  |  | checkpoint | Sampling Points Installed
checkpoint-status |  |  | checkpoint | MASDS installed & connected to FIP
checkpoint-status |  |  | checkpoint | MASDS Panel Fit Off
checkpoint-status |  |  | checkpoint | Strobes/ Illuminated signs installed
checkpoint-status |  |  | checkpoint | Confirm obscuration and alarm thresholds
checkpoint-status |  |  | checkpoint | Measure transport times
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Obscuration Levels Set
checkpoint-status |  |  | checkpoint | Confirm Travel Times
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-sectioned |  |  | checklist | ENT-016 - Fire Extinguishers |  |  |  |  | Yes | ENT-016 - Fire Extinguishers | 1be22e64-9573-4714-b0de-e81751a2632a
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | 04cd7eed-4559-5e35-b30f-618d85065262 |  | note | Specification Ref: AS:2444, AS:2941 and drawing
text | c6b4ba1f-16e8-5b34-b1d0-848a54c4ea7e |  | textbox | drawing reference
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Secure cabinet
checkpoint-status |  |  | checkpoint | Extinguishers installed
checkpoint-status |  |  | checkpoint | Signage to meet code compliance
checkpoint-status |  |  | checkpoint | Hangers location and spacing
checkpoint-status |  |  | checkpoint | Fire blankets
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-sectioned |  |  | checklist | ENT-020 - Occupant Warning System/EWIS |  |  |  |  | Yes | ENT-020 - Occupant Warning System/EWIS | 569d596b-6888-43ad-ac60-8e41bbb296b9
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | c1fa1a94-ab8a-5fa9-a618-dfe6c4dbcaab |  | note | Specification Ref: AS:1670, AS:3000 and drawing
text | a6860e1e-8fd7-5308-8abb-f25c81c7f68e |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | a9071bc6-a5b5-5f06-8467-1376a17eaa38 |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Cable/Conduit/Tray
label | 7bdbfcd8-49ce-5993-ad1d-15e585425653 |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | Speakers/Strobes
label | 365276d6-f12c-501a-95e0-d5fd47994e3a |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-group |  |  | section | Installation Rough-In
checkpoint-status |  |  | checkpoint | Correct cable used (eg Fire rated as required)
checkpoint-status |  |  | checkpoint | Cable Support
checkpoint-status |  |  | checkpoint | Segregation from other electrical services
checkpoint-group |  |  | section | Installation Fit-Off
checkpoint-status |  |  | checkpoint | Speakers/Strobes
checkpoint-status |  |  | checkpoint | OWS Panel
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Confirm operation of all speakers/strobes
checkpoint-status |  |  | checkpoint | Confirm decibel levels
checkpoint-status |  |  | checkpoint | Confirm OWS operation initiated from FDCIE
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-flat |  |  | checklist | ENT-005 Site works completion summary (sprinklers) |  |  |  |  | Yes | ENT-005 Site works completion summary (sprinklers) | 729bece8-0ca6-45a2-bd2c-35da5880e7c0
checkpoint-status |  |  | checkpoint | Drawing number
text | 1980b8a0-c278-5dfc-9d95-7cad64f00106 |  | textbox | Sprinklers rough in (ENT-004) date completed
text | 2b85045d-dd88-56ce-b173-7d6fa3ef5ba4 |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 514dc4d8-e91a-579a-91d8-0c6476fdfaf5 |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 7bfeee3e-2ae7-5bab-91a6-aaa47a5ac546 |  | textbox | Sprinklers rough in (ENT-004) date completed
text | 0d0e3f6b-dadb-5d10-8d3b-b47944a5eb68 |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 04a928fa-214d-5754-816b-a6e093cc2d33 |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 99d0d19b-d3b4-524a-a078-cee528570b9d |  | textbox | Sprinklers rough in (ENT-004) date completed
text | 9238642f-c267-50ca-8ab1-abf6a7502895 |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 30683fc9-527a-5315-95d4-1a2324d3444e |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 0b0532d7-7e29-553b-9adc-e7506393895c |  | textbox | Sprinklers rough in (ENT-004) date completed
text | a77cac15-5e35-5939-86b3-6f3d249a81fa |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 7a07d882-e391-563d-98b6-0411d794ddd1 |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 4c8fd1a4-12fe-5dd4-9ae9-2c397613c70a |  | textbox | Sprinklers rough in (ENT-004) date completed
text | 5658eee7-45f3-504f-9e36-eecd8288006f |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 76bb9f82-e870-5bb8-9e3c-e0ebad32b056 |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 80320742-6b1b-56d9-bb9f-3695d727b0ed |  | textbox | Sprinklers rough in (ENT-004) date completed
text | abaf2868-232f-5d17-a4ea-fa732665bcce |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 862b9dcb-de71-52df-bd39-5bf485719e9c |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Drawing number
text | 4165272a-d0e4-5f68-94da-30a6252cc8bf |  | textbox | Sprinklers rough in (ENT-004) date completed
text | 1bd3d292-089d-5e8c-8b83-a84f68e20e0c |  | textbox | Sprinklers fit off (ENT-004) date completed
text | 58e7d914-016a-5f41-8d2f-cdb7eaddbc87 |  | textbox | Sprinklers control valves (ENT-003) date completed
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-sectioned |  |  | checklist | ENT-003 - Sprinkler control valves |  |  |  |  | Yes | ENT-003 - Sprinkler control valves | a27ba36f-5063-4f38-962f-291355faa72b
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Specification reference checked
label | 7fd2346e-ae50-5828-b36b-659827408fe1 |  | note | Specification Ref: AS:2118 and drawing
checkpoint-status |  |  | checkpoint | Valves and valve monitors installed
checkpoint-status |  |  | checkpoint | Pressure switches supplied and operable
checkpoint-status |  |  | checkpoint | Pressure gauges fitted
checkpoint-status |  |  | checkpoint | Drains connected
checkpoint-status |  |  | checkpoint | Statutory Labelling
checkpoint-status |  |  | checkpoint | Certification
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-flat |  |  | checklist | ENT-010 - Calibration Record x5 |  |  |  |  | Yes | ENT-010 - Calibration Record x5 | a378a27c-2075-41fc-b9cd-404bdd81cba9
checkpoint-status |  |  | checkpoint | 1.Calibration Details - Pass once entered
text | e50dd07d-0f39-563c-b0cb-377323bd82ed |  | textbox | Equipment
text | 86a8e67c-8a73-508e-8d9d-2202a21f3747 |  | textbox | ID Number
text | 39de2782-279f-5ba7-abb9-a1292a2d0880 |  | textbox | Expiry (If applicable)
text | 2dd9f8af-4f95-5c85-b15a-b48cc5f5ff93 |  | textbox | Record Number
text | e3e0274a-2b85-546c-a04e-3631def26615 |  | textbox | Date Calibrated
checkpoint-status |  |  | checkpoint | 1.Calibration Details - Pass once entered
text | c08ea061-133e-5d72-b055-1eda289b2751 |  | textbox | Equipment
text | e0913397-0ccf-5767-841e-d15b671f7158 |  | textbox | ID Number
text | 73beca9b-b3e7-549c-9e23-070e3805afab |  | textbox | Expiry (If applicable)
text | c24fb30c-f1b0-5dda-8001-5b8f66d5c093 |  | textbox | Record Number
text | d999255f-437f-575c-b7a7-e999861ec40c |  | textbox | Date Calibrated
checkpoint-status |  |  | checkpoint | 1.Calibration Details - Pass once entered
text | a8505f93-73b8-5b18-84d5-c88c0ab02efd |  | textbox | Equipment
text | 37e99888-7fb1-5cb9-a6d9-3922c28ffaa0 |  | textbox | ID Number
text | d44eb946-3d4f-5e36-ab5b-42e549cc10e4 |  | textbox | Expiry (If applicable)
text | 00e394a9-74f2-516c-96a3-0e55e8f1b04e |  | textbox | Record Number
text | 68cfed05-5d29-5112-9d70-c5e2967d85e1 |  | textbox | Date Calibrated
checkpoint-status |  |  | checkpoint | 1.Calibration Details - Pass once entered
text | 366efd7d-b2ee-5fdd-be85-184e405dfee7 |  | textbox | Equipment
text | 2ed5ce0b-90d7-5aaf-8e5d-df7f26040d5f |  | textbox | ID Number
text | 6876ff2f-3133-530e-8c30-32634671a104 |  | textbox | Expiry (If applicable)
text | 2e07b009-8608-5e23-a47f-e656a0c7a823 |  | textbox | Record Number
text | 6effbabd-e631-5096-a127-8841d34a3efd |  | textbox | Date Calibrated
checkpoint-status |  |  | checkpoint | 1.Calibration Details - Pass once entered
text | 19ff318f-f1b2-5e85-827c-0e48549dc191 |  | textbox | Equipment
text | 888c23b0-1eaf-5330-b701-903e5eca12c7 |  | textbox | ID Number
text | 6f2ad8b9-64a1-558f-aa98-03ccf4667fd3 |  | textbox | Expiry (If applicable)
text | 3e91cc4c-4c03-5388-a7b5-e3cb62358daf |  | textbox | Record Number
text | e335331b-aa8c-5784-af69-8a820ebc8a14 |  | textbox | Date Calibrated
checkpoint-status |  |  | checkpoint | Sign-Off Records completed
label | 148fae3a-b3be-5f93-8949-4ec30319e78e |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 18a81e3e-e126-5c84-85e4-7367aa8f406f |  | button | Entire Fire Signature Sign-Off added below | Yes,No
checklist-sectioned |  |  | checklist | ENT-015 - Fire Electrical Commissioning Report |  |  |  |  | Yes | ENT-015 - Fire Electrical Commissioning Report | a7e122a5-4c8d-414d-ae48-209199c945b0
checkpoint-group |  |  | section | Pre-Start
checkpoint-no-status |  |  | checkpoint | Pre-Start
text | 0dbb8c89-c15b-5aa1-a3a4-fc268496776b |  | textbox | drawing reference
text | 332ba3b9-2424-5951-8c66-1483634ddfd5 |  | textbox | level and area
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Secure cabinet
label | 15a4766a-7431-54fb-bd3a-a06b1464fd74 |  | note | Specification Ref: drawing
checkpoint-status |  |  | checkpoint | Extinguishers installed
label | 3f20d2ef-0118-5e04-a07e-e20d2c0a7e6b |  | note | Specification Ref: drawing & AS:2444
checkpoint-status |  |  | checkpoint | Signage to meet code compliance
label | b47a73fd-f5a0-5c44-851f-fd193686199c |  | note | Specification Ref: drawing & AS:2941
checkpoint-status |  |  | checkpoint | Hangers location and spacing
label | bbb3dc99-0a66-564a-8c88-580387143990 |  | note | Specification Ref: drawing & AS:2941
checkpoint-status |  |  | checkpoint | Fire blankets
label | 9b4bf26c-f2f8-51e9-843a-b0557472976e |  | note | Specification Ref: AS:2444
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | da196ddf-04a6-5265-b8bb-c5d0010716af |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 4fff586b-2aff-51a0-b6a6-40c75be7a998 |  | button | Entire Fire Signature Sign-Off added below | Yes, No
checklist-sectioned |  |  | checklist | ENT-014 - Site Works Completion Summary (Fire Electrical) |  |  |  |  | Yes | ENT-014 - Site Works Completion Summary (Fire Electrical) | ba932c0c-39ff-4cc2-ba9c-95468fad6d4a
checkpoint-group |  |  | section | Completion Summary
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | a84dacde-55b6-5fcc-afd1-6f8493a6109a |  | textbox | Date completed
text | 69cff76b-cfc8-588e-ada7-16f250d3c108 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 1f7d7fd2-8d75-5d8d-b461-841c03a0dc03 |  | textbox | Date completed
text | d1a4a47c-a9e6-5196-980e-952b958118d4 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | ae53dd38-0c4b-5f42-99ae-2decc6af48fe |  | textbox | Date completed
text | 51896e69-2859-5f80-a231-3019f0c44001 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 5d786883-91b2-54d5-bc90-1148fb196cbf |  | textbox | Date completed
text | 1e406474-b705-5ac7-8657-58bd789b0ed5 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | d7387e0b-a62a-5162-8916-68d4c3bb1696 |  | textbox | Date completed
text | b6ee6779-f8b5-59a4-83d0-c55fe61a5486 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 2b0c026d-6884-5ec0-a733-d5f9d447fa4d |  | textbox | Date completed
text | 06e57656-effe-5c66-8e32-6aaa1fb45e8c |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 2e0270e2-fad1-5d76-9472-c65f247763fd |  | textbox | Date completed
text | c4b27915-7f5d-53ae-bcd8-626084c7448b |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | f67bfa59-736f-5eea-9257-d57d00bd5454 |  | textbox | Date completed
text | 45c0810a-24da-5f8f-bda5-f9e2d074d498 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 1bd1751e-8bfb-51b3-b997-76c8246b869d |  | textbox | Date completed
text | 0c4eca1a-89bc-5019-b1ba-4dd61f7a1991 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 00d29f92-b110-5ec3-8949-9373c0ff8a09 |  | textbox | Date completed
text | c2680019-fcb3-5a0d-a877-9159917bfb3e |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 5ed7b6ef-0d01-5432-8a29-e4104f593016 |  | textbox | Date completed
text | 9e2c9647-c226-5eaa-a54d-7dfe8b349a2e |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | 6bb9af11-8e0d-56f9-b3e1-97c88e5f6bcd |  | textbox | Date completed
text | c3bfac09-e95c-5cbf-b215-1037593118f0 |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
text | d29a6b68-55da-5280-8a46-a44e6d9583b5 |  | textbox | Date completed
text | 6676586e-ce64-552a-91ab-832e04fab58d |  | textbox | Level and/or area
checkpoint-status |  |  | checkpoint | Electrical Rough in (ENT-013)
checkpoint-status |  |  | checkpoint | Electrical Fit off (ENT-013)
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Sign-Off Records completed
text | 17343227-0e7b-5e8d-8680-a1442ee52690 |  | textbox | Date completed
label | ab2c69cf-1165-5b16-bb08-6a01df3528bc |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 50417a4e-ee2d-59af-990f-0feb15645830 |  | button | Entire Fire Signature Sign-Off added below | Yes,No
checklist-sectioned |  |  | checklist | ENT-001 - Inspection and Test Plan Schedule |  |  |  |  | Yes | ENT-001 - Inspection and Test Plan Schedule | cf28ff03-d498-40fa-8a26-e55e722f6e73
checkpoint-group |  |  | section | Design
checkpoint-status |  |  | checkpoint | Hydraulic Calculations
label | 45c8d088-7bba-5fe3-8183-f6ac763d2971 |  | note | Works By: Entire
label | e8ad2bbe-9b13-5951-ae0e-572ff79bbbdf |  | note | Entire: Review/Approve & Submitted
label | 8fdf877f-9dbc-55b5-a39a-e2baeb3d7809 |  | note | Consulting Engineer: Review/Approve
label | 580c3bd6-6965-5ad0-a33c-4713c73b6add |  | note | Builder: Review/Approve
label | c8482f73-9688-561e-888e-4645ecdad72c |  | note | Acceptance Criteria: AS:2118
checkpoint-status |  |  | checkpoint | Gaseous System Design
label | 656f3f3d-26f1-577e-bfbc-0d5e7d559a7c |  | note | Works By: Entire
label | c15c65ea-49f1-5d9b-b4fd-d79aa24b943b |  | note | Entire: Review/Approve & Submitted
label | ed2ba984-9790-576b-bc86-3072a94d1852 |  | note | Consulting Engineer: Review/Approve
label | fc3c576f-be7e-5f17-b81e-fc2167d527fd |  | note | Builder: Review/Approve
label | 034b99f0-87c1-556f-870c-d79d2c7c7284 |  | note | Acceptance Criteria: AS:14520
checkpoint-status |  |  | checkpoint | Fire Electrical
label | f45de5e4-edb0-5701-8e0b-23845c983906 |  | note | Entire: Review/Approve & Submitted
label | 3cdab5ca-0a2b-5f4d-91fb-fae2b7fb9b2a |  | note | Consulting Engineer: Review/Approve
label | de2a8653-a27a-5087-a524-e06766b108c5 |  | note | Builder: Review/Approve
label | 9afcb3e2-a9cc-5459-bcff-fbad1327c896 |  | note | Acceptance Criteria: AS:1670, AS:1668, AS:3000
checkpoint-group |  |  | section | Drafting
checkpoint-status |  |  | checkpoint | Drafting sprinkler
label | fde0d80d-875e-50dc-903b-f5fbc5625d67 |  | note | Works By: Entire
label | 10190b7e-3040-53f0-b0a4-3e0af8f62e25 |  | note | Entire: Review/Approve & Submitted
label | bdbae0d6-3246-56c5-a04e-0b86a5e7e2b5 |  | note | Consulting Engineer: Review/Approve
label | 4c49db89-4114-57ca-8f14-2a3b6848ceb1 |  | note | Builder: Review/Approve
label | 09df63ec-ef78-5052-b107-ed1e2b5711e8 |  | note | Statutory Authority: Inspect & Review/Approve
label | e1ab5653-ca13-5e85-9b77-5c8c5395cdab |  | note | Acceptance Criteria: AS:2419, AS:2441
label | b0881f5c-cbc8-53a8-99ab-366af2b04255 |  | note | QC Form: Drawing Register
checkpoint-status |  |  | checkpoint | Drafting Gaseous Suppression
label | e66a100e-5f33-54ee-a2da-818dee173d6d |  | note | Works By: Entire
label | fd41aa33-87b1-5086-832f-955c03ca18ce |  | note | Entire: Review/Approve & Submitted
label | bfd1ae3c-3993-5558-960d-8cfa7517e1d5 |  | note | Consulting Engineer: Review/Approve
label | de26dec9-dbd1-5656-9ec1-eecbcc6d37ad |  | note | Builder: Review/Approve
label | 69d354e1-851f-52c4-8556-1ec8c0b206c2 |  | note | Statutory Authority: Inspect & Review/Approve
label | 9fb98cbb-0a82-5e4d-a0b1-e2b997b41434 |  | note | Acceptance Criteria: AS:4214
label | 417f5ae0-501a-57df-8f1a-c11e28e10faf |  | note | QC Form: Drawing Register
checkpoint-status |  |  | checkpoint | Drafting Fire Electrical
label | 09f163d5-3bf7-56cd-9399-eab269c9441d |  | note | Works By: Entire
label | deeb0e3b-19c5-5ddc-add1-316abdbb000f |  | note | Entire: Review/Approve & Submitted
label | e28c4e60-a31d-5816-90d4-311724c4284a |  | note | Consulting Engineer: Review/Approve
label | 4a0ad159-9398-5f07-89bf-aa6cd2c9b52f |  | note | Builder: Review/Approve
label | 96ce920c-b88d-597f-b630-b62c8fbf8a5c |  | note | Statutory Authority: Inspect & Review/Approve
label | 1a531a7d-72d0-5913-b057-c4aa0bf4d137 |  | note | Acceptance Criteria: AS:1670, AS:1668, AS:3000
label | 9509b845-e432-5575-9450-f9c3ebe87c34 |  | note | QC Form: Drawing Register
checkpoint-group |  |  | section | Samples
checkpoint-status |  |  | checkpoint | Sample Tech Data
label | 23ae9678-4fed-553c-8598-70b5c9a81460 |  | note | Works By: Entire
label | bb380afd-8293-5c55-891c-c5651e785309 |  | note | Entire: Review/Approve & Submitted
label | d0a18b74-419c-5bf5-b87f-c67501f6cba7 |  | note | Consulting Engineer: Review/Approve
label | cc3ec748-a1c9-5234-99e4-047bceedf0fb |  | note | Builder: Review/Approve
label | 85f4e672-feaf-586b-8a4a-13c12a5f840a |  | note | Acceptance Criteria: Specification
label | 1c44bf9c-55e7-5faa-be5c-f77de887f65f |  | note | QC Form: Sample Register
checkpoint-group |  |  | section | Off-Site Manufacture
checkpoint-status |  |  | checkpoint | Fire pumps and tanks
label | 98267fec-fd78-54ad-b5a2-b696a5eefdd4 |  | note | Works By: Supplier
label | 4070eda4-8715-5990-9789-9e15d7760d8f |  | note | Entire: Review/Approve & Submitted
label | 33a56fbd-e227-5584-a22e-c4c9adfd0dcc |  | note | Consulting Engineer: Review/Approve
label | b9d2c869-bb4d-51f8-aec9-2d86ecdee7cb |  | note | Builder: Review/Approve
label | e6aea355-0670-5baf-9338-a2c5a96b3dca |  | note | Acceptance Criteria: AS:2941
checkpoint-status |  |  | checkpoint | Fire Indicator Panel
label | 14cd2d35-cfc7-54f3-96cc-9e8a0a98d742 |  | note | Works By: Supplier
label | 601fee0d-4357-5742-94d1-244c4551f7ce |  | note | Entire: Review/Approve & Submitted
label | 3368fe91-725b-5aaf-91f3-55c7e29f669a |  | note | Consulting Engineer: Review/Approve
label | 7d7f071f-fb21-5a78-bfbe-34a71f86a1cc |  | note | Builder: Review/Approve
label | 2d0f4782-8517-56a4-9819-818c46776720 |  | note | Acceptance Criteria: AS:1670, AS3000
checkpoint-group |  |  | section | Incoming Inspection
checkpoint-status |  |  | checkpoint | Sprinkler pipe
label | 37578873-4623-5381-bc57-c0bf8de775a0 |  | note | Works By: Entire
label | 8d83f024-486d-5180-b408-2951c5d15a69 |  | note | Entire: Review/Approve & Submitted
label | 270f663f-8fec-5e14-8774-721b7f0ef348 |  | note | Consulting Engineer: Review/Approve
label | 1b2cb0c6-ec9d-5d54-a624-e3d8d0a906e2 |  | note | Builder: Review/Approve
label | 257d2e33-8234-5657-9306-247dc158f242 |  | note | Acceptance Criteria: AS:2118
label | 1b8bb2f6-49cf-54cc-952c-6c5a9b43b381 |  | note | QC Form: ENT-006 Hydrants and hosereels
checkpoint-status |  |  | checkpoint | Fire pumps and tanks
label | d51e2e9b-71c3-5e3a-8fc4-f2a64d306477 |  | note | Works By: Entire
label | a4ecbb38-d212-5bf9-a7b2-74129d4051ec |  | note | Entire: Review/Approve & Submitted
label | 365c30e0-880d-5b96-aa63-83d03b2d6e0b |  | note | Consulting Engineer: Review/Approve
label | a1a2bc28-4dae-5fb4-be26-1a464717e1cc |  | note | Builder: Review/Approve
label | 053e857f-174b-5c54-aaef-87b17b126517 |  | note | Acceptance Criteria: AS:2941
label | 08061eb6-6b66-5c43-87fe-ecf8a336110a |  | note
checkpoint-status |  |  | checkpoint | Gaseous Fire Suppression
label | 4f04c0a7-6b99-5f21-9955-b57d46906e75 |  | note | Works By: Entire
label | 44328447-cf41-500a-bd60-809546657722 |  | note | Entire: Review/Approve & Submitted
label | 56834aa9-4a89-57fe-9b9e-10fc6fc1edc5 |  | note | Consulting Engineer: Review/Approve
label | 3e713268-12c9-5507-bffd-1fa105983639 |  | note | Builder: Review/Approve
label | dec1f119-afff-5b21-83b8-03b26b96530a |  | note | Acceptance Criteria: AS:4214
label | 1a93a1a5-ce38-55a2-b079-627378d28906 |  | note | QC Form: ENT-002 - Gaseous Suppression
checkpoint-status |  |  | checkpoint | Fire Electrical
label | 6186d837-197f-598a-8799-6856325c6a0c |  | note | Works By: Subcontractor
label | aa4f2ae0-2d52-55a9-859b-8232af7361cc |  | note | Entire: Review/Approve & Submitted
label | 638e4e36-326c-5d09-91a4-030ae0ec3b40 |  | note | Consulting Engineer: Review/Approve
label | 4c2827e6-715f-546e-966a-111d19644ebe |  | note | Builder: Review/Approve
label | e6fca1e1-b387-55b8-a97c-29314d709920 |  | note | Acceptance Criteria: AS:1670, AS:1668, AS:3000
label | 2f6f3fa8-5b5f-5247-a490-612818bf7887 |  | note | QC Form: ENT-013 - Fire Detection
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Fire Hydrant / Hosereels - Rough-In & Fit-Off
label | 17e6c2da-48ea-582e-ac4b-e27d5262a2ad |  | note | Works By: Entire
label | ba31912b-7036-5a5e-b5e3-58fcb245f0ad |  | note | Entire: Review/Approve & Submitted
label | 8db8b494-8b95-5113-b993-4b80acaaed0e |  | note | Consulting Engineer: Review/Approve
label | 9d06d949-f4dc-5df8-b56e-8a7ef27c4e1a |  | note | Builder: Review/Approve
label | 1d72700a-3676-5c57-b070-4cadbb81f369 |  | note | Statutory Authority: Inspect & Review/Approve
label | 23e27a29-441d-5d99-ab32-e9dc0e00c1e7 |  | note | Acceptance Criteria: AS:2419, AS:2441
label | 6ca88a4b-0503-5a6c-92ca-155715dcaf48 |  | note | QC Form: ENT-004 - Sprinkler rough in and fit off
checkpoint-status |  |  | checkpoint | Gaseous Fire Suppression - Rough-In & Fit-Off
label | bbe201e6-103e-5e79-9dff-83defeef02d5 |  | note | Works By: Entire
label | d4940b4e-b01b-5aac-a1c3-d8b4ea08b323 |  | note | Entire: Review/Approve & Submitted
label | 104215e5-e5bd-5568-8ab0-9e2c5f6a14bc |  | note | Consulting Engineer: Review/Approve
label | 0408e415-eef7-5d93-8b8b-ad312fdae7c4 |  | note | Builder: Review/Approve
label | 3177d3b2-c92f-5094-b9fd-dee77b8524b7 |  | note | Statutory Authority: Inspect & Review/Approve
label | 67f84bb7-7be9-5ee7-a45b-6a8fdb9c1c45 |  | note | Acceptance Criteria: AS:4214
label | 516f16f7-82c5-5824-973d-f3a7c3c69991 |  | note | QC Form: ENT-002 - Gaseous Suppression
checkpoint-status |  |  | checkpoint | Fire Electrical - Rough-In & Fit-Off
label | bb05ea6f-d4c6-5d1a-8a0f-b1fdf19de11b |  | note | Works By: Subcontractor
label | 7fe467f1-f77e-55fe-967c-33e75e326d41 |  | note | Entire: Review/Approve & Submitted
label | b68d2be8-9a7b-57e1-a09d-f6aee890b0c2 |  | note | Consulting Engineer: Review/Approve
label | 5a248740-69cf-522c-b0e8-488520da5e61 |  | note | Builder: Review/Approve
label | be37999a-60d6-5537-9139-0c1e74a1ebd2 |  | note | Statutory Authority: Inspect & Review/Approve
label | 061f156c-efe8-5123-9ecd-b76d6aeefe90 |  | note | Acceptance Criteria: AS:1670, AS:1668, AS:3000
label | fa7883d7-533a-586e-804e-f2436190acf6 |  | note | QC Form: ENT-013 - Fire Detection
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Fire Hydrant / Hosereels
label | 688c2436-dc2e-57c0-a50d-0c6f39324d68 |  | note | Works By: Entire
label | 8f32c9e6-4aa0-59df-bc38-2daa7e1c16c7 |  | note | Entire: Review/Approve & Submitted
label | f26160bf-818f-5856-ae78-dd00706a9e32 |  | note | Consulting Engineer: Review/Approve
label | 5b48124a-bf12-5a82-801f-9666e8fbf82e |  | note | Builder: Review/Approve
label | 7667d04f-0b3a-51f7-bbc9-7d0604446a56 |  | note | Statutory Authority: Inspect & Review/Approve
label | 12e48b55-7d16-5a58-84e5-e47f134de4cd |  | note | Acceptance Criteria: AS:2419, AS:2441
label | 3de4be80-e3fb-58cf-b7dd-7ae312fab300 |  | note | QC Form: ENT-006 - Hydrants & Hosereels
checkpoint-status |  |  | checkpoint | Gaseous Fire Suppression
label | 91cf40d1-4226-5e3f-9236-8a3d8363c36a |  | note | Works By: Entire
label | 9110d328-a624-5f54-bf47-15e41a5c5240 |  | note | Entire: Review/Approve & Submitted
label | 01c61301-d514-5ebf-a58f-c615638a5d38 |  | note | Consulting Engineer: Review/Approve
label | 6924bffc-e133-5539-ac87-38cade25c962 |  | note | Builder: Review/Approve
label | a8ec70e1-448f-5dff-a4c2-77f73d2d4808 |  | note | Statutory Authority: Inspect & Review/Approve
label | 898bbc1f-c475-50dd-8254-81934c528c05 |  | note | Acceptance Criteria: AS:4214
label | bb6bdda6-faf3-5b8a-ad16-5f10ae1150f3 |  | note | QC Form: ENT-002 - Gaseous Suppression
checkpoint-status |  |  | checkpoint | Fire Electrical
label | 361f8638-7390-5f46-bc5d-5829c0d16677 |  | note | Works By: Subcontractor
label | 2000dc9b-fa4d-5fab-b34e-1c52cdc097c4 |  | note | Entire: Review/Approve & Submitted
label | c8755cfe-581e-561c-be90-87dbbe482a39 |  | note | Consulting Engineer: Review/Approve
label | 8ec356ae-046a-53ff-bd2b-6dca00b5e8fb |  | note | Builder: Review/Approve
label | 868e546d-c9ff-5334-b3ed-8a234452aae2 |  | note | Statutory Authority: Inspect & Review/Approve
label | 460d6d04-a6a4-5113-8c2f-929265242390 |  | note | Acceptance Criteria: AS:1670
label | 3b2670dd-9469-52d3-9e17-2504ea15e437 |  | note | QC Form: ENT-015
checkpoint-status |  |  | checkpoint | Interface Checks - Mechanical / Fire
label | ef21266a-041d-5736-a314-66adb2d10073 |  | note | Works By: Entire
label | 637adf35-6c4b-506b-a6aa-a85c88d452e3 |  | note | Entire: Review/Approve & Submitted
label | 860480b3-4788-5ea8-8939-99fa023d604b |  | note | Consulting Engineer: Review/Approve
label | bb807e05-5155-5827-943a-116722144b52 |  | note | Builder: Review/Approve
label | d8c45648-e4a7-55e9-9e57-ae8f370ef9fb |  | note | Statutory Authority: Inspect & Review/Approve
label | 53733eb7-9383-5298-98d9-9817d3dd0ca2 |  | note | Acceptance Criteria: AS:1670, AS:1668
label | cfda4210-a2a2-580a-95c0-60d84f47c9e6 |  | note | QC Form: ENT-015
checkpoint-status |  |  | checkpoint | As-Installed Drawings and - Manuals (inc. Test Data)
label | 237a8bb0-6ded-553b-a480-1ca9111c1444 |  | note | Works By: Entire
label | 9b69366d-cc8d-5de1-bd6e-65ea1e5333cb |  | note | Entire: Submitted
label | 78c98269-721f-59f1-9cec-0008e9775ee2 |  | note | Consulting Engineer: Inspected & Review/Approve
label | af46a58b-16c0-536e-8b77-bfb4bb909844 |  | note | Builder: Inspected & Review/Approve
checkpoint-status |  |  | checkpoint | Final Defects List
label | 2d513a53-3f59-5e2b-b3bf-79804e097a78 |  | note | Works By: Entire
label | 11a0744a-9829-51b6-97c5-c3d65bb9f519 |  | note | Entire: Inspected
label | 102b3e75-a6ca-5b21-a499-1e56ddd4400a |  | note | Consulting Engineer: Inspected & Review/Approve
label | 66d2d995-891e-56a0-94e2-6926d2c48c88 |  | note | Builder: Inspected & Review/Approve
checkpoint-group |  |  | section | Defects Liability & Warranty
checkpoint-status |  |  | checkpoint | Entire to Provide Servicing information for Defects Liability Period
label | 64f446e0-31f4-52ee-a535-78d2d61efd3f |  | note | Works By: Entire Service Department
label | 9e9f7162-be5c-52da-b6c5-e6a2aa08925a |  | note | Entire: Provide
label | e08e8d6d-c198-5934-83cc-89fbf35795e9 |  | note | Builder: Review/Approve
label | 4d1fac10-c4bd-5896-b7dd-241370418448 |  | note | Acceptance Criteria: AS:1851.3
checkpoint-status |  |  | checkpoint | Entire to Provide Warranty Information
label | cc91d418-5b30-5a1c-a542-a905e411ab86 |  | note | Works By: Entire Service Department
label | e7feb7a2-ebde-5f7a-ace0-5bee74f505d3 |  | note | Entire: Provide
label | adb2e988-1d9b-59b4-8b82-aa5f54ccdc88 |  | note | Builder: Review/Approve
label | 70f70ff8-911e-5d4b-bb9d-6be779109f47 |  | note | Acceptance Criteria: AS:1851.4
checklist-flat |  |  | checklist | ENT-012 - Register of Non-Conformance Reports x10 |  |  |  |  | Yes | ENT-012 - Register of Non-Conformance Reports x10 | e358c515-a0a8-4737-88c5-5180cc4a429c
checkpoint-status |  |  | checkpoint | Item 1. Pass once entered
text | 8212627f-79fe-5fb0-9df4-59b0c17bc3c6 |  | textbox | Report Number
text | 362c4a59-7004-51af-85b1-ba17c341ebb5 |  | textbox | Description
button | 3681972b-c51e-5115-96c0-62a226c608a1 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | e88d6124-26e7-50c2-ba50-179bcf0b80b3 |  | textbox | Date rectified
button | 2471d0dc-4a29-5c17-ab69-7a1f88a03e97 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 2. Pass once entered
text | 8fcf1691-d1aa-5b77-ad65-76cada3c4c26 |  | textbox | Report Number
text | 240fd65c-554d-5550-abab-18952ba5c6a5 |  | textbox | Description
button | adc24e94-3fa2-5121-9965-a9f66c1ef47e |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 00e86d6d-928f-53b6-b0ed-b1bbab912b65 |  | textbox | Date rectified
button | ff5fade6-2387-5928-821e-5758e565790c |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 3. Pass once entered
text | 05a54e0a-248a-5b63-a5fc-94ac097986f9 |  | textbox | Report Number
text | bf81600a-a5f4-50e0-9444-c6a839710746 |  | textbox | Description
button | 96ecb881-4440-576a-8316-795e5bab46cb |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 002da23c-2db3-5e6b-8b48-8b71721d8f5c |  | textbox | Date rectified
button | b1e6c5f1-ecf8-5bbc-a59b-a3c0e8c30e91 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 4. Pass once entered
text | 24a0c5c8-0c8e-58d4-9980-bc222be8e186 |  | textbox | Report Number
text | 54815767-e39c-504c-9524-ce07bdeb16a0 |  | textbox | Description
button | 2bdcea38-d01e-5250-a109-3c7d9237b0b8 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | b860bf64-f456-5e40-9434-0a1800c417e4 |  | textbox | Date rectified
button | a448c25e-a896-5eb4-bdaf-ecb2af510940 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 5. Pass once entered
text | d807775f-9a1c-5f8d-9bb3-9a27d28a9bbc |  | textbox | Report Number
text | eb7a9271-996f-5fa4-bf23-e54fa7ad0daf |  | textbox | Description
button | cb462ae2-df98-5cf8-b8b8-d0cc95f474e7 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 12b29a19-0423-5432-913c-955ca1c21516 |  | textbox | Date rectified
button | a1898a49-cf14-53e1-90ab-c43ea99c681c |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 6. Pass once entered
text | 1f1b863e-2537-57c1-9b02-893d85be6811 |  | textbox | Report Number
text | ac3ec31b-9b4f-5766-a938-78af9ebdbd6c |  | textbox | Description
button | 499fa4c7-721d-5fdc-871f-a5859b2208e9 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 1e21eb7d-da97-5d6c-82a5-19ec4af0af0d |  | textbox | Date rectified
button | 5644aff4-3927-5871-915f-dd8305212935 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 7. Pass once entered
text | 0c9342c4-a341-59db-96d6-ddeb305b7dfa |  | textbox | Report Number
text | 963320ff-39c0-5a9a-abcc-1026d29c8e58 |  | textbox | Description
button | 5b9e43ea-3d60-53be-91e6-0b65db8766ad |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 956cc285-ed73-5da9-b278-82c09b2dba36 |  | textbox | Date rectified
button | 169b4d40-3c25-53ae-bf57-0e3ec643d4ad |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 8. Pass once entered
text | 3f62506f-5714-5e7d-8fe8-1d6717134b06 |  | textbox | Report Number
text | 1060e3f7-5470-5769-875c-1268a1fe32de |  | textbox | Description
button | 300ad4e2-f911-56cf-8215-cfeed709bda2 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 7fcbef71-d05a-5fa3-91b1-fcc35ee92930 |  | textbox | Date rectified
button | c697df3d-7c42-5753-aaf5-e6de8bbdb4e2 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 9. Pass once entered
text | 372c9257-6d86-523c-a54a-eb2a0b13c8a7 |  | textbox | Report Number
text | 8a2e7900-989e-59d0-87c2-ca63199105e7 |  | textbox | Description
button | 7ad91591-5289-525d-b832-af43faefaef5 |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 5f35c8bd-594f-5021-a919-f9029829ba9a |  | textbox | Date rectified
button | b147a360-6a3c-528f-a9c0-e66910bc3590 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Item 10. Pass once entered
text | 75c4efe8-d6c8-598b-af56-e660e9c54619 |  | textbox | Report Number
text | b9b427c3-079b-5a44-a750-6197a2af3d85 |  | textbox | Description
button | 1c831b88-d311-54af-9577-318cb2c4831c |  | button | Non-Conformance rectified (Input date below) | Yes,No
text | 811da921-6f59-563a-8f10-1257d79de81a |  | textbox | Date rectified
button | bed198b4-f22a-5617-9b67-bbbfed3770d6 |  | button | Non-Conformance approved (Input date below) | Yes,No
checkpoint-status |  |  | checkpoint | Sign-Off Records completed
label | bc3189f8-e5e8-503f-855a-9da5852c88e3 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 16238ba1-bb80-5932-bf8e-1c5f61d9bb7e |  | button | Entire Fire Signature Sign-Off added below | Yes,No
checklist-flat |  |  | checklist | ENT-011 - Action Request Form |  |  |  |  | Yes | ENT-011 - Action Request Form | e75e7050-811a-484d-94dd-772418f903e4
checkpoint-status |  |  | checkpoint | Action Request Details - Pass once entered
text | 731df594-64d0-5a00-ab03-1659e283bddf |  | textbox | Action Request Number
label | 266e8e79-03f6-51d1-911c-1d9889f02ca4 |  | note | This action request is a result of (Tick below)
boolean | 4d8c2431-839a-55f8-aa35-3242b3429c7d |  | tickbox | Audit
boolean | 5d004c0e-af35-56e7-96a6-5354a111bac2 |  | tickbox | Failure
boolean | 7b57986a-e6ab-531e-a180-b3f5d0ca96f6 |  | tickbox | Non-Conformance
boolean | d757ebb8-3a2d-5752-9dc3-adb1d5e88f6e |  | tickbox | Process Improvement Idea
boolean | ee647da9-b02a-5b70-9aad-f30c09cb9ed7 |  | tickbox | Customer Complaint
boolean | c95e063f-09b5-550c-9492-5c8edb2f97b6 |  | tickbox | Corrective/Preventative Action
checkpoint-status |  |  | checkpoint | Description of failure/Non Conformance/Improvement Idea/Customer Complaint
label | c0e839ac-a1bf-581a-8924-8833b6be928e |  | note | Send to Quality Manager for allocation of number and passing to appropriate person for action
text | cc6ce2c7-34e8-534b-a18f-639bb4e295da |  | textbox | Details
text | 20779af3-8455-59d5-b8e1-30537556cf17 |  | textbox | Reported By
text | ea1fcb77-e804-52a6-9ac0-1c29aedca2c6 |  | textbox | Date
checkpoint-status |  |  | checkpoint | Investigate cause and list details
label | 07ade307-d553-5b9a-bd60-f18a165c5d25 |  | note | State action when and if there is a deeper underlying issue or problem
text | 52bb4b22-200f-5050-b738-4d1154851961 |  | textbox | Details
text | 93d45b77-7a87-5acd-b88c-ef4833a3a648 |  | textbox | Assigned To
text | 17b1268a-42c2-5ed1-8e25-95bb3a049a9b |  | textbox | Date of Completion
label | 1b8cc853-fbf2-5e5d-974a-6ac4c692d903 |  | note | Signature Sign-Off attached below
checkpoint-status |  |  | checkpoint | List details of deeper underlying issue and corrective action
label | 76f0173a-0f57-5c7f-b687-169178b08fbc |  | note | This section only applicable if above indicates the need
text | 665aeadc-0470-50a1-8d67-dd0e8643f78c |  | textbox | Details
text | 7834fae7-ac01-5d61-9f95-8f6c859c998d |  | textbox | Assigned To
text | 4f4be5af-d6d2-51f3-812d-6d6efaaf5f5b |  | textbox | Date of Completion
label | 6fd0ce93-45a7-57d9-81a1-dec864bb2279 |  | note | Signature Sign-Off attached below
checkpoint-status |  |  | checkpoint | Verification/Follow-up
text | a36b4509-5225-5bb4-972c-fdbddf3269c9 |  | textbox | Details
text | a21db381-7892-52a0-855d-7c8e98781efa |  | textbox | Assigned To
text | 4996658e-bb92-5373-ba84-e55a95628b3f |  | textbox | Date of Completion
label | 21b8b58f-dd1a-5209-983f-bd849933a557 |  | note | Signature Sign-Off attached below
checkpoint-status |  |  | checkpoint | Sign-Off Records completed
label | 6622263f-20bf-546a-b252-27e2998208d6 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
button | 9383b796-80ad-5d9c-91ea-f3a3254afc65 |  | button | Entire Fire Quality Manager Signature Sign-Off added below | Yes,No
checklist-sectioned |  |  | checklist | ENT-013 - Fire Electrical rough in and fit off |  |  |  |  | Yes | ENT-013 - Fire Electrical rough in and fit off | ea1a9bd7-75c8-481e-b388-1cacbd4241d3
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | 00daef04-519b-51d1-b893-3719f3dfd01f |  | note | Specification Ref: AS:1670, AS:3000, AS:1760, BCA and drawing
text | e08a4705-132a-560f-9deb-991eaf402d62 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | f46559dd-33c8-5c3f-8a23-ff289eee298f |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Cable/Conduit/Tray
label | 5e422259-251a-5cdd-b96c-dda53096187b |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | Fire Devices
label | b0d2b43d-1d24-5056-b720-7de0e948d96e |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-group |  |  | section | Installation Rough-In
checkpoint-status |  |  | checkpoint | Correct cable used (eg Fire rated as required)
checkpoint-status |  |  | checkpoint | Cable Support
checkpoint-status |  |  | checkpoint | Segregation from other electrical services
checkpoint-status |  |  | checkpoint | Type of cable fixing and spacing
checkpoint-status |  |  | checkpoint | No cable joins between equipment
checkpoint-status |  |  | checkpoint | Conduit type
checkpoint-status |  |  | checkpoint | Conduit fixings
checkpoint-status |  |  | checkpoint | MASDS
checkpoint-group |  |  | section | Installation Fit-Off
checkpoint-status |  |  | checkpoint | Sensor locations as shown on drawings
checkpoint-status |  |  | checkpoint | Warden intercom phone locations
checkpoint-status |  |  | checkpoint | Break glass alarm located per drawings
checkpoint-status |  |  | checkpoint | Hold open devices located per drawings
checkpoint-status |  |  | checkpoint | Interface with Mechanical services
checkpoint-status |  |  | checkpoint | Interface with DDC
checkpoint-status |  |  | checkpoint | Sensors fixed correctly
checkpoint-status |  |  | checkpoint | FIP installed & connected
checkpoint-status |  |  | checkpoint | Connection of system to Tyco for Monitoring
checkpoint-status |  |  | checkpoint | MASDS Panel Fit Off
checkpoint-status |  |  | checkpoint | Strobes
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Confirm all devices indicate at FDCIE
checkpoint-status |  |  | checkpoint | Confirm operation of all ancillary functions from FDCIE
checkpoint-status |  |  | checkpoint | FDCIE. Operate each alarm test, isolate and reset for each alarm zone
checkpoint-status |  |  | checkpoint | ASE. Confirm the master alarm facility receives all alarms
checkpoint-status |  |  | checkpoint | ASE. Confirm the master alarm facility receives all alarms
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy - Builder final signature to be attached below if applicable
checklist-sectioned |  |  | checklist | ENT-004 - Sprinkler rough in and fit off |  |  |  |  | Yes | ENT-004 - Sprinkler rough in and fit off | fab2e9c8-bd6c-4943-83f8-16385aefcfef
checkpoint-group |  |  | section | Pre-Start
checkpoint-status |  |  | checkpoint | Specification reference checked
label | 89c6ee46-aab7-55fe-aec2-c6cbd2380290 |  | note | Specification Ref: AS:2118 and drawing
checkpoint-status |  |  | checkpoint | Pipe + Fittings
label | 14e78002-fc6f-525b-b47a-f3185cbb0cf3 |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-status |  |  | checkpoint | Sprinklers
label | 2d89eabf-ba89-5a22-8711-c0521c5fa347 |  | note | PASS if received in good condition - If not FAIL & Attach Photos/Comments below
checkpoint-group |  |  | section | Installation Rough-In
checkpoint-status |  |  | checkpoint | Mains, ranges & riser pipes, flow switch & valves, solenoid drains installed to drawing
checkpoint-status |  |  | checkpoint | Hangers Location
checkpoint-status |  |  | checkpoint | Concealed spaces sprinker heads installed
checkpoint-status |  |  | checkpoint | Outlets capped
label | eb1902d0-1de0-5e58-b008-e0b349c2018f |  | note | Specification Ref: drawing
checkpoint-status |  |  | checkpoint | Pressure test carried out
label | bb61164b-0884-5a4f-b220-6e41a3c35d5b |  | note | Specification Ref: ENT-009
checkpoint-status |  |  | checkpoint | Pentrations sealed
checkpoint-group |  |  | section | Installation Fit-Off
checkpoint-status |  |  | checkpoint | Sprinkler heads fitted to final locations as per coordinated RCP
checkpoint-status |  |  | checkpoint | Pressure test fit off
label | b75395a7-818f-5f23-8479-e7525276208e |  | note | Specification Ref: ENT-009
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Inspected by Independent Certifier - Signature ttached below as applicable
label | e96f9fb2-6403-53bd-b360-b72edf196894 |  | note | Specification Ref: AS:2118 and drawing