## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | HPP-UGL-CIV-GN-GEN-ITP-021 Bollard Installation - Rev.0 | itp |  |  |  |  | HPP-UGL-CIV-GN-GEN-ITP-021 Bollard Installation - Rev.0
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance criteria - Prepare a lot map for traceability of the work area.
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot Map
checkpoint | 1.3 - Confirm Bollard Type
label | Ref docs - Drawings
label | Acceptance criteria - Confirm bollard type as detailed on the drawings.
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 1.4 - Setout bollard location
label | Ref docs - Drawings
label | Acceptance criteria - Setout bollard at locations as detailed on the drawings
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 1.5 - Excavation Permit
label | Ref docs - Drawings
label | Acceptance criteria - Ensure approved excavation permit is in place and review on site – if required
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
section | 2.0 Site Preparation
checkpoint | 2.1 - Location
label | Ref docs - Drawings
label | Acceptance criteria - Confirm location and place setout offset marks
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 2.2 - Underground utilities
label | Ref docs - Drawings
label | Acceptance criteria - Check utilities to avoid footing clashing
button | Acceptance | Yes,No,N/A
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
section | 3.0 Installation Process - In concrete
checkpoint | 3.1 - Anchors
label | Ref docs - Drawings
label | Acceptance criteria - Install specified anchor bolts following manufacturers requirements
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
section | 4.0 Installation Process - In pavement
checkpoint | 4.1 - Excavation
label | Ref docs - Drawings
label | Acceptance criteria - Vacuum excavate site according to bollard specifications (depth and width based on bollard type and use case)
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 4.2 - Placement
label | Ref docs - Drawings
label | Acceptance criteria - Position and secure bollard or sleeve in hole before pouring concrete
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 4.3 - Concrete - footing
label | Ref docs - Drawings
label | Acceptance criteria - Fill N32 concrete around bollard foundation, slope the top of concrete down away from bollard all round
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
section | 5.0 Finishes
checkpoint | 5.1 - Eyelets
label | Ref docs - Drawings
label | Acceptance criteria - Install eyelets in locations shown on drawings
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 5.2 - Concrete - bollard
label | Ref docs - Drawings
label | Acceptance criteria - Fill bollard with concrete – if detailed on the drawings
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
checkpoint | 5.3 - Final Inspection
label | Ref docs - Drawings
label | Acceptance criteria - Inspect bollard and apply touch up paint to any damaged areas
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Checklist
section | 6.0 Acceptance of Works
checkpoint | 6.1 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | ○ HOLD POINT
button | Acceptance | Yes,No,N/A
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT