## Precast Concrete Headwall.
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Culvert Headwall Using a Precast Concrete Headwall |  |  | DN-GD-GP084 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | NO | R | R | H |  |  | W & I | Supplier
2 | Setting Out |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | NO | R | R | H
3 | Prepare the Foundation |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | NO | R | R | H
4 | Install Headwall |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | YES | W(10%) | R | H
5 | Apron Extension (If Required) |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | YES | W(10%) | R | H
6 | Backfilling |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | YES | W(10%) | R | H
7 | Barriers |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | YES | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP084 | YES | W | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Install a Culvert Sock
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Culvert Sock |  |  | DN-GD-GP085 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Base |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP085 | NO | R | R | H |  |  | W & I | Supplier
2 | Install Sock |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP085 | YES | W(10%) | R | H
3 | Outlet Control |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP085 | NO | W(10%) | R | H
4 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In-process | DN-GD-GP085 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Install a Flume
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Flume - Nestable Corrugated Steel or HDPE |  |  | DN-GD-GP086 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | R | R | H |  |  | W & I | Supplier
2 | Trestle Construction (to bridge over low spots) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | R | R | H
3 | Install Flume |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | W(10%) | R | H
4 | Join Flume |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | W(10%) | R | H
5 | Fix Flume to Slope |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | W(10%) | R | H
6 | Align Flume |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | W(10%) | R | H
7 | Outlet Control |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | NO | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP086 | YES | W | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Install a Reno Mattress
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Reno Mattress |  |  | DN-GD-GP087 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | NO | R | R | H |  |  | W & I | Supplier
2 | Prepare Foundation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | NO | W(10%) | R | H
3 | Prepare Wire Basket |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | NO | W(10%) | R | H
4 | Filling the Reno Mattress |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | NO | W(10%) | R | H
5 | Backfilling |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | NO | W(10%) | R | H
6 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP087 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Install a Subsoil Drain Fabric
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install a Subsoil Drain Fabric Wrapped Strip Type |  |  | DN-GD-GP088 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | R | R | H
2 | Prepare Base |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | W(10%) | R | H
3 | Lay Filter Fabric Wrap |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | W(10%) | R | H
4 | Lay Bedding Material |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | W(10%) | R | H
5 | Lay Strip Drain |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | W(10%) | R | H
6 | Outlet Control |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | NO | W(10%) | R | H
7 | Test and Check |  | Sub Sup/Downer Eng | As per Specification | In- process | DN-GD-GP088 | YES | W(10%) | R | H
11 | Spreading Passes 1-2 |  | XXX |  |  |  |  | - | - | - | -
12 | Test and Check |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -

## Install Subsoil Drain Corrugate
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Install Subsoil Drain Corrugated Plastic Type |  |  | DN-GD-GP089 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Design Principles |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | R | R | H |  |  | W & I | Supplier
2 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | W(10%) | R | H
3 | Prepare Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | W(10%) | R | H
4 | Lay Filter Fabric Wrap (if required) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | W(10%) | R | H
5 | Lay Bedding Material |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | YES | W(10%) | R | H
6 | Lay Pipe |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | YES | W(10%) | R | H
7 | Outlet Control |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | W(10%) | R | H
8 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP089 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Line a Channel With Rock Riprap
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Line a Channel With Rock Riprap |  |  | DN-GD-GP090 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare the Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP090 | NO | R | R | H |  |  | W & I | Supplier
2 | Setting Out |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP090 | NO | W(10%) | R | H
3 | Prepare Base |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP090 | NO | W(10%) | R | H
4 | Place Rock |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP090 | NO | W(10%) | R | H
5 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP090 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Removal of High Shoulders
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Removal of High Shoulders |  |  | DN-GD-GP091 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP091 | NO | R | R | H |  |  | W & I | Supplier
2 | Remove EMP (Edge Marker Posts) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP091 | NO | W(10%) | R | H
3 | Cutting Shoulders |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP091 | NO | W(10%) | R | H
4 | Cart Material |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP091 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Repair Broken Kerb and Channel
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Broken Kerb and Channel In Situ |  |  | DN-GD-GP092 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | NO | R | R | H |  |  | W & I | Supplier
2 | Excavation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | NO | W(10%) | R | H
3 | Bae Construction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
4 | Formwork/Boxing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
5 | Concrete |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
6 | Concrete Finishing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
7 | Restore Road Pavement |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
8 | Surfacing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
9 | Restore Grass Berm and/or Footpath |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
10 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP092 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Broken Kerb and Channel Precas
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Repair Broken Kerb and Channel – Pre-cast Block |  |  | DN-GD-GP093 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Prepare |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | NO | R | R | H |  |  | W & I | Supplier
2 | Excavation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | NO | R | R | H
3 | Base Construction |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
4 | Formwork/Boxing (if channel required) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
5 | Kerb Laying |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
6 | Concrete Finishing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
7 | Restore Road Pavement |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
8 | Surfacing |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
9 | Restore Grass Berm and/or Footpath |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
10 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP093 | YES | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client

## Manning of a Checkpoint
|  | INSPECTION & TEST PLAN | [5 empty] | ITP reference: | ITP # 001 | Rev.: | 0 |  | H | Client Rep
|  | Project: | CONOC NETWORK SH001, 083, 085, 086, 087, 088, 090 | [9 empty] | I | Downer Engineer
[13 empty] | W | QA Manager
GENERAL TITLE : |  |  | DRAWING Nos. OR DOCUMENT REFERENCES : |  |  |  | TEST AND INSPECTION CODES: | [5 empty] | R | Surveyor
Manning of a Checkpoint |  |  | DN-GD-GP100 |  |  |  | H = Hold Point – Stop work until seen – Signed Record |  |  |  |  | ` | - | Designer
WORK BY: Downer(or subcontractor named below) | [6 empty] | I = In-process Inspection – Work Continues – Signed Record | [5 empty] | W(90%) | Foreman
KELSO/SKEVINGTONS/South Roads | [6 empty] | W = Witness Inspection – Work Continues – Signature if Witness | [5 empty] | W(10%) | Supervisor
[7 empty] | R = Records Review – Signed Record per package | [5 empty] | W(50%) | Sub Manager
OP. No. | Operation To Be Inspected Or Tested |  | Controlled By : (Position) | Accept / Reject Criteria | Frequency Of Inspection Or Test | Spec. Ref, Procedure Or Method Statement | Records Required | ENGINEER | SUPER VISOR | Downer/ SUB-CON | OTHER |  | W(5%) | Sub Supervisor
1 | Co-ordinating Incident Management (CIMMS) |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | R | R | H |  |  | W & I | Supplier
2 | Preparation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | R | R | H
3 | Manual Traffic Controller |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | YES | W(10%) | R | H
4 | Manual Traffic Controller Operation |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | YES | W(10%) | R | H
5 | Establishment on Site |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | W(10%) | R | H
6 | Inform the Public about Work Procedure and Progress |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | W(10%) | R | H
7 | Media |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | W(10%) | R | H
8 | Incident Reporting |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | YES | W(10%) | R | H
9 | Test and Check |  | Sub Sup/Downer Eng | As per specification | In-process | DN-GD-GP100 | NO | W(10%) | R | H
12 |  |  | XXX |  |  |  |  | - | - | - | -
13 |  |  | XXX |  |  |  |  | - | - | - | -
14 |  |  | XXX |  |  |  |  | - | - | - | -
15 |  |  | XXX |  |  |  |  | - | - | - | -
16 |  |  | XXX |  |  |  |  | - | - | - | -
17 |  |  | XXX |  |  |  |  | - | - | - | -
18 |  |  | XXX |  |  |  |  | - | - | - | -
19 |  |  | XXX |  |  |  |  | - | - | - | -
20 |  |  | XXX |  |  |  |  | - | - | - | -
PREPARED/EDITED BY: |  |  | APPROVED BY: |  | APPROVED BY: |  | COMMENTS:
Zaheed Dalvi |  |  | Andrew Beattie |  | Rowan Tumai
DATE: 13/12/2023 |  |  | DATE: |  | DATE:
On behalf of Downer |  |  | On behalf of Downer / Engineer |  | On behalf of Client