## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - CONOC Operations - Install a Culvert Headwall Using a Precast Concrete Headwall | itp |  |  |  |  | ITP - CONOC Operations (General) - Install a Culvert Headwall Using a Precast Concrete Headwall
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Setting Out
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare the Foundation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Install Headwall
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Apron Extension (If Required)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Backfilling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Barriers
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP084
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Install a Culvert Sock | itp |  |  |  |  | ITP - CONOC Operations (General) - Install a Culvert Sock
checkpoint | 1 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Install Sock
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Outlet Control
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP085
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Install a Flume - Nestable Corrugated Steel or HDPE | itp |  |  |  |  | ITP - CONOC Operations (General) - Install a Flume - Nestable Corrugated Steel or HDPE
checkpoint | 1 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Trestle Construction (to bridge over low spots)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Install Flume
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Join Flume
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Fix Flume to Slope
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Align Flume
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Outlet Control
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP086
label | Records Required - YES
label | ENGINEER - W
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Install a Reno Mattress | itp |  |  |  |  | ITP - CONOC Operations (General) - Install a Reno Mattress
checkpoint | 1 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Prepare Foundation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare Wire Basket
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Filling the Reno Mattress
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Backfilling
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP087
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Install a Subsoil Drain Fabric Wrapped Strip Type | itp |  |  |  |  | ITP - CONOC Operations (General) - Install a Subsoil Drain Fabric Wrapped Strip Type
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Lay Filter Fabric Wrap
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Lay Bedding Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Lay Strip Drain
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Outlet Control
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per Specification
label | Frequency Of Inspection Or Test - In- process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP088
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Install Subsoil Drain Corrugated Plastic Type | itp |  |  |  |  | ITP - CONOC Operations (General) - Install Subsoil Drain Corrugated Plastic Type
checkpoint | 1 - Design Principles
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Lay Filter Fabric Wrap (if required)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Lay Bedding Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Lay Pipe
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Outlet Control
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP089
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Line a Channel With Rock Riprap | itp |  |  |  |  | ITP - CONOC Operations (General) - Line a Channel With Rock Riprap
checkpoint | 1 - Prepare the Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Setting Out
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Prepare Base
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Place Rock
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP090
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Removal of High Shoulders | itp |  |  |  |  | ITP - CONOC Operations (General) - Removal of High Shoulders
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Remove EMP (Edge Marker Posts)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Cutting Shoulders
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Cart Material
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP091
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Repair Broken Kerb and Channel In Situ | itp |  |  |  |  | ITP - CONOC Operations (General) - Repair Broken Kerb and Channel In Situ
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Bae Construction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Formwork/Boxing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Concrete
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Concrete Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Restore Road Pavement
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Surfacing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Restore Grass Berm and/or Footpath
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP092
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Repair Broken Kerb and Channel – Pre-cast Block | itp |  |  |  |  | ITP - CONOC Operations (General) - Repair Broken Kerb and Channel – Pre-cast Block
checkpoint | 1 - Prepare
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Base Construction
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Formwork/Boxing (if channel required)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Kerb Laying
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Concrete Finishing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Restore Road Pavement
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Surfacing
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Restore Grass Berm and/or Footpath
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP093
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - CONOC Operations - Manning of a Checkpoint | itp |  |  |  |  | ITP - CONOC Operations (General) - Manning of a Checkpoint
checkpoint | 1 - Co-ordinating Incident Management (CIMMS)
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Preparation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - R
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Manual Traffic Controller
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Manual Traffic Controller Operation
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Establishment on Site
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Inform the Public about Work Procedure and Progress
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Media
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Incident Reporting
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - YES
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Test and Check
label | Controlled By : (Position) - Sub Sup/Downer Eng
label | Accept / Reject Criteria - As per specification
label | Frequency Of Inspection Or Test - In-process
label | Spec. Ref, Procedure Or Method Statement - DN-GD-GP100
label | Records Required - NO
label | ENGINEER - W(10%)
label | SUPERVISOR - R
label | Downer/ SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT