## General
SECTION 1 – GENERAL DETAILS
Project Name: | Sh1 Shouth Foxton | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558021 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 9500 | [5 empty] | C | Check | ER | Engineers Representative | Luke Cameron | LC
Area/ Sub-System: | Wire Rope Stage 1 SH1 Ch 9270-CH 11295 |  |  | Lot ID Number: | WR01 |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | O2L ITP 6 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Covers all inspection points pre, during and post construction of the road side barriers both W-Beam and Wire Rope | [5 empty] | I | Inspection | PM | Project Manager | Meyer du Plessis | MdP
Discipline: | Road Barriers | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 NZTA M23 | [5 empty] | O | Operation | QE | Quality Engineer | Cody Graham | CG
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor | Richard Wild | RW
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Meyer du Plessis |  |  | Date: | 2024-01-12 |  | W | Witness Point | SV | Surveyor | Stefan Kilian | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Christopher coleman |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Item
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency |  | Inspection Type | Inspection
[8 empty] | Key | By | Checked (PM Initial) | Date
6.0 | Barriers | Final Sign Off | All below requirements are met and approved by ER | Referenced Item numbers as below | Once post construction |  | Hold Point | H | ER
6.1 | Materials
6.1.1 | Documentation Review | Review | All barrier componants comply to the relevant specification as per NZTA M23. | Manufacturers Certificates | Once per supplier |  | Review | R | ER/PM
6.2 | Construction
6.2.1 | Design Revision as required | Design submission & review | Engineer to review and approve | Revised design NTE/NTC | Once per design revision. |  | Review | R | ER
6.2.2 | Barrier set out & review | Site inspection | Engineer to review barrier setout onsite and approve. | Ste inspection form | Once per barrier string |  | Witness Point | W | ER/PM
6.2.3 | Anchor Block Construction | Site Inspection | Engineer to inspect excavated foundation prior to anchor block pour. | Site inspection form | Once per anchor block |  | Hold Point | H | ER
6.2.4 | Concrete Work | Site Inspection | Concrete works shall be constructed to the line and levels detailed on the drawings, and finished to a smooth suface with no significant cracks, spalling or exposed reinforcing. Concrete dockets to be provided to engineer. | Site inspection form | Once per barrier string |  | Witness Point | W | ER/PM
6.2.5 | Marker posts, reflectors and signage | Site inspection | Edge marker posts to be installed along w-beam at standard spacing intervals Wire rope barriers to have reflectorised top caps every 3rd post. Leadign end terminals to have Hazard/width marker where required Wire rope barrier leading end terminals installed with RD6L signage | Site inspection form | Once per barrier string |  | Review | R | ER/PM
6.2.6 | WRB Pull Test | Witnessed pull test | No viusal damage to occur to posts or foundation as a result of the pull test. Any damage is to be rectified prior to sign off & string retested. | Site inspection form | Minimum one test / 100m |  | Witness Point | H | ER
6.2.7 | W-Beam Inspection | Check Sheet | Contractor to provide end terminal check sheet signed by a suitably qualified person. | Barrier Inspection form | One per end terminal |  | Witness Point | W | ER
6.2.8 | As-Built | Survey As-Built | As-built to show Barrier constructed as per design and within tolerences as per m23 | As-Built Data | Once Per String |  | Hold Point | H | ER
COMMENTS
[6 empty] | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: