## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558010 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Engineers Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | O2L ITP 7 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all inspection points pre, during and post construction of the sealing works project wide. | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Sealing | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 & all relative sealing specifications noted within. | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor | Richard Wild | RW
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Sam Christensen |  |  | Date: | 2023-05-10 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Item
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
7.0 | Sealing | Final Sign Off | All below requirements are met and approved by ER | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
7.1 | Bitumen Approval
7.1.1 | NZTA M1: 2022: Bitumen Material Approval | Test Report Review | Bitumen/binder compliant with NZTA M/1 - Table 5.1 | Manufacturers Certificate | Minimum 5 working days prior to construction | Hold Point | H | PM/ER
7.2 | Source Properties
7.2.1 | NZTA M6: 2022: 4.2 Crushing Resistance | Test Report Review | Maximum of 10% fines shall be produced under a load of 230kN. | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.2 | NZTA M6: 2022: 4.3 Weathering Resistance | Test Report Review | The aggregate shall have a quality index of AA or BA | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.3 | NZTA M6: 2022: 4.4 Weak Particles Test | Test Report Review | Note - only required if source properties are disputed. The aggregate shall have a maximum of 1% of unsound materials | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.2.4 | NZTA M6: 2022: 4.6 Polished Stone Value | Test Report Review | Polished Stone Value (PSV) - compliant with NZTA M6: 2022: 4.6 & project requirements | IANZ Lab Report | Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser | Hold Point | H | PM/ER
7.3 | Production Properties |  | Grade 2, 3 & 4 Chip
7.3.1 | NZTA M6: 2022: 5.1 Cleanness | Test Report Review | Cleaness of aggregate samples compliant with NZTA M6: 2022 5.2 Cleanness | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.3.2 | NZTA M6: 2022: 5.2 Size and Shape | Test Report Review | Size and Shape of Aggregate Particles compliant with NZTA M6: 2022: 5.2 Size and Shape | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.4 | Production Properties |  | Grade 5 & 6 Chip
7.4.1 | NZTA M6: 2022 5.3 PSD | Test Report Review | Particle Size Distribution compliant with NZTA M6: 2022 5.1 Table 4 | IANZ Lab Report | Three initially per grade of chip from stockpile, then repeat as follows: 1 test per < 100m3; 2 tests per 100-500m3; or 3 tests per > 500m3 | Hold Point | H | PM/ER
7.5 | Pre-Construction
7.5.1 | Chipseal Design Submission | Design Review | Designer to approve sealing design | NTC confirming acceptance | Once per seal design | Hold Point | H | PM/ER
7.5.2 | Pre-seal Inspection | Visual Site Inspection | Basecourse (prime seal) - To be prepped to a tight, uniform surface, swept to remove any dust and other foreign objects. Prime or previouis seal - Full surface swept with a power broom to remove excess chip and any other foreign material | Site Inspection Form | Prior to construction of sealing coat | Hold Point | H | PM/ER
7.5.3 | Pre-seal testing | Degree of Saturation test TNZB/02 Clause 12 | Compliant as per TNZ B/02 Clause 12 DOS at each of minimim 5 points < 80% | Testing results | Minimum 5 tests per 1000m2 | Hold Point | H | PM/ER
7.6 | Construction
7.6.1 | Working Temperature Prior to Spraying | Onsite check & Document | The road shall be reasonably dry before the binder is applied, and no spraying shall be carried out when the air temperature measured within the confines of the sealing course is below 10 degrees C in the shade | Sealing Checklist | Prior to Spraying | Review | R | PM/ER
7.6.2 | Application rate for Bituminous Seal | Onsite check & Document | Sprayed Rate measured compliant with the Approved Seal Design | Sealing Checklist | Per spray run | Review | R | PM/ER
7.6.3 | Chip Spread Rate | Onsite check & Document | Sealing Records showing compliant spread rate of the chips based on C0213.5;TNZ P/3: 1995-21 Cl. 28 | Sealing Checklist | 1 test per chip grade per 2,000m2 seal constructed | Review | R | PM/ER
7.6.4 | Rolling Requirements | Onsite check & Document | Sealing Records showing compliant rolling requirements based on C0213.5;TNZ P/3: 1995-22 ROLLING | Sealing Checklist | Per Shift | Review | R | PM/ER
7.6.5 | On Site Checks - Post PTR and Brooming | Onsite check & Document | Surface Compliant and Surplus chip removed | Sealing Checklist | Prior to construction of next layer/ Prior removal of the temporary speed restriction signs | Review | R | PM/ER
COMMENTS
[6 empty] | ☐ Yes | ☐ No | Date: