## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558010 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Engineers Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | O2L ITP 9 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all inspection points pre, during and post construction of all Road Signs project wide. | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Road Signs | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 & all relative specifications noted within. | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor | Richard Wild | RW
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Sam Christensen |  |  | Date: | 2023-05-10 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Items
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
9.0 | Road Signs | Final Sign Off | All below requirements are met and approved by ER | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
9.1 | Materials | Pre Installation - Compliance Check | All materials to comply with relevent clause under TNZ P24 2020 | Manufacturers Cetificate | Once Per Supplier | Review | R | ER
9.2 | Installation
9.2.1 | Delivery | Inspection upon delivery | Signs to be checked for any damage upon delivery, return to manufacturer if damaged. | Delivery Checklist | Once Per Delivery | Check | C | PM/PS
9.2.2 | Positioning & Orientation | Onsite inspections and checks | Positioning & Orientation to comply to TNZ P24 2020 Clause 7.3 & 7.4 | Site Checklist Form | Once per sign installation | Inspection / Review | I / R | PM/PS/ER
9.2.3 | Sign Support Selection | Onsite inspections and checks | Supports to comply as per TNZ P24 2020 - Table 7.1 | Site Checklist Form | Once per sign installation | Inspection / Review | I / R | PM/PS/ER
9.2.4 | Foundations | Onsite inspections and checks | Foundations to comply as per TNZ P24 2020 Clause 7.7 Foundations | Site Checklist Form | Once per sign installation | Inspection / Review | I / R | PM/PS/ER
9.2.5 | Daytime Survey | Post construction survey | (a) The actual sign face is free of environmental soil such as mildew or lichen growth (b) No physical damage has affected or risked sign face readability and or sign integrity (c) No vegetation or other structure impedes line of sight or visibility to the sign face (d) The sign is free of any graffiti or the aftermath of previous poor cleaning action (e) Sign supports and foundations are sound and maintain correct sign presentation (f) The need for the sign still exists – for example a speed reduction has not negated the need for a posted curve warning speed (g) Confirming that the physical sign and its structure remain suitable for purpose or note that some repair should be undertaken (h) Any fluorescent sign, deemed to require a higher level of day time visibility through its fluorescing colour feature, maintains a satisfactory performance e.g. Signs for active users (schools, pedestrians, cyclists). | Survey Checklist | Once per completed section of works | Inspection | Inspection | PM/ER
9.2.6 | Nighttime Survey | Post construction survey | (a) Overall any sign or part of a traffic sign (eg guide sign), especially when set in a disadvantaged position, is performing suitable for purpose, exhibiting an even level of retroreflectivity across the face of the sign to ensure that an appropriate level of readability is achieved across the entire sign throughout the approach (b) The orientation of the sign face is such that no specular (mirror) retroreflection creates an over bright glare effect that interferes with sign recognition/readability (c) At the threshold of retroreflectivity the traffic sign presents a level of visibility that ensures a driver becomes aware the sign is present – before actual readability is possible (d) That any previous maintenance completed during daylight hours has not damaged retroreflectivity at night – for example poor graffiti cleaning (e) Traffic signs remain fully effective and suitable for the purpose for which they were installed | Survey Checklist | Once per completed section of works | Inspection | Inspection | PM/ER
COMMENTS
[6 empty] | ☐ Yes | ☐ No | Date: