## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | [6 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Cust. Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: |  |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all planning and documnentation required prior to construction works commencing. | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Documentation and Planning | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 & relevant TNZ / NZTA Documents | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : N/A | [5 empty] | S | Subcontractor | SP | Supervisor
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sam Christensen |  |  | Date: | 2023-04-19 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Documentation and Planning
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
1 | Documentation and Planning | Final Sign Off | All below HP Closed | Referenced Item numbers as below | Once prior to works commencing | Hold Point | H | ER
1.1 | Contract Obligation | Project Management Plan | Approved by CR | Signed CP | Prior to Work Commencing | Review | R | ER
1.2 | Contract Obligation | Health and Safety Management Plan | Approved by CR | Signed HSMP | Prior to Work Commencing | Review | R | ER
1.3 | Contract Obligation | Quality Management Plan | Approved by CR | Signed QMP | Prior to Work Commencing | Review | R | ER
1.4 | Contract Obligation | Communication Management Plan | Approved by CR | Signed CSCMP | Within 2 weeks of physical works commencing on site | Review | R | ER
1.5 | Contract Obligation | Environmental Management Plan | Approved by CR | Signed ESMP | Within 2 weeks of physical works commencing on site | Review | R | ER
1.5.1 | Contract Obligation | Sediment Control Plan | Approved by CR | Approved Control Plan | Prior to Work Commencing | Hold Point | H | PM
1.6 | Contract Obligation | Inspection and Testing Plan | Approved by CR | Approved ITP | Prior to Work Commencing | Review | R | ER
1.7 | Contract Obligation | Traffic Management Plan (TMP) | Approved by TMC & CR | Approved TMP | Prior to Work Commencing | Hold point | H | PM
1.8 | Contract Obligation | Construction Programme | Approved by CR | Gantts Bar Chart | Prior to Work Commencing | Review | R | ER
COMMENTS | [8 empty] | Checked (PM Initial) | Date
[5 empty] | Customer Release Granted: | ☐ Yes | ☐ No
Certificate Number: