## General
SECTION 1 – GENERAL DETAILS
Project Name: | Ōtaki to Levin Saftey Improvements | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | [6 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | 345084-NZ Transport Agency | [5 empty] | B | Report by Breach | CM | Construction Manager | Chris Colman | CC
Contract Number: | NZTA 6581 | [5 empty] | C | Check | ER | Cust. Representative | Luke Cameron | LC
Area/ Sub-System: | Ōtaki to Levin State Highway 1 |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[7 empty] | E | Examine | MC | Material Controller
ITP Number: |  |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | Glen Flint | GF
ITP Description: | Covers all inspection points pre, during and post construction of the earthworks phase including subgrade construction. | [5 empty] | I | Inspection | PM | Project Manager | Sam Christensen | SC
Discipline: | Earthworks | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Richard Wild | RW
Specification: | Consultants Standard Technical Specifications TS1 TNZ F/1 NZS 4402 NZS 4407 | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | For construction drawings : | [5 empty] | S | Subcontractor | SP | Supervisor
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Sam Christensen |  |  | Date: | 2023-04-19 |  | W | Witness Point | SV | Surveyor | Andre Wilkes | AW
Quality Specified: | Project Technical Specifications cross referencing relevant to Transit New Zealand (TNZ) & NZTA Z8:2022 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Tipping |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Earthworks
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection
[7 empty] | Key | By | Checked (PM Initial) | Date
2 | Earthworks | Final Sign Off | All below requirements are met and approved by CR | Referenced Item numbers as below | Once post construction | Hold Point | H | ER
2.1 | Source Properties Imported Fill
2.1.1 | Bearing Strength | Sampled from truck or stockpile onsite as per NZS4402 clasue 1.6.3 & 1.6.4 | CBR > 40 as per NZS4402 | IANZ Lab Report | Once per stockpile | Review | R | ER
2.1.2 | Weathering Resistance | Samples to be sent to lab for testing or provided by quarry | QI = AA, AB, AC, BA, BB, CA, CB as per NZS4407 1991 Test 3.11 | IANZ Lab Report | Once per stockpile | Review | R | ER
2.1.3 | Grading Limits | Samples to be sent to lab for testing or provided by quarry | Grading within envelope as per table 302.2.3 (Technical Specifications) Tested in accordance with NZS4407 1991 Test 3.8.1 | IANZ Lab Report | Once per stockpile | Review | R | ER
2.2 | Construction
2.2.1 | Topography Survey | Pre-Cut/Fill Survey | Within Design Expectations | Survey Data | Once per construction area | Action | A | SV
2.2.2 | Survey Set out | Onsite Setout | Survey have setout using pegs or similar, the location of the pavement in regards to horizontal and vertical alignment, as per design. | N/A | As required | Action | A | SV
2.2.3 | Visual inspection of final trimmed subgrade surface | Pre pavement construction visual inspection | Entire surface to be firm, uniform and smooth. | Site Inspection Form | Once per construction area | Witness Point | W | PM & ER
2.2.4 | Compaction (granular) | Proof Roll | Surface impression not greater than: 7mm for bulk fill 5mm for subgrade fill Using 11t Smooth Drum Roller or equivalent. | Site Inspection Form | Once per construction area | Hold Point | H | PM & ER
2.2.5 | Compaction (Non-granular) | Wet density measure | See TNZ F-1 1997 Clause 10.5.2 Non Granular Material | Site Inspection Form | Once per construction area | Hold Point | H | PM & ER
2.2.6 | California Bearing Ratio | DCP Testing | Equivilant CBR value of ≥ 2% | DCP Test Report | TBD by Engineer | Hold Point | H | ER
2.2.7 | Surface Finish Tolerances | Straight edge, as-built and inspection | No point varying more than 30mm on a 3m straight edge laid parallel to centreline, or x-section camber board at 90° to centreline. No ponding where design slope ≥ 2% RL Tolerence = +0 - 30mm from design Survey data / As-built drawings to be submitted to engineer. | Straight Edge form, as-built survey data, visual inspection | TBD by Engineer | Hold Point | H | PM & ER
2.2.8
COMMENTS
[5 empty] | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: