## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 8 - Road Marking & Deliniation | itp |  |  |  |  | F2LSIP - ITP 8 - Road Marking & Deliniation
section | 8.0 - Road Marking & Deliniation
checkpoint | Road Marking & Deliniation
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 8.1 - Materials - Pilot Spec M7
checkpoint | 8.1.1 - High Performance Roadmarking
label | Inspection Point: Quality Control Activity - Compliance Check
label | Acceptance Criteria - To Comply with TS1 & TNZ P12
label | Verifying Document - Manufacturers Cetificate
label | Frequency - Once Per Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 8.1.2 - Audio Tactile Profiled Roadmarking
label | Inspection Point: Quality Control Activity - Compliance Check
label | Acceptance Criteria - To Comply with TS1 & TNZ M24
label | Verifying Document - Manufacturers Cetificate
label | Frequency - Once Per Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 8.1.3 - Raised Pavement Markers
label | Inspection Point: Quality Control Activity - Compliance Check
label | Acceptance Criteria - To Comply with TS1 & M12
label | Verifying Document - Manufacturers Cetificate
label | Frequency - Once Per Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 8.1.4 - Edge Marker Posts
label | Inspection Point: Quality Control Activity - Compliance Check
label | Acceptance Criteria - To Comply with TS1 & NZTA M14
label | Verifying Document - Manufacturers Cetificate
label | Frequency - Once Per Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 8.2 - Construction
checkpoint | 8.2.1 - Preparation
label | Inspection Point: Quality Control Activity - Onsite sweep and visual check
label | Acceptance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
label | Verifying Document - Site Checklist
label | Frequency - Prior to all marking.
label | Inspection Type - Check / Review
label | Inspection: Key - C / R
label | Inspection: By - PM/ER
checkpoint | 8.2.2 - High Performance & ATP Marking
label | Inspection Point: Quality Control Activity - Check
label | Acceptance Criteria - Paint applied minimum of 6 weeks prior to HP or ATP markings.
label | ○ ATP to comply MOTSAM Part 2 Section 4.08 - Profiled Line Markings
label | Verifying Document - Site Checklist
label | Frequency - All marking.
label | Inspection Type - Check / Review
label | Inspection: Key - C / R
label | Inspection: By - PM/ER
checkpoint | 8.2.3 - Raised Pavement Markers
label | Inspection Point: Quality Control Activity - Check
label | Acceptance Criteria - Installed as per drawings and in accordance with TNZ P14.
label | ○ Surface to be clean & dry prior to installation of RPM.
label | Verifying Document - Site Checklist
label | Frequency - All RPM
label | Inspection Type - Check / Review
label | Inspection: Key - C / R
label | Inspection: By - PM/ER
checkpoint | 8.2.4 - Edge Marker Posts
label | Inspection Point: Quality Control Activity - Check
label | Acceptance Criteria - Installed in accordance with requirements of TNZ P16
label | Verifying Document - Site Checklist
label | Frequency - All Edge Markers
label | Inspection Type - Check / Review
label | Inspection: Key - C / R
label | Inspection: By - PM/ER
checkpoint | 8.2.5 - As-Built Survey
label | Inspection Point: Quality Control Activity - Check
label | Acceptance Criteria - Dimensional tolerance achieved in accordance with TS1
label | Verifying Document - Survey Records
label | Frequency - All Linemarking
label | Inspection Type - Check / Review
label | Inspection: Key - C / R
label | Inspection: By - PM/ER