## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 9 - Road Signs | itp |  |  |  |  | F2LSIP - ITP 9 - Road Signs
section | 9.0 - Road Signs
checkpoint | Road Signs
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 9.1 - Materials
checkpoint | Materials
label | Inspection Point: Quality Control Activity - Pre Installation - Compliance Check
label | Acceptance Criteria - All materials to comply with relevent clause under TNZ P24 2020
label | Verifying Document - Manufacturers Cetificate
label | Frequency - Once Per Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 9.2 - Installation
checkpoint | 9.2.1 - Delivery
label | Inspection Point: Quality Control Activity - Inspection upon delivery
label | Acceptance Criteria - Signs to be checked for any damage upon delivery, return to manufacturer if damaged.
label | Verifying Document - Delivery Checklist
label | Frequency - Once Per Delivery
label | Inspection Type - Check
label | Inspection: Key - C
label | Inspection: By - PM/PS
checkpoint | 9.2.2 - Positioning & Orientation
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Positioning & Orientation to comply to TNZ P24 2020 Clause 7.3 & 7.4
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.3 - Sign Support Selection
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Supports to comply as per TNZ P24 2020 - Table 7.1
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.4 - Foundations
label | Inspection Point: Quality Control Activity - Onsite inspections and checks
label | Acceptance Criteria - Foundations to comply as per TNZ P24 2020 Clause 7.7 Foundations
label | Verifying Document - Site Checklist Form
label | Frequency - Once per sign installation
label | Inspection Type - Inspection / Review
label | Inspection: Key - I / R
label | Inspection: By - PM/PS/ER
checkpoint | 9.2.5 - Daytime Survey
label | Inspection Point: Quality Control Activity - Post construction survey
label | Acceptance Criteria - (a) The actual sign face is free of environmental soil such as mildew or lichen growth
label | (b) No physical damage has affected or risked sign face readability and or sign integrity
label | (c) No vegetation or other structure impedes line of sight or visibility to the sign face
label | (d) The sign is free of any graffiti or the aftermath of previous poor cleaning action
label | (e) Sign supports and foundations are sound and maintain correct sign presentation
label | (f) The need for the sign still exists – for example a speed reduction has not negated the need for a
label | posted curve warning speed
label | (g) Confirming that the physical sign and its structure remain suitable for purpose or note that some repair should be undertaken
label | (h) Any fluorescent sign, deemed to require a higher level of day time visibility through its fluorescing colour feature, maintains a satisfactory performance e.g. Signs for active users (schools, pedestrians, cyclists).
label | Verifying Document - Survey Checklist
label | Frequency - Once per completed section of works
label | Inspection Type - Inspection
label | Inspection: Key - Inspection
label | Inspection: By - PM/ER
checkpoint | 9.2.6 - Nighttime Survey
label | Inspection Point: Quality Control Activity - Post construction survey
label | Acceptance Criteria - (a) Overall any sign or part of a traffic sign (eg guide sign), especially when set in a disadvantaged position, is performing suitable for purpose, exhibiting an even level of retroreflectivity across the face of the sign to ensure that an appropriate level of readability is achieved across the entire sign throughout the approach
label | (b) The orientation of the sign face is such that no specular (mirror) retroreflection creates an over bright glare effect that interferes with sign recognition/readability
label | (c) At the threshold of retroreflectivity the traffic sign presents a level of visibility that ensures a driver becomes aware the sign is present – before actual readability is possible
label | (d) That any previous maintenance completed during daylight hours has not damaged retroreflectivity at night – for example poor graffiti cleaning
label | (e) Traffic signs remain fully effective and suitable for the purpose for which they were installed
label | Verifying Document - Survey Checklist
label | Frequency - Once per completed section of works
label | Inspection Type - Inspection
label | Inspection: Key - Inspection
label | Inspection: By - PM/ER