## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | F2LSIP - ITP 1 - Documentation and Planning | itp |  |  |  |  | F2LSIP - ITP 1 - Documentation and Planning
checkpoint | 1 - Documentation and Planning
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below HP Closed
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once prior to works commencing
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1 - Contract Obligation
label | Inspection Point: Quality Control Activity - Project Management Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Signed CP
label | Frequency - Prior to Work Commencing
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.2 - Contract Obligation
label | Inspection Point: Quality Control Activity - Health and Safety Management Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Signed HSMP
label | Frequency - Prior to Work Commencing
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.3 - Contract Obligation
label | Inspection Point: Quality Control Activity - Quality Management Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Signed QMP
label | Frequency - Prior to Work Commencing
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.4 - Contract Obligation
label | Inspection Point: Quality Control Activity - Communication Management Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Signed CSCMP
label | Frequency - Within 2 weeks of physical works commencing on site
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.5 - Contract Obligation
label | Inspection Point: Quality Control Activity - Environmental Management Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Signed ESMP
label | Frequency - Within 2 weeks of physical works commencing on site
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.5.1 - Contract Obligation
label | Inspection Point: Quality Control Activity - Sediment Control Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Approved Control Plan
label | Frequency - Prior to Work Commencing
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Contract Obligation
label | Inspection Point: Quality Control Activity - Inspection and Testing Plan
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Approved ITP
label | Frequency - Prior to Work Commencing
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 1.7 - Contract Obligation
label | Inspection Point: Quality Control Activity - Traffic Management Plan (TMP)
label | Acceptance Criteria - Approved by TMC & CR
label | Verifying Document - Approved TMP
label | Frequency - Prior to Work Commencing
label | Inspection Type - Hold point
label | Inspection: Key - H
label | Inspection: By - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Contract Obligation
label | Inspection Point: Quality Control Activity - Construction Programme
label | Acceptance Criteria - Approved by CR
label | Verifying Document - Gantts Bar Chart
label | Frequency - Prior to Work Commencing
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER