## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 2 - Earthworks | itp |  |  |  |  | F2LSIP - ITP 2 - Earthworks
section | 2 - Earthworks
checkpoint | Earthworks
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by CR
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 2.1 - Source Properties Imported Fill
checkpoint | 2.1.1 - Bearing Strength
label | Inspection Point: Quality Control Activity - Sampled from truck or stockpile onsite as per NZS4402 clasue 1.6.3 & 1.6.4
label | Acceptance Criteria - CBR > 40 as per NZS4402
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 2.1.2 - Weathering Resistance
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - QI = AA, AB, AC, BA, BB, CA, CB as per NZS4407 1991 Test 3.11
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 2.1.3 - Grading Limits
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Grading within envelope as per table 302.2.3 (Technical Specifications) Tested in accordance with NZS4407 1991 Test 3.8.1
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per stockpile
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 2.2 - Construction
checkpoint | 2.2.1 - Topography Survey
label | Inspection Point: Quality Control Activity - Pre-Cut/Fill Survey
label | Acceptance Criteria - Within Design Expectations
label | Verifying Document - Survey Data
label | Frequency - Once per construction area
label | Inspection Type - Action
label | Inspection: Key - A
label | Inspection: By - SV
checkpoint | 2.2.2 - Survey Set out
label | Inspection Point: Quality Control Activity - Onsite Setout
label | Acceptance Criteria - Survey have setout using pegs or similar, the location of the pavement in regards to horizontal and vertical alignment, as per design.
label | Verifying Document - N/A
label | Frequency - As required
label | Inspection Type - Action
label | Inspection: Key - A
label | Inspection: By - SV
checkpoint | 2.2.3 - Visual inspection of final trimmed subgrade surface
label | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | Acceptance Criteria - Entire surface to be firm, uniform and smooth.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 2.2.4 - Compaction (granular)
label | Inspection Point: Quality Control Activity - Proof Roll
label | Acceptance Criteria - Surface impression not greater than:
label | ○ 7mm for bulk fill
label | ○ 5mm for subgrade fill
label | ○ Using 11t Smooth Drum Roller or equivalent.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.5 - Compaction (Non-granular)
label | Inspection Point: Quality Control Activity - Wet density measure
label | Acceptance Criteria - See TNZ F-1 1997 Clause 10.5.2 Non Granular Material
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.6 - California Bearing Ratio
label | Inspection Point: Quality Control Activity - DCP Testing
label | Acceptance Criteria - Equivilant CBR value of ≥ 2%
label | Verifying Document - DCP Test Report
label | Frequency - TBD by Engineer
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.7 - Surface Finish Tolerances
label | Inspection Point: Quality Control Activity - Straight edge, as-built and inspection
label | Acceptance Criteria - No point varying more than 30mm on a 3m straight edge laid parallel to centreline, or x-section camber board at 90° to centreline. No ponding where design slope ≥ 2%
label | ○ RL Tolerence = +0 - 30mm from design
label | ○ Survey data / As-built drawings to be submitted to engineer.
label | Verifying Document - Straight Edge form, as-built survey data, visual inspection
label | Frequency - TBD by Engineer
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT