## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1b0a4b49-8a0c-4d2e-bb63-6e3edea49d4d |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | 05d19ddd-ad66-4e6f-8b6f-4a26a794e0d7
checkpoint-status | 21405333-da65-4a54-8626-69a291b6e202 |  | checkpoint | O&M
checkpoint-status | de13e88e-1a75-4822-9613-6acb567e1685 |  | checkpoint | PS3 Mechanical Service - BCO10328723
checkpoint-status | f69cd0fe-17c6-4fb5-bdb3-047d88a5092a |  | checkpoint | Carbon Monitor & Fantech Checksheet
checkpoint-status | 4578a1e9-4c24-4686-a7d3-0082112ae7c5 |  | checkpoint | HVAC - As built
checkpoint-status | 4bb19ec2-08ce-41ee-b356-a0ea1e2c4dde |  | checkpoint | PS3 HVAC - BCO10328723
checkpoint-status | 10017f0c-3bb9-4e97-a4ca-67fd6ad31ced |  | checkpoint | Electrical Safety Certification
checkpoint-status | d80bf36b-c85c-4c37-9267-95531d1bec66 |  | checkpoint | PS4 Seismic Support - BCO10328723
checklist-sectioned | c706d50c-9211-4f26-afe8-d5564b00384d |  | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  |  |  |  | Yes | SYS - S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan | 0d5b9ca7-1d83-42bd-b389-272c3de75ee5
checkpoint-group | c649ee96-818e-4649-a492-7a825e2ee093 |  | section | Pre-start checks
checkpoint-status | 31ad7911-d72a-44c3-91d4-0622e4e23110 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 0385439f-82e8-4a50-8e88-abad80f2abb8 |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | af3ffe3e-2900-4f8d-8271-deac7dbc78e3 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 03dea435-c39c-454b-8282-fdc1131c856b |  | section | First Fix
checkpoint-status | f6b2df1b-590e-4377-a032-89ec5ed587e0 |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | e6709270-f12b-4ad6-ac97-edb693e23c77 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
checkpoint-status | 9fc48c80-09c8-4fa3-92bf-b9619cfbd889 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | 5a1d28c6-6b10-46fa-a180-64a58450156e |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 7209dbd4-2283-4fd0-add0-54d1494257d1 |  | section | Second Fix
checkpoint-status | e800fddb-ba8b-4bd4-b903-3e8b751aad37 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | 76bbd1cc-5f6a-44db-99be-9087b2451458 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | fc514a33-aa6a-4e53-bdd0-53fac74bbd3e |  | section | Commissioning
checkpoint-status | 39c3a161-8ed4-489c-8a8c-0c4cb766f165 |  | checkpoint | Good access to all areas of building
checkpoint-status | f4702235-70ce-4e34-8f3c-943550454bba |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 717cf23d-4553-4f54-86a2-d1cbfe4e7b83 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 4deb5fb5-4e8f-44b4-849b-02d73c1a3829 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | be4686be-ab0d-4ecf-9c53-a50ab700b670 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 6c26533f-2562-4257-93d8-40033ef5ea73 |  | checklist | S - S - Ventilation - Apartment Ventilation |  |  |  |  | Yes | S - S - Ventilation - Apartment Ventilation | 0e50280a-b050-4d80-a616-1bfdd0af6389
checkpoint-group | b6dd4f5f-5533-48d9-8a0b-5d41721904ad |  | section | Pre-start checks
checkpoint-status | f3ee19b7-c26f-4213-8009-1764b3f54aa3 |  | checkpoint | Penetrations done in floors and walls (if needed)
checkpoint-status | 5d820ddf-e64d-473d-b138-57d00e6fd0d2 |  | checkpoint | Space for ducting (no trades in the way)
checkpoint-status | d7cb900e-2c3d-4f7c-9452-154befb26bbd |  | checkpoint | Pipe through exterior wall installed by RHC to connect to
checkpoint-status | 864dabe9-3cc5-4556-b1d6-0b1d50d6d481 |  | checkpoint | Drawings and work scope confirmed
checkpoint-group | 623e27d8-675e-4e63-908d-da431620a95d |  | section | First Fix
checkpoint-status | 837861cb-2cd0-426c-96f6-0ff553fa852e |  | checkpoint | Ductwork run straight level and well supported
checkpoint-status | e3736b84-04f8-4e7f-9335-72568d4862e3 |  | checkpoint | All ductwork joints sealed
checkpoint-status | b42f151a-fb17-43a7-97b5-9bde356c20b5 |  | checkpoint | All SAB joints sealed and taped
checkpoint-status | 7772997f-e4a1-42bb-bd40-5aef5a11b5ad |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | 716cb1ac-4886-42db-8d48-62661109551e |  | checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint-status | 88c58908-84f7-4c19-adfb-e200f60e7b78 |  | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint-status | 858d1669-221f-4428-821b-1a58965e2080 |  | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
checkpoint-status | 6a6bea08-f329-41f8-9b79-56744f394c62 |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | db1a45c8-191b-4b7c-8f54-8f971703dfc4 |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | e803fc06-c8c5-4905-abed-103b6699c93a |  | checkpoint | Upload Photos of Install
checkpoint-status | 2eae6d55-f38d-4a15-b229-9949f7ffbdaf |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | 95ff7dd8-96cc-44eb-98a0-a9e264179884 |  | checkpoint | Flexible ducts fixed in place to grille location
checkpoint-status | 0c2da016-2f58-4f6b-993b-de49ad1d2487 |  | checkpoint | Identify Fan Upgrade Requirement
checkpoint-status | 897cbf65-a87c-4d5e-9baa-544d07285b70 |  | checkpoint | Area Clear for Install of Ducting, Fan, and Control Box
checkpoint-status | 5da74eb1-796d-4604-94ac-091b443144fe |  | checkpoint | Install Fan, ducting and control box as per spec.
checkpoint-status | af65dfc4-78ca-4b75-a52f-1bf503303859 |  | checkpoint | Grille locations/access panels marked on plans
checkpoint-status | 492a071d-bbe2-4941-a1c5-02cc951f6da9 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 682e4b12-c5f7-4261-a7cc-f4bbee24d840 |  | section | Second Fix
checkpoint-status | 7939e776-bcb1-4143-ab15-cfc66407943d |  | checkpoint | Ceiling fans installed square and level
checkpoint-status | 27a2071e-c74e-48a8-9153-f9a180b537bd |  | checkpoint | Kitchen range hood installed by RHC to connect to
checkpoint-status | a85a63db-035c-4345-aadd-8d7dd5b473a5 |  | checkpoint | Fingerprints removed from grilles/walls/ceilings
checkpoint-status | 6fdacd83-1b56-45cd-b03a-839863b99fb8 |  | checkpoint | Fan plugged in before install to ceiling
checkpoint-status | 9337ef6b-ef77-40a0-b89b-fddf36a37be4 |  | checkpoint | External louver supplied by TSL, installed by RHC completed
checkpoint-status | 90f50d67-155c-4d90-88b5-f2e31d67ca47 |  | checkpoint | Commissioning form completed & given to TSL
checkpoint-status | c4dcf216-e019-42de-a515-26e32e4dbe25 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | aaed8233-5bc2-437b-8839-301def598c9e |  | section | Commissioning
checkpoint-status | 75612112-a662-4c03-bb0d-58a6e604ab8d |  | checkpoint | Correct product used as per requirements
checkpoint-status | 12f10394-a6b3-458a-b7b2-3cdf33b9e4a2 |  | checkpoint | Correct design followed as per drawings
checkpoint-status | facc2bee-ec3d-43fe-b785-4ff6e407c184 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 028b6c57-1a82-4610-886d-1eb8955b790a |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | b04a2dc0-91dc-4d03-966e-279bee7dd6f8 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 533259f1-5a54-4df4-84fa-6db1168a2aa2 |  | checklist | SA FAN |  |  |  |  | Yes | SA FAN | 104cf838-1e31-43f4-968a-c028ab83473d
checkpoint-group | 00128593-245e-466a-80d6-a6679f0dff45 |  | section | Pre-Start SA Fan
checkpoint-status | 3a2b1683-fae4-4b20-a432-1d9fd5845690 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 5355f9ea-d3da-4886-8b20-5f73a5802365 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 7ce70ffc-e1f9-464d-8a72-7dc9b0d4b3a4 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 87176826-abc4-4939-90c7-3f00940c0538 |  | section | First Fix SA Fan
checkpoint-status | 4cd434a4-03e0-41de-ba3f-5ca1544afaaa |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 629f9149-669c-4480-ab11-e48d91fa5fe9 |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 82d3ded8-6425-4144-b9ec-65dd930deaed |  | checkpoint | Correct Fan installed
checkpoint-status | 186cb580-5f83-42d1-9d5c-f148e8243cbd |  | checkpoint | Fan serial No. recorded
checkpoint-status | e31c99f3-a63e-418a-ac30-54200bc110fa |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | d6227a4c-5201-4834-a175-903676c7fec6 |  | checkpoint | Heater Bank installed to Manufacturers instructions
checkpoint-status | 9535a3d7-e2cb-4eb1-92a0-9cdb291e8cf7 |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 9b5a97a2-b806-4e71-be16-fb9da0826165 |  | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
checkpoint-status | 6ef1d040-04be-41cf-b293-c73da2bc9245 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | f6964fc0-807f-4213-abc4-d917ca347726 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 439ae54a-7de7-4bf7-9559-c2f2cd1da26d |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | ba772db1-270a-40a6-9570-d787e0a2caaf |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 954f4cb2-c912-4205-af69-32aadf09d925 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 7842b09c-6059-463b-87f1-831534cfe4df |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | bef6b770-cddc-46a9-9ddb-557c1de6941a |  | section | Second Fix SA Fan
checkpoint-status | 4bef0442-d37b-4f92-9db5-2398b00f28a7 |  | checkpoint | Grilles installed square and level
checkpoint-status | 385a8aaa-994c-442b-9b29-f7f01ab1b62a |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | fa1f9917-9865-4519-a8e8-9989d0a29975 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 5087305f-30d3-44bf-90fe-320869038750 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | 7806e55b-ba4d-4b0e-8198-acb1e968b6ba |  | checkpoint | Controllers fitted off. Heater Bank THT set
checkpoint-status | f84fb844-9423-474f-b9c3-98c4993a6646 |  | checkpoint | Power fitted off
checkpoint-status | 8fc3d683-f33c-4c88-a7b2-7563861ab2d6 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 0803f5c6-3997-4786-beb8-8393df8922c6 |  | checkpoint | Plant and controllers labelled
checkpoint-group | 96cbdca3-bc5d-4fdf-9261-713459859ddf |  | section | Commission SA Fan
checkpoint-status | f23d1782-d17f-497f-823c-0a91900cc362 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 7a69c5a2-0773-4211-b399-556d9c11abc4 |  | checkpoint | Electrical testing complete
checkpoint-status | 530ae2a8-4a04-491d-9cb2-abcdfcc0567b |  | checkpoint | COC issued
checklist-sectioned | b025fd65-15d5-4c06-8f0d-b0c3c5287608 |  | checklist | SPLIT HIGH WALL |  |  |  |  | Yes | SPLIT HIGH WALL | 17bf6d88-dbed-491b-b052-208f0f8e039b
checkpoint-group | 093b2e5a-4a94-415b-a438-8cee3ef75367 |  | section | Pre-Start HW
checkpoint-status | d65b0904-eab9-4afb-8e59-7b6b8dbb87cf |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 6011abd1-57f4-4afe-9f46-6abfc2544cc2 |  | checkpoint | Area/base ready for outdoor unit
checkpoint-status | 5ca25a48-6f59-436a-ac1a-d4656776914e |  | checkpoint | Any required drains for outdoor unit in place
checkpoint-status | ac748339-f730-4da9-bb8f-46171a9cc8c6 |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | 041b4fa4-1590-4d23-9108-af4705d5a193 |  | checkpoint | Nogs in place
checkpoint-status | b2938345-85e5-4e84-9cdb-655cd028439b |  | checkpoint | Drain 1m from Indoor unit location by plumber
checkpoint-group | e8ca27b9-6479-4b47-a31b-9123cecaeb32 |  | section | First Fix HW
checkpoint-status | 774d711f-09da-4dd3-8a48-d09890689060 |  | checkpoint | Pipework Insulated complete length
checkpoint-status | 4b498e21-3c13-4ca7-a82a-7916df7cadb1 |  | checkpoint | Drain installed and insulated
checkpoint-status | 547e7c73-f828-4c7d-ba7a-45d521367a22 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 9cb83c0f-19e0-426e-9b4c-49ef4d7b7507 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-group | 7c64e59f-8c03-4791-a540-766e39096f46 |  | section | Second Fix HW
checkpoint-status | 2341d03b-9e34-442e-9012-e2fd85bfe608 |  | checkpoint | System pressure checked and still holding 1st fix pressure
checkpoint-status | 6fbd7af6-3e39-44fd-8bec-dc35e694f372 |  | checkpoint | Indoor unit secure, level and tight to wall
checkpoint-status | 86102b73-e9c2-4251-bf83-141f7d1fcb2f |  | checkpoint | Correct Indoor unit installed
checkpoint-status | d03aa8f9-7e26-435e-942a-2cae9ae6416c |  | checkpoint | Outdoor unit secure and level
checkpoint-status | 63f10872-8a3a-4ff0-be94-11a929d29916 |  | checkpoint | Correct Outdoor unit installed
checkpoint-status | c42fd5bd-67c6-41a8-bb00-2de993765393 |  | checkpoint | Indoor unit serial no. recorded
checkpoint-status | d545cedb-76db-40b5-853a-7ce00923fd22 |  | checkpoint | Outdoor Unit serial no. recorded
checkpoint-status | f9ef278b-2836-457c-9f4c-6624898ad552 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-group | d6a2f93d-69aa-43d8-bd14-0cdb28fdfdcf |  | section | Commission
checkpoint-status | 4214b773-6eea-4874-8ce9-58666e847230 |  | checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint-status | ac76e613-0fda-41a9-9d0f-1e97a2a9d61d |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 66e08c15-8706-4427-a0e7-22d9a885bc24 |  | checkpoint | Electrical testing complete
checklist-flat | f4cf5fc9-e78f-4838-afb0-ab8261a078ce |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checks | 201b9631-0294-4c44-b129-d1f49cbb2bb2
checkpoint-status | 5ac79c7c-2d5a-4eb1-bbc6-aed9d7a5ec66 |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 887b7e91-a489-4f16-91d2-bd6d861ac12e |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | c4b0df3e-4082-4e1e-bf3d-c9b80e777887 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | b0a4fd5d-c743-4e1a-a991-28aebcb20aa4 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | f9cc1b91-4e86-4bef-8a0e-14a148d4be86 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | a62de021-85e7-4a98-8c88-693905035154 |  | checkpoint | Matrix/Insight Setup (if required)
checklist-sectioned | bf397771-74e8-4a66-a032-216b91f10074 |  | checklist | Jet Pulse Fan |  |  |  |  | Yes | Jet Pulse Fan | 2fd4e2c3-3876-48b8-a750-d8f19f87bcc0
checkpoint-group | 1651307c-ab20-4c84-b2f7-bebf06e585da |  | section | Pre-Start SA Fan
checkpoint-status | d0670663-fe9a-445d-a83c-3777c59e72d1 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | a2253bb9-08d8-47ad-bf3e-4b8978ffe932 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 35918245-eb9a-4ec7-8f95-5eb140fe84f5 |  | checkpoint | Nogs/Supports in place
checkpoint-group | c0b41224-180a-4e65-8f6e-fa55173c9174 |  | section | First Fix SA Fan
checkpoint-status | 37319aab-6497-4de8-8352-3f71aa416029 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | cdf09533-441f-41a9-adbc-aaf4c5a88d86 |  | checkpoint | Correct Fan installed
checkpoint-status | 55a13ba4-852c-47cd-a752-15d807f190b0 |  | checkpoint | Fan serial No. recorded
checkpoint-status | ec3acd39-c837-4d52-a042-fb853edfc1f8 |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | 5e650dd2-7a8e-4d9c-8f87-9abf2caedf73 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 4d2b54f3-674c-41be-88fb-cbb7878586d6 |  | checkpoint | Supply cable type, size and manufacturer
checkpoint-status | a3f5d39c-fed6-42c8-a5b2-ae3d219037e1 |  | checkpoint | Circuit protection type and rating
checkpoint-status | fbf106b9-76f9-4d0d-83b1-0bbde9e0c4b0 |  | checkpoint | Correctly rated isolator installed to standards
checkpoint-status | c19359a0-9421-48de-bead-b37555cf1b3d |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 3a2fd1c8-8218-4806-9ec1-3940b4ae2242 |  | checkpoint | Control cables correct rating and type
checkpoint-status | 9356086f-26df-469b-810e-6520378c70f3 |  | checkpoint | Screened cables drain to earth as per specifications
checkpoint-status | 102fc274-84f5-41d4-82a5-39ef3468de59 |  | checkpoint | Control cables maintain minimum distance from power cables
checkpoint-status | 77e5f88c-d1b8-4d3f-ba22-991119a1bdb3 |  | checkpoint | Daisy chain loops complete and correct
checkpoint-status | 5714b6dd-c118-40ba-91e4-eff1c6947bad |  | checkpoint | Remote controller cable installed
checklist-sectioned | f119bfd5-6cfb-4768-b2b0-320d46387a12 |  | checklist | S - S - Ventilation - Apartment Ventilation |  |  |  |  | Yes | SYS - S - S - Ventilation - Apartment Ventilation | 6b7292dc-927c-4507-9a9c-3c9dcc04adae
checkpoint-group | 2a9ecd91-9670-48de-ac41-13c023094e91 |  | section | Pre-start checks
checkpoint-status | 2bf55232-3092-4103-a793-5ac465829bab |  | checkpoint | Penetrations done in floors and walls (if needed)
checkpoint-status | a5058456-8e3b-4edc-b562-e436e5275a07 |  | checkpoint | Space for ducting (no trades in the way)
checkpoint-status | 61a0ddcf-e17b-44a9-b9bd-6bf3aed912bb |  | checkpoint | Pipe through exterior wall installed by RHC to connect to
checkpoint-status | 64f8b3be-6b07-475a-8f0d-0cc4c40b1c4e |  | checkpoint | Drawings and work scope confirmed
checkpoint-group | b9f35315-0959-4844-aa07-79a4c670ea9e |  | section | First Fix
checkpoint-status | c47b90ad-56e4-48e8-a7b6-4c65d82eed34 |  | checkpoint | Ductwork run straight level and well supported
checkpoint-status | fa585f6c-c57e-4249-a795-c773b034b137 |  | checkpoint | All ductwork joints sealed
checkpoint-status | b95a1ab2-6738-45e9-adf2-59b759ce7675 |  | checkpoint | All SAB joints sealed and taped
checkpoint-status | 5c718a27-74e3-4dcb-8e7d-e56f84ccc88f |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | 107b75ea-16b6-4529-8ec1-aee98c48f8e3 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | 6d5380f3-2847-4539-933b-e5cf098ac10e |  | checkpoint | Flexible ducts fixed in place to grille location
checkpoint-status | 22c22a16-fee4-4944-83c1-560b3ba9e1ba |  | checkpoint | Grille locations/access panels marked on plans
checkpoint-status | 7e4c6003-d350-4511-af02-ca6bf974fefa |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 74a963eb-aa33-4ef5-9a6f-0ac559b92adf |  | section | Second Fix
checkpoint-status | 71dd306d-191c-421f-93be-9d1e3f6dfe6a |  | checkpoint | Ceiling fans installed square and level
checkpoint-status | 83f224c9-45c7-4a9d-a6eb-90cbd8825017 |  | checkpoint | Kitchen range hood installed by RHC to connect to
checkpoint-status | 6cc1fe96-a4ea-4344-99c9-17f52a7491e9 |  | checkpoint | Fingerprints removed from grilles/walls/ceilings
checkpoint-status | 117a9c9c-9161-48eb-bdef-802498a33279 |  | checkpoint | Fan plugged in before install to ceiling
checkpoint-status | 90545d9d-a4fb-4384-a17c-22f0154ba50b |  | checkpoint | External louver supplied by TSL, installed by RHC completed
checkpoint-status | c4d33aba-663e-4f52-8316-a679eb6d0c0e |  | checkpoint | Commissioning form completed & given to TSL
checkpoint-status | b23d663e-7d85-4575-9991-5c7916e68f44 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 9e588e07-9d8e-48ee-bf80-68b2cad52c54 |  | section | Commissioning
checkpoint-status | 010f4c6f-9417-4e79-a19a-8f2b9e1883b0 |  | checkpoint | Correct product used as per requirements
checkpoint-status | 340b0c7b-a613-41be-8681-8d8206f37f30 |  | checkpoint | Correct design followed as per drawings
checkpoint-status | 4a4190ea-d487-4e2c-bdd6-4347e9a6b1be |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 78a85b87-b6dc-4ed7-81e5-06561c99cff7 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 12d9224c-81ac-4036-b202-60b512669702 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 57e1f027-e22f-4757-9651-c2a277078e1e |  | checklist | S - S - Kitch Extraction |  |  |  |  | Yes | S - S - Kitch Extraction | 82aae130-ad0a-410f-9aa8-8dc93bd8ab9e
checkpoint-group | 91b02919-4cf0-48ce-bd82-ca40398f58f5 |  | section | Pre-start checks
checkpoint-status | b810c440-1d4a-4cd9-bf53-8d45492b7545 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 5ed33d5a-a9a3-4a1c-a0ad-983f85b98c5e |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | 690594b6-068b-4646-83c8-07f55661a877 |  | checkpoint | Nogs/Supports in place
checkpoint-group | dd809eb0-ab9c-437b-aa39-fb8a6ea0e1fe |  | section | First Fix
checkpoint-status | 7b3bc762-4cc6-4fb3-aa13-2ba4ab6ce787 |  | checkpoint | Fan installed straight and level and correct orientation
checkpoint-status | ec56f0e4-bb4b-4af9-9b7c-14675c960e15 |  | checkpoint | Correct Fan installed
checkpoint-status | 12f84648-80ef-402b-ae5a-ac596f12c0e5 |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | 3fc3a96e-8f1e-4ac7-b28e-2defa46b1f20 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 612a5a65-9483-4e4f-8ed8-7f321e6b9754 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 57dc1940-cb3d-4461-88c1-b8978d278f66 |  | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan |  |  |  |  | Yes | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan | 83249ecb-ab9a-43f5-b7d8-337fa40a591d
checkpoint-group | 3ffb6250-34eb-435f-b63a-fc4f0e68b1c5 |  | section | Pre-start check
checkpoint-status | ada200ed-b8ee-4e0e-875d-703a15cca0e2 |  | checkpoint | Area clear, access god, enough space for install
checkpoint-status | ce539e3b-5d50-4ee2-8fd1-024bd73e4923 |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | da63f65a-a477-4ccc-bfa4-728b58af0bad |  | checkpoint | Nogs/Supports in place
checkpoint-group | 0fee4110-4645-44f0-ade2-adcb75e0994f |  | section | First Fix
checkpoint-status | 1c4af97b-360b-44e0-8d7e-cf5d8ae9a62e |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 033db637-130d-4d91-ab5a-6a21c58f5a6a |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
checkpoint-status | 6f9b1140-2cdc-4e3b-925d-2fe7f22c72ba |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | e814f537-78bc-4d23-a05f-2b2556e4f9fc |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | 6ec13a0f-25c1-4614-807d-cce919b8da34 |  | checkpoint | Upload Photos of Install
checkpoint-status | 82a6f427-c0d1-40f2-b900-02ae3b464a6d |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | c3351c81-31d1-4ef6-b6d1-184ac63090b1 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | 198df8cd-91aa-4b4f-97a1-ef72a78d2e16 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | f1e096ef-e9fc-4701-9c4a-0f091233f412 |  | section | Second Fix
checkpoint-status | 7cad9c04-dbbd-407e-b515-7db73f9e6610 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | 39c91235-a811-4a6d-a3d0-4ead1f1efaf2 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | baf90bc7-d521-464a-b3bb-d8611b77d520 |  | section | Commissioning
checkpoint-status | 6d1f1d8b-f95f-479d-b885-0de3774d961c |  | checkpoint | Good access to all areas of building
checkpoint-status | 20e8834e-8274-4fc9-a400-09380a54f8a6 |  | checkpoint | Power live to Mechanical Plant
checkpoint-status | 8f229f25-b6d0-4c35-9dde-0a9cab44d9d6 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 00a9a74c-de08-4f61-a785-b4a49246b861 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | cfb64fa1-d359-4ebe-8da7-0b9e70791842 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | a8d7560c-0328-4b02-8bac-e58e149d554c |  | checklist | Extract Fan |  |  |  |  | Yes | Extract Fan | b66e72b6-95d6-40f6-a891-bb81a64a91d3
checkpoint-group | bfc4c44b-fcb7-46fa-9a72-19dc9f0b8659 |  | section | Pre-Start Ext Fan
checkpoint-status | 1c090a2a-d831-467e-8bd1-db439d363997 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 308e032f-5c04-44b1-a9b9-083728ea1259 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 971d7327-caec-4b0c-bf0b-173e2701c8b7 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 948458c9-b74d-4e8d-bc47-e7c2f5d1baed |  | section | First Fix Ext Fan
checkpoint-status | 898f9753-77b4-46b6-acac-3b4ed0f58eaa |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | a4e85487-8bb1-40fe-bc23-8afc7d0e39f7 |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 75fb9abc-0ceb-4917-932c-1fcbba624f49 |  | checkpoint | Correct Fan installed
checkpoint-status | ba06da6c-7bbe-4bbb-90f8-0db8d685476d |  | checkpoint | Fan serial No. recorded
checkpoint-status | 340e7f48-0a23-41d3-842d-a26adefdd3a9 |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | ded0344c-52a5-4523-bf42-bd96482b5ea5 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 307db7bf-6bd6-45ab-8fca-6f9dce083352 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 05c5af82-0f1f-4fcb-83be-8d6f027f2432 |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 703887bf-5560-4545-8f2c-a1337d73051b |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | f2494147-463c-452f-8b96-fc42291dd509 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | cee4e101-bd9b-4f5a-9443-564e0f307c1b |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | 08c3fcf3-5b52-47f2-9ffc-3906cac2a2a1 |  | section | Second Fix Ext Fan
checkpoint-status | 07e96289-bae6-456e-b477-b13b96e7b174 |  | checkpoint | Grilles installed square and level
checkpoint-status | 77f8d6e9-1218-49cc-bce0-6587bdc71266 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | 9aa1e7f9-5e08-49d5-97a0-6d265f3a97d5 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 81c915c9-670e-49f7-b76e-294238a72ec0 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | edbc13e0-ba64-4932-81c4-90a2e26ff5fb |  | checkpoint | Controllers fitted off
checkpoint-status | cc7b3e2a-c9d8-4f53-9a61-787ad696c58a |  | checkpoint | Power fitted off
checkpoint-status | 334eea21-4378-42d9-b0e2-8112672a884b |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 96fc09d8-7cef-4e90-8473-bc785f805fe4 |  | checkpoint | Plant and controllers labelled
checkpoint-group | 487a9565-65d1-46da-a7f9-1972e3471d37 |  | section | Commission Ext Fan
checkpoint-status | 87916ffe-c6ec-4550-89d5-7d33097e305d |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 4e33162e-ac1e-4ec3-a358-893b3a85df26 |  | checkpoint | Electrical testing complete
checkpoint-status | fa4be4bb-6727-4771-87a7-1d5977199aac |  | checkpoint | COC issued
checklist-sectioned | 4c720a29-07e9-4537-b584-9134115b3f23 |  | checklist | S - S - Air conditioning |  |  |  |  | Yes | S - S - Air conditioning | cfa2dfd7-1c2d-44af-95d5-c70fc4ae0f87
checkpoint-group | af3fa9b2-4269-4bde-ad66-431eccc9b375 |  | section | Pre-start checks
checkpoint-status | a65f6ba0-8a8d-4ef4-88fa-2bfec902e771 |  | checkpoint | Area/base/wall ready for outdoor unit
checkpoint-status | 54108c13-3216-455f-8d3f-35c672b824df |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | c00fab10-a211-4602-a5f9-07cafade177d |  | checkpoint | Nogs/ply in place for indoor unit
checkpoint-status | b926f047-ea72-4787-b5f8-27688e3beff4 |  | checkpoint | Drain 1m from indoor unit location by plumber
checkpoint-group | f61b1fb5-1030-4201-81b1-b8a276d92c3c |  | section | First Fix
checkpoint-status | 4c7757d9-cc67-40a8-85e4-8bf446b1e667 |  | checkpoint | Complete length of pipework is insulated and acceptable
checkpoint-status | 8719c841-308a-4dce-ab21-37d9af93594a |  | checkpoint | Drain installed and insulated
checkpoint-status | 0bef9eb4-785f-46d4-a488-a0073c4f5e39 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 8a36b64e-787e-42e3-9d53-2b6ccec23442 |  | checkpoint | Outdoor wall brackets in place
checkpoint-status | d05ac3fb-1112-49fe-8f55-a91d9dfdb5f1 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 7b8cd8af-fae2-4bd3-9d20-19ae334f375b |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | 5ea99b23-77c0-48e7-9292-a73914b4064e |  | checkpoint | Mechanical First Fix complete and acceptable
checkpoint-group | 882af7f3-ccb2-4991-b8cf-9e7770448a8a |  | section | Second Fix
checkpoint-status | 15d8c86c-3496-4abb-bdc5-8984cfea4471 |  | checkpoint | System pressure checked and still holding pressure and acceptable
checkpoint-status | fd46791a-1f71-4cef-9016-2e89ed02a3b1 |  | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
checkpoint-status | 19981e92-ab5e-4185-9b28-cd6ca0d1414c |  | checkpoint | Correct Outdoor unit installed and secure
checkpoint-status | 60571827-2854-4fde-a5e3-2ed31223d254 |  | checkpoint | Indoor unit serial no. recorded
checkpoint-status | 920cb875-ae76-4156-92a0-51ace6daa81c |  | checkpoint | Outdoor Unit serial no. recorded
checkpoint-status | 37499202-a355-4442-9896-298e7387259c |  | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
checkpoint-status | 1b27453a-422d-440a-a9f9-443591264c8e |  | checkpoint | Air conditioning Second Fix complete and acceptable
checkpoint-group | 1c640d53-96d0-40f3-917c-38fa0eef293f |  | section | Commissioning
checkpoint-status | c0bbb5ad-3fff-40d0-89be-a769a58f4f64 |  | checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint-status | 6402b437-5e29-4b33-9de5-6e029f6507c3 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | ff156ea6-8fb5-4234-a529-9ebeae3cc785 |  | checkpoint | Electrical testing complete
checkpoint-status | 6e5490ec-5038-4523-995e-402800513627 |  | checkpoint | Commissioning complete and acceptable
checkpoint-status | 947cd8d8-84d2-41d5-afef-07658b2f1957 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 98a8b22e-715c-4098-9430-6a7ad52187a6 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | c4a7559c-3246-4f3e-ba27-f1f1182557f1 |  | checklist | S - S - Ventilation - Corridors Ventilation |  |  |  |  | Yes | S - S - Ventilation - Corridors Ventilation | d5bc43c1-dd2e-43d5-9551-ffb24e67f666
checkpoint-group | 6d79b3fb-a6e2-40b4-9f81-33c99467caa5 |  | section | Pre-start checks
checkpoint-status | 2ff9905e-b48d-4e66-85b1-cf32d8b6493d |  | checkpoint | Area clear, access god, enough space for install
checkpoint-status | 80a3d3d8-c311-435c-97d2-7de2622baad8 |  | checkpoint | Duct Route clear, Penetrations completed
checkpoint-status | 7d5e8699-f927-40fa-99f4-91366f40f77d |  | checkpoint | Nogs/Supports in place
checkpoint-group | c572c6cd-8558-4b25-b957-be15b7b8f72c |  | section | First Fix
checkpoint-status | 44a59efb-a6bc-4a13-93ec-e384654005da |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | a03b4baa-adc2-4131-a92d-7fca22b173cf |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations)
checkpoint-status | 5bc427a5-4ab7-4272-947b-5abd7e82ee12 |  | checkpoint | All flexible ducts cable tied and taped to duct
checkpoint-status | 82556c0b-a841-4dfc-8bb7-fc7f23dc5fed |  | checkpoint | Identify locations and correct model of Fire damper to be installed
checkpoint-status | ba0fb8ce-8a53-4669-abf9-54d4908be982 |  | checkpoint | Install to Manufacturers Specifications
checkpoint-status | 872096b4-f509-465b-a663-c32848da8ed4 |  | checkpoint | Inform RHC PM Fire Dampers are ready for sealing
checkpoint-status | ff4f4b53-29ab-4d7c-a0e7-4f4e74d335f4 |  | checkpoint | Using damper handle and fusible link, test damper operation and then set blade to required position
checkpoint-status | 06b11eb5-bf5b-422f-9f3b-f2be20883c8a |  | checkpoint | Understand the requirements of the Seismic PS1 and identify the locations where engineered bracing is required
checkpoint-status | 34f95825-8ce4-4962-9980-04d6843cba14 |  | checkpoint | Install using Materials specified in the PS1
checkpoint-status | e09fbbce-e58d-4c94-8d85-631e8c1a2bf8 |  | checkpoint | Upload Photos of Install
checkpoint-status | 12033816-2adc-4b83-a349-f15935189949 |  | checkpoint | Refer back to Seismic Engineer for PS4 Production.
checkpoint-status | 8c3066b5-a68a-4fc6-91f3-bd4e2cbab764 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | 98d4c8f3-b989-4a7e-871c-efbb4d6e587d |  | section | Second Fix
checkpoint-status | 0c94b06f-d8cd-4c1f-821a-6b5d533bb343 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | fe9b0fd7-3519-4307-b005-6d22166cc1f6 |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | a8107314-dad2-46da-8419-658e9052813e |  | section | Commissioning
checkpoint-status | f22f8a51-dbae-483f-8d0f-79717eca75a1 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | 72b6b916-7d80-4dc2-a1ad-c5ecd8323016 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | f7c8799a-76e2-4c55-820f-aeaeb3cda2b6 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | a7ea4423-4627-4bf6-a349-013e78fae846 |  | checklist | Kitchen Extract Fan |  |  |  |  | Yes | Kitchen Extract Fan | eb666037-e9a8-413d-9582-200595b0ed5e
checkpoint-group | f80aa660-a6d1-4c6b-a606-0b49c7811313 |  | section | Pre-Start Ext Fan
checkpoint-status | 74f12232-33ad-4e4d-987c-a09780b085c1 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 03a9d0c2-7bca-4561-9b58-b0954a65c4a0 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | be8220b8-fe65-4262-b4b0-a499ae3c5223 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 5fd663a2-c77d-46aa-81dd-4bdfe8f1919b |  | section | First Fix Ext Fan
checkpoint-status | a44c5136-f01d-4476-8b5b-04757fbd3807 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 53e405e0-fe57-4773-b48a-06d6f542215f |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 35330a94-b91c-4f24-bd1c-ebdbe457296f |  | checkpoint | Correct Fan installed
checkpoint-status | 50706214-c1c4-4301-bb19-e6510faee410 |  | checkpoint | Fan serial No. recorded
checkpoint-status | d40ac509-15df-4054-b635-4d9163d7708a |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 0642e4a6-7661-4831-ae34-bd2638122881 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 4214649d-828f-4d5a-8fb5-551711c43c6b |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 1484200d-bfb2-4d8b-aa61-baa541b0345f |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 2d3d6ee2-39b1-4214-beb4-cb1a288d42be |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 8cee5050-aaec-4b73-b127-f7246e656c04 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 03782186-917b-4b4e-92f6-425e8189d0db |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | 5768f924-2c0a-443a-a8bb-9088d30cf8b8 |  | section | Second Fix Ext Fan
checkpoint-status | 4c547e3f-ee04-4f0b-a607-6dfb31f8b6f0 |  | checkpoint | Grilles installed square and level
checkpoint-status | b757ea2f-905c-421d-94d3-0edec7481d43 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | f6b8b24a-dfbf-4a13-a972-3ad8c6bc0967 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 7da2fcad-8618-4f22-9e9e-09cadce29940 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | c33a6059-f0df-4939-8c74-4865c56b147e |  | checkpoint | Controllers fitted off
checkpoint-status | c97528f5-50cc-436a-bd3c-6196f4e856ec |  | checkpoint | Power fitted off
checkpoint-status | 790f0f4c-79b6-46b4-8cee-3b2ac839ead7 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | a1d26f7b-644b-4bdc-8e90-55af845f100f |  | checkpoint | Plant and controllers labelled
checkpoint-group | 27c3790f-3f1b-4395-9341-4d19de4271ca |  | section | Commission Ext Fan
checkpoint-status | 7c71ea12-e083-4467-a0aa-7e8ee1047102 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 3a170b85-4a13-4332-8830-4498cf0bcda8 |  | checkpoint | Electrical testing complete
checkpoint-status | c06bcaf5-53f5-452f-9de9-da865389b024 |  | checkpoint | COC issued
checklist-sectioned | a1f360d1-7f5e-4c3b-b43d-a85c3897b85b |  | checklist | S - S - Ventilation - Corridors Ventilation |  |  |  |  | Yes | SYS - S - S - Ventilation - Corridors Ventilation | fb3454d1-fc3c-4186-8ea5-1dc4af9392a6
checkpoint-group | 3b3c4eba-dc16-44bc-9876-cb9699de4328 |  | section | Pre-start checks
checkpoint-status | 61cf8fec-e62b-4394-8c26-b55ab57586fc |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 8a74f4d0-afb0-4994-8ecd-1e03acfa9638 |  | checkpoint | Duct route clear, Penetrations complete
checkpoint-status | 0a047580-d8cc-4f50-9921-6fba766ae6d9 |  | checkpoint | Nogs/Supports in place
checkpoint-group | fb800e25-a626-40a9-a325-3f03b9c09cc7 |  | section | First Fix
checkpoint-status | b95571df-b24c-4e88-9217-010fd2636d2c |  | checkpoint | Access Panel requirements marked up on drawings and submitted to client
checkpoint-status | 7a546c30-fcf1-460f-8baa-b112861974f1 |  | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
checkpoint-status | 15de8009-9a26-41f1-8149-d0bd1a98ba59 |  | checkpoint | All seismic restraints in place (if needed)
checkpoint-status | 13d17564-6328-468f-8d20-0754a6de6311 |  | checkpoint | Mechanical First Fix complete
checkpoint-group | a3d3bdf8-3f59-467b-9d44-304d7f3e2267 |  | section | Second Fix
checkpoint-status | dd586d0c-bffc-430b-a17c-4b9502a1b1e2 |  | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
checkpoint-status | 3aa7fa2e-9bf6-489b-9af3-501a9cbef1be |  | checkpoint | Mechanical Second Fix complete
checkpoint-group | 8ea5227b-3aa4-4894-b1f1-7dd8f33e70c1 |  | section | Commissioning
checkpoint-status | 568e05de-8d7b-4b38-97cf-d878f4c7a919 |  | checkpoint | Mechanical Plant commissioned
checkpoint-status | aee8f081-be4c-4ec7-8436-27cd03723b42 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | dc000573-6bbb-44af-af26-981254288db7 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS