## Master List Templates
Id | Type | Name | Values | Prompting Name
e3e70f80-8138-4d8d-9580-62000efe2320 | checklist | Drainage Inspection and Testing Checklist v1 |  | Drainage Inspection and Testing Checklist v1
9f02cfc9-fd5a-4c02-9726-20feff01bc5f | section | Line Name Details
6ba55fc0-627a-457d-a0d2-b64af29ea2fb | checkpoint | Details (Pass when complete)
e2bb1fff-7c29-5221-a491-2f14b1905e52 | textbox | Start ID
95308580-e95f-5b3f-9a01-d596beb1c001 | textbox | To Finish ID
bd62f38b-75ec-5bde-8a06-cd2f37f5ebb6 | textbox | Line Name
895fdedc-b55e-56ae-8016-74a40cc04f6e | textbox | Forman:
f800f461-d036-506b-87d0-8d19effbe51a | date | Date:
37427748-5b42-586f-b6b9-5e215604020f | textbox | Road Name / Location:
b4686f3e-3aa4-5662-9f6f-335c510a275e | textbox | Engineer / Inspector:
9914b9fb-fd96-45fb-bd51-afb5d49cbb42 | section | Item Details
c63a2ae8-0d38-4980-8fac-811981266cdc | checkpoint | Details (Pass when complete)
d71c4f65-2c3f-596c-a809-30fd2eb3dd26 | textbox | Drainage Type
ad36b7a0-6ab7-588e-bada-d08aaa2bd2c6 | textbox | Drawing No
9672efc9-99aa-5b49-9395-4ac4cf11190d | textbox | Total length (metres)
19570b0f-20a7-566e-b390-e69d77a6ebd1 | textbox | Pipe Invert level (out)
3dda63ba-3896-523d-a925-93c354cb69a8 | textbox | Pipe Invert level (in)
ab170339-5ef1-50a1-8343-9886bb6fc490 | textbox | Pipe diameter
e100ff5e-e24b-51aa-b4cb-dcb405996460 | textbox | Class of pipe
f6f677f3-dbf6-567a-bfc4-4f395d341a50 | textbox | Grade (1: or %)
cd69ce94-f476-5ff7-9c89-491adeb2911f | textbox | Trench Width (600 + pipe diamater)
39bf4f09-142e-4403-89d6-95c2b60568d4 | section | Manhole/Structure
8fe8931f-3400-46fe-b78f-f6c3778cbb89 | checkpoint | Details (Pass when complete)
aef26611-db80-5fba-9836-b7ae8720e658 | textbox | Name
267bcf46-2d20-5a1f-8c62-49dd4e1cd73a | textbox | Size mm
6d7ab49f-32d2-5c64-bee9-5c7d07ca48a0 | textbox | Depth to Invert
23932769-ecb2-5822-a765-f35666088150 | textbox | Risers
10b69186-a9f2-5ad0-8e93-59b60641f528 | textbox | Number and Site
099e6c5c-f531-4323-acc5-9507e6c881fe | section | Pipe (Items Used)
d9a3c05a-9ab8-445d-a2b1-4d713cb794b7 | checkpoint | Details (Pass when complete)
a8dd26f9-7386-5f64-ae2b-08d4a05e1a66 | textbox | Starter
8996385f-0b55-5d4d-8673-490791c76ab8 | textbox | Shorts
7ef38f9c-6cfa-5b18-9b6a-e60c37a97ff4 | textbox | Length
79aff0c9-b6fe-517f-a019-ff7d451974c6 | textbox | Laterals
10604fe6-0713-5d94-8a9b-82e81cc11c9b | textbox | Shorts
693c11fd-91a9-54fb-878f-3c437aa125dc | textbox | Finisher
4c54f792-a94e-4441-81a9-c8af7e5a939c | section | Manhole/Structure
fd18c261-f5ef-49dd-8f72-5c3f48d7192e | checkpoint | Details (Pass when complete)
73000c4c-670b-503f-84f7-1fbf3cfb263f | textbox | Name
52703bc0-8682-5160-98dd-d3749dd1d33b | textbox | Size mm
97f6a219-5da3-55df-a0cd-8151d5068412 | textbox | Depth to Invert
5682d75e-e4f9-5b69-a9df-3d2502359d91 | textbox | Risers
63d71692-3850-5b44-b711-8384d22e746c | textbox | Numbers and Size
5a26b165-07b8-4c00-840d-3bb4e4e925bb | checklist | Drainage ITP |  | Drainage ITP
14165932-3700-4063-b0c1-72cba0ef9a31 | section | Prestart
677784ef-82d7-489b-9133-ba523ff0fe7a | checkpoint | Site Isolation and Fencing
29a58f60-42d0-5e76-bc96-99e80004b721 | note | Ops SOP
949ede47-0908-4a7c-a1ac-7eae779d160d | checkpoint | Erosion and sediment control plan
48356a47-7051-475c-9219-bd17a205efde | checkpoint | TTMP
5259a264-ee17-5ca5-8306-4aece00112b2 | note | Required or Not
1afa7f98-74d6-40cf-8bb5-8395b7443351 | checkpoint | Calibration is current
1025bd93-5411-45ea-86e9-591b18fcf162 | checkpoint | Materials in good condition
83d6c92e-92ce-589b-be90-9d1e17a97fd8 | note | Check materials specification
c289cf74-965d-497f-ac37-4e26ca503649 | checkpoint | Correct plans for this work
364776ae-0cbb-431c-994c-ce4c8cb8f359 | checkpoint | Witnesses advised of today’s checks
a705dab4-5aa0-4898-be25-4e1ba9478614 | signoff | Dig Permit completed
4e32f2ce-d171-4bc3-bfd3-8f4bcdb9612b | checkpoint | Excavation
5c6e933c-464b-4503-840c-e1362a8738e4 | checkpoint | Trench width
e029752f-45cf-5c60-a62d-ccf66933e272 | note | Check Specification
60cf49e4-8e8d-47e2-b141-c6736e9d7428 | signoff | Engineer check of subbase testing
6c3d6f2e-9c19-48da-94c9-de5064d77521 | section | Structures
ddc9532c-2498-4f5f-ba82-8e3413a180c5 | checkpoint | Sumps and installations
9de14d73-b1fa-5715-ac58-9d8f515ac883 | note | Check each design
5c5f0db0-f3a5-4b1b-ae78-fcc6416a7666 | signoff | Corbels and yield joints comply
bd474112-5738-4734-81a9-648e7925b885 | section | Pipe Laying
5ac4e3ab-9bdb-4b47-bdec-49b33f061653 | checkpoint | Trench is free of water
1face012-0548-57a8-afd9-7da23004eff2 | note | Must be dry
35da7852-6e73-4ecd-8336-b4c0b8e60635 | checkpoint | Pipe laid straight
d228aeda-aa7c-5f2f-9356-6fd81d4eb392 | note | Joints Cut Straight
044ad5f4-3b85-4eb4-bae5-1dfd8d73de5f | checkpoint | Grade check
e8750fe4-2a36-5232-b311-ba13d1c8553f | note | Two Peg Check
3539a923-7a8e-4d52-ac27-06107bd92f8b | checkpoint | Haunching metal used to compact
769d0ae7-40de-4ab7-830d-6a13207b4469 | signoff | Bedding and Haunching Compaction
e67a6bd7-04f1-4783-990b-a27833026028 | checkpoint | Lateral invert
99403b50-6a6b-4dd1-9a24-b364cd20f55b | checkpoint | As built records: inverts, joints, ends
4303e9c1-c58e-4e18-8528-9e1e8d5edcb8 | signoff | Backfilling approval (engineers approval)
0c900804-0ac4-4690-b5fb-9d56ce8a1904 | section | Pipe Pressure Testing
66dba5e2-08bd-4837-9c78-5d9e3705e166 | checkpoint | Air Test
b5096a28-59e4-4001-aea9-90fcaea83b60 | checkpoint | Water Test
fff83668-4a7d-4199-9400-c1c639d0ca79 | checkpoint | Gravity Pipe test check sheet
9ee190ce-e4e6-4034-84e6-4876096c6257 | signoff | Test witnessed by CCC/Engineer
51a74494-d659-4343-abba-1f755be31fbf | section | Final Pipe Inspection
04add905-257f-4bf7-96d1-86af2e24aaa9 | checkpoint | CCTV inspection of pipe run
7c8d23f6-b1fb-4c6c-9275-a4ebbe8456f2 | signoff | Inspection sheet accepted - SS Approval
f50358d1-c4bd-4aec-93f1-0b0dfc7bdf94 | section | Backfilling
4891abea-bada-47c5-b59a-1d72daeb3c67 | checkpoint | Backfill and compact each layer
088f909e-2ff7-404c-9553-5d863b716b21 | checkpoint | Back filling compaction
9d1f269d-ed7c-5991-a3a4-e4ec272c9e47 | note | Use Test Sheet
5dcdd0eb-f70f-47a0-8ebe-36c88cb19252 | checkpoint | AP40 Layer construction
75da4e4e-e9d1-574e-a8d8-3da1e925e9eb | note | Use Test Sheet
b2d82c7d-cc34-4e91-8e81-320fec000de9 | signoff | Check records for all layers (Records Collation)
408e3aeb-871f-4415-8a5c-1a0224b1f651 | checkpoint | Backfilling and compaction (photo)
b806c435-3922-481d-8713-c9270449b5a5 | signoff | Engineer Approval