## ITP
|  | Project: |  |  |  |  | BG Project Manager (PM): |  |  | BG Contracting
|  | Project Location: |  |  |  |  | BG Supervisor/Foreman (SS)/(F): |  |  | BG Contracting
|  | Job number: |  |  |  |  | BG Surveyor (SVY): |  |  | BG Contracting
[7 empty] | BG H&S Mgr (HS): |  |  | BG Contracting
Site Engineer(ENG)
Council Engineer (CENG)
[7 empty] | Subcontractor (SUB) |  |  | Various
Testing | [5 empty] | Inspection | Verification
Item # | Section | Description | Testing and inspection Methodology | Specification Reference | Hold Points | Acceptance Criteria | Responsible Person | BG Signed | Client Signed | Record
GENERAL
1.1 | General | Establishment | Risks Identified |  |  | Up to date, and specific to this contract | PM |  |  | Site Folder
1.2 | General | Health and Safety | Submitted to Client Health and Safety Representative |  |  | SSSP and SWMS produced and submitted | PM |  |  | SSSP SWMS
1.3 | General | Construction Management Plan | CMP submitted prior to the commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer | PM |  |  | CMP
1.4 | General | Quality | QA to be recorded and submitted for review |  |  | QA system needs to store test requirements in a manner that can be reasonably found on-demand | PM |  |  | ITP
1.5 | General | Environmental Management | CMP submitted prior to commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer | PM |  |  | Contract Management Plan
1.6 | General | Programme | Construction Programme supplied to engineer for approval |  |  | Approved Construction Programme | PM |  |  | Construction Programme
1.7 | General | Traffic Management | Submitted, when received back, form local authority |  | Hold Point | TMP submitted and accepted prior to work commencing within roadway | PM |  |  | TMP
1.8 | General | Archaeological and Culture | CMP submitted prior to commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer. Local iwi has been notified of intent to start work. | PM |  |  | Contract Management Plan
1.9 | General | As-Builts | As-Built drawings submitted that comply with KDC requirements |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY |  |  | As built file
EARTHWORKS
2.1 | Earthworks | Topsoil Strip | Strip Topsoil |  | Hold Point | Photos and survey prior to further works | F |  |  | Survey and photos
2.2 | Earthworks | Cut to Fill | Contractor to identify and select suitable material for fill. Quality records made available to the engineer. |  |  | Fill material approved by the Engineer | PM |  |  | Visual inspections and photos
2.3 | Earthworks | Compaction | Compact fill material to 95% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC | SVY |  |  | MDD NDM Test Records
2.4 | Earthworks | Topsoil Respread | Respread topsoil to Design FL |  |  | • Final inspection • Survey | PM SVY |  |  | Visual inspections and photos
DRAINAGE
3.1 | Drainage | Trench Base inspection | Inspect trench base prior to pipe installation | CCC CSS Part 3 Section 6.4 |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F |  |  | Photos
3.2 | Drainage | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 |  | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY |  |  | MDD NDM Test Record
3.3 | Drainage | Corbels | Corbel inspections (Pre construction and Post construction) |  | Hold Point | Ensure compliance with Local Council | F CENG |  |  | Engineer inspection Drainage Checklist
3.4 | Drainage | Pressure Testing | Air Pressuse testing (Pipes less the or equal to 450mm dia | CCC CSS Part 3 Section 14 |  | Pipe section is to be pumped to 10 kPa which is to be maintained for at least 3 minutes | F ENG |  |  | Engineer inspection Drainage Checklist
3.5 | Drainage | CCTV | CCTV inspection | CCC CSS Part 3 Section 14 |  | General pipe cleanliness and ensure there is no sudden changes in alignment, leaking or potential areas prone to leaking (open joins), pipe cracking or obstructions/debris | SUB |  |  | Test report and footage
3.6 | Drainage | Drainage Checklist | Drainage Checklist to be completed of every pipe line |  |  | Completed by Foreman for every line installed, before starting a new line | F |  |  | Drainage Checklist
3.7 | Drainage | As-Builts | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY |  |  | As-built file
FOOTPATH
4.1 | Footpath | Basecourse Material | Clean AP40 to be used |  |  | Complies with relevant material spec | F |  |  | Lab Report
4.2 | Footpath | Basecourse Compaction | Clegg hammer testing at 15m intervals | CCC CSS Part 6 Section 6.6 | Hold Point | • CLEGG test shall exceed a CIV of 25 (Residential) • CLEGG test shall exceed a CIV of 35 (Commercial) • Engineer Inspection prior to seal/concrete | SVY |  |  | Engineer inspection CLEGG Test Records
ROADING
5.1 | Roading | Subgrade | Subgrade inspection prior to placing sub-base |  | Hold Point | • There is little to no moisture on the surface, no soft spots or organic matter on and/or in the subgrade and depths are in accrodance with design. | ENG |  |  | Engineer inspection and photos
5.2 | Roading | Sub-base Material | Clean AP65 to be used |  |  | Complies with relevant material spec | PM |  |  | MDD
5.3 | Roading | Sub-base Compaction | Compact all fill materials to 95% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | SVY |  |  | Engineer inspection NDM Test Records
5.4 | Roading | Basecourse Material | Clean AP40 to be used |  |  | Complies with relevant material spec | PM |  |  | MDD
5.5 | Roading | Basecourse Compaction | Compact all fill materials to 98% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | SVY |  |  | Engineer inspection NDM Test Records
5.6 | Roading | Benkleman Beam Test | Benkleman Beam testing after basecourse compaction and prior to sealing |  | Hold Point | 95% of test must be less than specified requirements | SUB |  |  | Test report
5.7 | Roading | Pre seal Inspection | Engineer inspections prior to sealing |  | Hold Point | ensure a moziac basecourse finish has been achieved and there is no pooling/high levels of moisture in the surface. | ENG CENG |  |  | Engineers sign off
KERB AND CHANNEL
6.1 | Kerb and Channel | Basecourse Compaction | NDM testing every 10m |  | Hold Point | All ND readings shall not be less than 2150kg/m3 | SVY |  |  | NDM Test Records
6.2 | Kerb and Channel | Kerb installation | Check alignment, grade, Cutdowns, SW outlets prior to pouring |  |  | All checks completed prior to commencement of kerb pour | F |  |  | Kerb QA Checklist
6.3 | Kerb and Channel | Kerb Core Strength | 28 Days after kerb pour, 1 kerb core is to be taken for each pour |  |  | 90mm dia concrete core 28 day strength is to be greater than 20Mpa | F |  |  | Test report
SERVICES
7.1 | Services | Trench Base inspection | Inspect trench base prior to pipe installation |  |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F |  | N/A | Photos
7.2 | Services | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 | Hold Point | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY |  | N/A | MDD NDM Test Record
7.3 | Services | As-Builts | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY |  | N/A | As-built file
WATER
8.1 | Water | Trench Base inspection | Inspect trench base prior to pipe installation |  |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F |  | N/A | Photos
8.2 | Water | Thrust Block Inspection (pre construction) | Prior to backfilling and following installation of thrust block framework and reinforcing. |  | Hold Point | Ensure Complaince with Local Council | CENG |  | N/A | Inspection Sign off
8.3 | Water | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 |  | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY |  | N/A | MDD NDM Test Record
8.4 | Water | Constant pressure (water loss) method | After bedding and haunching but prior to backfilling |  | Hold Point | Test is to comply with NZS25466.2:2002 Section 6.3.4.1 | SUB |  | N/A | Test Report
8.5 | Water | Pre-construction weld testing | Prior to submain welding on site |  |  | EF welding equipment to pass weld testing criteria on specified materials prior to use on site | F |  | N/A | Test Report
8.6 | Water | Standover for any live water connections | Any Live water connections |  | Hold Point | Application for live water connection has been submitted well in advance before live connection date | CENG |  | N/A | MDD NDM Test Record
8.7 | Water | As-built | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY |  | N/A | As-built file
8.8 | Water | Serial Number of water meter | Every lot with a water meter installed |  |  | Serial number and lot recorded in a schedule | PM |  | N/A | Spreadsheet