## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP Generic Template | itp
section | GENERAL
checkpoint | 1.1 - General
label | DESCRIPTION - Establishment
label | TESTING & INSPECTION METHODOLOGY - Risks Identified
label | ACCEPTANCE CRITERIA - Up to date, and specific to this contract
label | RESPONSIBLE PERSON - PM
label | RECORD - Site Folder
checkpoint | 1.2 - General
label | DESCRIPTION - Health and Safety
label | TESTING & INSPECTION METHODOLOGY - Submitted to Client Health and Safety Representative
label | ACCEPTANCE CRITERIA - SSSP and SWMS produced and submitted
label | RESPONSIBLE PERSON - PM
label | RECORD - SSSP, SWMS
checkpoint | 1.3 - General
label | DESCRIPTION - Construction Management Plan
label | TESTING & INSPECTION METHODOLOGY - CMP submitted prior to the commencement of on site works
label | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer
label | RESPONSIBLE PERSON - PM
label | RECORD - CMP
checkpoint | 1.4 - General
label | DESCRIPTION - Quality
label | TESTING & INSPECTION METHODOLOGY - QA to be recorded and submitted for review
label | ACCEPTANCE CRITERIA - QA system needs to store test requirements in a manner that can be reasonably found on-demand
label | RESPONSIBLE PERSON - PM
label | RECORD - ITP
checkpoint | 1.5 - General
label | DESCRIPTION - Environmental Management
label | TESTING & INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works
label | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer
label | RESPONSIBLE PERSON - PM
label | RECORD - Contract Management Plan
checkpoint | 1.6 - General
label | DESCRIPTION - Programme
label | TESTING & INSPECTION METHODOLOGY - Construction Programme supplied to engineer for approval
label | ACCEPTANCE CRITERIA - Approved Construction Programme
label | RESPONSIBLE PERSON - PM
label | RECORD - Construction Programme
checkpoint | 1.7 - General
label | DESCRIPTION - Traffic Management
label | TESTING & INSPECTION METHODOLOGY - Submitted, when received back, form local authority
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - TMP submitted and accepted prior to work commencing within roadway
label | RESPONSIBLE PERSON - PM
label | RECORD - TMP
holdpoint | HOLD POINT
checkpoint | 1.8 - General
label | DESCRIPTION - Archaeological and Culture
label | TESTING & INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works
label | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer. Local iwi has been notified of intent to start work.
label | RESPONSIBLE PERSON - PM
label | RECORD - Contract Management Plan
checkpoint | 1.9 - General
label | DESCRIPTION - As-Builts
label | TESTING & INSPECTION METHODOLOGY - As-Built drawings submitted that comply with KDC requirements
label | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
label | RESPONSIBLE PERSON - SVY
label | RECORD - As built file
section | EARTHWORKS
checkpoint | 2.1 - Earthworks
label | DESCRIPTION - Topsoil Strip
label | TESTING & INSPECTION METHODOLOGY - Strip Topsoil
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Photos and survey prior to further works
label | RESPONSIBLE PERSON - F
label | RECORD - Survey and photos
holdpoint | HOLD POINT
checkpoint | 2.2 - Earthworks
label | DESCRIPTION - Cut to Fill
label | TESTING & INSPECTION METHODOLOGY - Contractor to identify and select suitable material for fill. Quality records made available to the engineer.
label | ACCEPTANCE CRITERIA - Fill material approved by the Engineer
label | RESPONSIBLE PERSON - PM
label | RECORD - Visual inspections and photos
checkpoint | 2.3 - Earthworks
label | DESCRIPTION - Compaction
label | TESTING & INSPECTION METHODOLOGY - Compact fill material to 95% of MDD
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC
label | RESPONSIBLE PERSON - SVY
label | RECORD - MDD, NDM Test Records
holdpoint | HOLD POINT
checkpoint | 2.4 - Earthworks
label | DESCRIPTION - Topsoil Respread
label | TESTING & INSPECTION METHODOLOGY - Respread topsoil to Design FL
label | ACCEPTANCE CRITERIA - Final inspection
label | ○ Survey
label | RESPONSIBLE PERSON - PM, SVY
label | RECORD - Visual inspections and photos
section | DRAINAGE
checkpoint | 3.1 - Drainage
label | DESCRIPTION - Trench Base inspection
label | TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
label | SPECIFICATION REFERENCE - CCC CSS Part 3, Section 6.4
label | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
label | RESPONSIBLE PERSON - F
label | RECORD - Photos
checkpoint | 3.2 - Drainage
label | DESCRIPTION - Backfilling
label | TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
label | SPECIFICATION REFERENCE - CCC CSS Part 1, Section 32
label | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
label | RESPONSIBLE PERSON - SVY
label | RECORD - MDD, NDM Test Record
checkpoint | 3.3 - Drainage
label | DESCRIPTION - Corbels
label | TESTING & INSPECTION METHODOLOGY - Corbel inspections (Pre construction and Post construction)
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Ensure compliance with Local Council
label | RESPONSIBLE PERSON - F, CENG
label | RECORD - Engineer inspection, Drainage Checklist
holdpoint | HOLD POINT
checkpoint | 3.4 - Drainage
label | DESCRIPTION - Pressure Testing
label | TESTING & INSPECTION METHODOLOGY - Air Pressuse testing (Pipes less the or equal to 450mm dia
label | SPECIFICATION REFERENCE - CCC CSS Part 3, Section 14
label | ACCEPTANCE CRITERIA - Pipe section is to be pumped to 10 kPa which is to be maintained for at least 3 minutes
label | RESPONSIBLE PERSON - F, ENG
label | RECORD - Engineer inspection, Drainage Checklist
checkpoint | 3.5 - Drainage
label | DESCRIPTION - CCTV
label | TESTING & INSPECTION METHODOLOGY - CCTV inspection
label | SPECIFICATION REFERENCE - CCC CSS Part 3, Section 14
label | ACCEPTANCE CRITERIA - General pipe cleanliness and ensure there is no sudden changes in alignment, leaking or potential areas prone to leaking (open joins), pipe cracking or obstructions/debris
label | RESPONSIBLE PERSON - SUB
label | RECORD - Test report and footage
checkpoint | 3.6 - Drainage
label | DESCRIPTION - Drainage Checklist
label | TESTING & INSPECTION METHODOLOGY - Drainage Checklist to be completed of every pipe line
label | ACCEPTANCE CRITERIA - Completed by Foreman for every line installed, before starting a new line
label | RESPONSIBLE PERSON - F
label | RECORD - Drainage Checklist
checkpoint | 3.7 - Drainage
label | DESCRIPTION - As-Builts
label | TESTING & INSPECTION METHODOLOGY - As-built survey
label | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
label | RESPONSIBLE PERSON - SVY
label | RECORD - As-built file
section | FOOTPATH
checkpoint | 4.1 - Footpath
label | DESCRIPTION - Basecourse Material
label | TESTING & INSPECTION METHODOLOGY - Clean AP40 to be used
label | ACCEPTANCE CRITERIA - Complies with relevant material spec
label | RESPONSIBLE PERSON - F
label | RECORD - Lab Report
checkpoint | 4.2 - Footpath
label | DESCRIPTION - Basecourse Compaction
label | TESTING & INSPECTION METHODOLOGY - Clegg hammer testing at 15m intervals
label | SPECIFICATION REFERENCE - CCC CSS Part 6, Section 6.6
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - CLEGG test shall exceed a CIV of 25 (Residential)
label | ○ CLEGG test shall exceed a CIV of 35 (Commercial)
label | ○ Engineer Inspection prior to seal/concrete
label | RESPONSIBLE PERSON - SVY
label | RECORD - Engineer inspection, CLEGG Test Records
holdpoint | HOLD POINT
section | ROADING
checkpoint | 5.1 - Roading
label | DESCRIPTION - Subgrade
label | TESTING & INSPECTION METHODOLOGY - Subgrade inspection prior to placing sub-base
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - There is little to no moisture on the surface, no soft spots or organic matter on and/or in the subgrade and depths are in accrodance with design.
label | RESPONSIBLE PERSON - ENG
label | RECORD - Engineer inspection and photos
holdpoint | HOLD POINT
checkpoint | 5.2 - Roading
label | DESCRIPTION - Sub-base Material
label | TESTING & INSPECTION METHODOLOGY - Clean AP65 to be used
label | ACCEPTANCE CRITERIA - Complies with relevant material spec
label | RESPONSIBLE PERSON - PM
label | RECORD - MDD
checkpoint | 5.3 - Roading
label | DESCRIPTION - Sub-base Compaction
label | TESTING & INSPECTION METHODOLOGY - Compact all fill materials to 95% of MDD
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC.
label | ○ Test every 10m alternating between LHS and RHS
label | RESPONSIBLE PERSON - SVY
label | RECORD - Engineer inspection, NDM Test Records
holdpoint | HOLD POINT
checkpoint | 5.4 - Roading
label | DESCRIPTION - Basecourse Material
label | TESTING & INSPECTION METHODOLOGY - Clean AP40 to be used
label | ACCEPTANCE CRITERIA - Complies with relevant material spec
label | RESPONSIBLE PERSON - PM
label | RECORD - MDD
checkpoint | 5.5 - Roading
label | DESCRIPTION - Basecourse Compaction
label | TESTING & INSPECTION METHODOLOGY - Compact all fill materials to 98% of MDD
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC.
label | ○ Test every 10m alternating between LHS and RHS
label | RESPONSIBLE PERSON - SVY
label | RECORD - Engineer inspection, NDM Test Records
holdpoint | HOLD POINT
checkpoint | 5.6 - Roading
label | DESCRIPTION - Benkleman Beam Test
label | TESTING & INSPECTION METHODOLOGY - Benkleman Beam testing after basecourse compaction and prior to sealing
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - 95% of test must be less than specified requirements
label | RESPONSIBLE PERSON - SUB
label | RECORD - Test report
holdpoint | HOLD POINT
checkpoint | 5.7 - Roading
label | DESCRIPTION - Pre seal Inspection
label | TESTING & INSPECTION METHODOLOGY - Engineer inspections prior to sealing
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - ensure a moziac basecourse finish has been achieved and there is no pooling/high levels of moisture in the surface.
label | RESPONSIBLE PERSON - ENG, CENG
label | RECORD - Engineers sign off
holdpoint | HOLD POINT
section | KERB AND CHANNEL
checkpoint | 6.1 - Kerb and Channel
label | DESCRIPTION - Basecourse Compaction
label | TESTING & INSPECTION METHODOLOGY - NDM testing every 10m
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - All ND readings shall not be less than 2150kg/m3
label | RESPONSIBLE PERSON - SVY
label | RECORD - NDM Test Records
holdpoint | HOLD POINT
checkpoint | 6.2 - Kerb and Channel
label | DESCRIPTION - Kerb installation
label | TESTING & INSPECTION METHODOLOGY - Check alignment, grade, Cutdowns, SW outlets prior to pouring
label | ACCEPTANCE CRITERIA - All checks completed prior to commencement of kerb pour
label | RESPONSIBLE PERSON - F
label | RECORD - Kerb QA Checklist
checkpoint | 6.3 - Kerb and Channel
label | DESCRIPTION - Kerb Core Strength
label | TESTING & INSPECTION METHODOLOGY - 28 Days after kerb pour, 1 kerb core is to be taken for each pour
label | ACCEPTANCE CRITERIA - 90mm dia concrete core 28 day strength is to be greater than 20Mpa
label | RESPONSIBLE PERSON - F
label | RECORD - Test report
section | SERVICES
checkpoint | 7.1 - Services
label | DESCRIPTION - Trench Base inspection
label | TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
label | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
label | RESPONSIBLE PERSON - F
label | RECORD - Photos
checkpoint | 7.2 - Services
label | DESCRIPTION - Backfilling
label | TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
label | SPECIFICATION REFERENCE - CCC CSS Part 1, Section 32
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
label | RESPONSIBLE PERSON - SVY
label | RECORD - MDD, NDM Test Record
holdpoint | HOLD POINT
checkpoint | 7.3 - Services
label | DESCRIPTION - As-Builts
label | TESTING & INSPECTION METHODOLOGY - As-built survey
label | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
label | RESPONSIBLE PERSON - SVY
label | RECORD - As-built file
section | WATER
checkpoint | 8.1 - Water
label | DESCRIPTION - Trench Base inspection
label | TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
label | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
label | RESPONSIBLE PERSON - F
label | RECORD - Photos
checkpoint | 8.2 - Water
label | DESCRIPTION - Thrust Block Inspection (pre construction)
label | TESTING & INSPECTION METHODOLOGY - Prior to backfilling and following installation of thrust block framework and reinforcing.
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Ensure Complaince with Local Council
label | RESPONSIBLE PERSON - CENG
label | RECORD - Inspection Sign off
holdpoint | HOLD POINT
checkpoint | 8.3 - Water
label | DESCRIPTION - Backfilling
label | TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
label | SPECIFICATION REFERENCE - CCC CSS Part 1, Section 32
label | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
label | RESPONSIBLE PERSON - SVY
label | RECORD - MDD, NDM Test Record
checkpoint | 8.4 - Water
label | DESCRIPTION - Constant pressure (water loss) method
label | TESTING & INSPECTION METHODOLOGY - After bedding and haunching but prior to backfilling
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Test is to comply with NZS25466.2:2002 Section 6.3.4.1
label | RESPONSIBLE PERSON - SUB
label | RECORD - Test Report
holdpoint | HOLD POINT
checkpoint | 8.5 - Water
label | DESCRIPTION - Pre-construction weld testing
label | TESTING & INSPECTION METHODOLOGY - Prior to submain welding on site
label | ACCEPTANCE CRITERIA - EF welding equipment to pass weld testing criteria on specified materials prior to use on site
label | RESPONSIBLE PERSON - F
label | RECORD - Test Report
checkpoint | 8.6 - Water
label | DESCRIPTION - Standover for any live water connections
label | TESTING & INSPECTION METHODOLOGY - Any Live water connections
label | HOLD POINTS - Hold Point
label | ACCEPTANCE CRITERIA - Application for live water connection has been submitted well in advance before live connection date
label | RESPONSIBLE PERSON - CENG
label | RECORD - MDD, NDM Test Record
holdpoint | HOLD POINT
checkpoint | 8.7 - Water
label | DESCRIPTION - As-built
label | TESTING & INSPECTION METHODOLOGY - As-built survey
label | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
label | RESPONSIBLE PERSON - SVY
label | RECORD - As-built file
checkpoint | 8.8 - Water
label | DESCRIPTION - Serial Number of water meter
label | TESTING & INSPECTION METHODOLOGY - Every lot with a water meter installed
label | ACCEPTANCE CRITERIA - Serial number and lot recorded in a schedule
label | RESPONSIBLE PERSON - PM
label | RECORD - Spreadsheet