## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Boardwalk Checklist 1 | [5 empty] | Boardwalk Checklist 1
section | Details
checkpoint | 30 mpa concrete pile 450mm dia 450mm deep
checkpoint | 150mm gap above gound
checkpoint | H5 140mm x 140mm timber posts
checkpoint | quantity and locations piles correct
checkpoint | H3.2 240mm x 45mm joist @ max500mm crs
checkpoint | straps/fixings/bolts/nails plates all secured
checkpoint | level of boardwalk correct
checkpoint | 50mm gap between boardwalk structure and retaining wall
checkpoint | 150x70 capping with light fitting
checkpoint | 50x50 balustrade bajttens