## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-007-STR-Material Inspection-Precast Barrier Kerb | itp |  |  |  |  | CHK-007-STR-Material Inspection-Precast Barrier Kerb Rev 0
section | Details
checkpoint-no-value | 1. Referenced Documentation
label | Document Title: CHK-001-STR-CPD-Material Inspection-Precat Barriers & Kerbs
label | ITP Description: CPD-Material Inspection-Precat Barriers & Kerbs
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 14/11/2024
label | ITP created by: Ahmed Abdelsalam
label | ITP approved for use by: Pradeep Talasila
section | 2. Preliminary
checkpoint | 1 - Delivery Details
label | Acceptance Criteria -
textbox | Enter: Delivery Docket Number:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
label | ○ Attach: Delivery Docket and packaging Slip
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
label | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
label | Method - Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | Method - Document Review
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 5 - Packaging Inspection-Transport
label | Acceptance Criteria - Is the condition of packaging acceptable.
label | ○ Precast items are protected from damage during the transport
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 6 - Fault IDs:
label | Acceptance Criteria - For each precast type delivered, check for the following:
label | 1 - Identification markings match the panel type
label | 2 - Panels fabricated as per drawings
label | 3 - Cracks
label | 4 - Spalling/Damage to concrete surface
label | 5 - Exposed Reinforcement
label | 6 - Damage to Anti-Graffiti coating
label | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
date | Date Completed:
checkpoint | 7 - Check for Faults - 1
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 2
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 3
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 4
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Check for Faults - 5
label | Reference - Item 6 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP