## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | HPP-UGL-CIV-GN-GEN-ITP-021 Bollard Installation - Rev.0 | itp | HPP-UGL-CIV-GN-GEN-ITP-021 Bollard Installation - Rev.0 |  | 5c136609-d3ea-4917-955a-8f4f9a6b3ec5
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Documentation
73900dfc-4921-5270-8f79-eaa37971e070 | note | Ref docs - Issued drawings / Site copy drawings
cac828de-8e61-512a-91d1-32d247a0c3a9 | note | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
cd5fcafc-835d-542a-9d3e-e60ccab59282 | button | Acceptance | Yes,No,N/A
acea05d4-588e-59c6-8a3d-55baf8df60d3 | note | HPP CON Key - S
c9fc699f-735d-58fc-ae57-b303a5749895 | note | HPP QA Key - S
| checkpoint | 1.2 - Lot Traceability
867902d1-89b7-5d18-9849-f34d93456357 | note | Ref docs - Spec. 0161 Quality [Cl 7.3]
eac15c2f-7894-5d20-8fda-07c87c173226 | note | Acceptance criteria - Prepare a lot map for traceability of the work area.
f4278a31-c5be-5336-be9f-efed28522780 | button | Acceptance | Yes,No,N/A
d803184b-20d3-5877-97ba-15c46a74fa65 | note | HPP CON Key - S
f0d33d03-69a7-5e09-b702-b3b2a6c331d2 | note | HPP QA Key - S
1a31c448-2573-58d1-bf76-d08bd22f03bf | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
187bd0fb-35f7-5102-a397-6e3de83ffca6 | tickbox | Lot Map
| checkpoint | 1.3 - Confirm Bollard Type
356230bd-54dd-5584-bd03-387f0a41deb0 | note | Ref docs - Drawings
77939aa9-0d5b-5a94-bb41-16cba6d5c823 | note | Acceptance criteria - Confirm bollard type as detailed on the drawings.
96acb761-0cca-5721-95fd-907d484eb247 | button | Acceptance | Yes,No,N/A
3d4e7ab0-30ad-51c3-8059-be520cb24965 | note | HPP CON Key - S
0ef6c693-ba61-5cfa-bf14-9589c1bf80ac | note | HPP QA Key - S
7b8cff58-4418-5309-b161-3609f361715f | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
28289cb9-1b10-5977-a469-5ce260b76e1f | tickbox | Checklist
| checkpoint | 1.4 - Setout bollard location
51fd4f0f-1017-51ff-a434-ef4aa830a4a1 | note | Ref docs - Drawings
91cd5f97-c727-5195-974a-6bd44553c743 | note | Acceptance criteria - Setout bollard at locations as detailed on the drawings
c904968e-ae4d-5124-bb1d-25d73213dec5 | button | Acceptance | Yes,No,N/A
3c5883df-4736-55b5-b05f-e47f8c017387 | note | HPP CON Key - S
f0be3afb-b38c-5b5f-b2de-cd01567a60e2 | note | HPP QA Key - S
97cceb70-be01-5f85-aef7-4b322bc63494 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
333d7b59-2081-567c-a42b-01752d25b7fd | tickbox | Checklist
| checkpoint | 1.5 - Excavation Permit
19ecb653-46fa-5c94-9cd8-262a3c6d93c5 | note | Ref docs - Drawings
47060844-7815-597e-ab9d-c2b32ae1a98e | note | Acceptance criteria - Ensure approved excavation permit is in place and review on site – if required
701d10c3-b680-5872-98ab-b466b76ae426 | button | Acceptance | Yes,No,N/A
d2ef0cd3-a222-5494-9e3b-a60354ab6042 | note | HPP CON Key - S
ab3c6390-2ade-524c-a206-b6578c4d141e | note | HPP QA Key - S
a6c88038-f02f-5b22-9ef2-51589a1505a2 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
d29a8f45-d564-5373-800c-916c20cbd29f | tickbox | Checklist
| section | 2.0 Site Preparation
| checkpoint | 2.1 - Location
11e691ee-17d5-5d75-b56e-3f1a6a8eba92 | note | Ref docs - Drawings
7988997f-4f35-59b4-915d-28fb544cdc18 | note | Acceptance criteria - Confirm location and place setout offset marks
d024570f-3a62-5099-8e9d-37ac57db0d20 | button | Acceptance | Yes,No,N/A
848b8d25-2a42-5e23-ad30-ae4b3bc612f2 | note | HPP CON Key - S
e2f044db-1cec-592d-bf9b-f749a9e1fa2f | note | HPP QA Key - S
ffd19249-369b-5e0f-a2ce-791817f76017 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
e1521c6c-db7d-5263-8376-cc38d62ccc13 | tickbox | Checklist
| checkpoint | 2.2 - Underground utilities
cdb0944e-8a43-54e3-8405-a53164d346a7 | note | Ref docs - Drawings
1201cd36-abec-5444-a298-899090383c74 | note | Acceptance criteria - Check utilities to avoid footing clashing
ee3f60e1-811e-5f22-a141-265d9f2ae6aa | button | Acceptance | Yes,No,N/A
67acb78c-d4a6-5a34-8ff2-5f7b804b8ed7 | note | HPP CON Key - S
c166969f-96fa-557d-a668-4657f0bb5f26 | note | HPP QA Key - S
b7363661-04aa-5db8-91bf-86a66fdf223f | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
69908cba-cd4a-54c2-ac37-55c97b34c2cd | tickbox | Checklist
| section | 3.0 Installation Process - In concrete
| checkpoint | 3.1 - Anchors
fe2db7da-5ca5-5ee1-a48b-71543b853652 | note | Ref docs - Drawings
48627c70-9e1d-51aa-a246-44c93c996b89 | note | Acceptance criteria - Install specified anchor bolts following manufacturers requirements
26df8bb3-b017-5bfd-bafc-e95306112fc7 | button | Acceptance | Yes,No,N/A
942192ea-d134-5419-8d5f-60c714a632f2 | note | Key - S
584ae11c-6996-52bc-a995-5ab3a3a07e4d | note | HPP CON Key - S
26817f94-7013-55c4-8f7d-328d72949204 | note | HPP QA Key - S
b37c239d-8fc2-5f0d-b890-7e98b085677f | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
88e9a939-a7c7-5f4e-a1fe-f11a31f73ef9 | tickbox | Checklist
| section | 4.0 Installation Process - In pavement
| checkpoint | 4.1 - Excavation
feb411ef-e106-5db1-a898-50973966c747 | note | Ref docs - Drawings
5ba35a3d-13a2-5d56-8f86-e762b6118b24 | note | Acceptance criteria - Vacuum excavate site according to bollard specifications (depth and width based on bollard type and use case)
71a16fab-4645-460a-8ec7-709b7fb3281e | note | ○ TYPE 5 - 450mm diameter x 500mm deep
6d51ae06-1094-57ed-8ee3-f7a205ff5454 | button | Acceptance | Yes,No,N/A
940a10d8-2d7c-50b4-8696-1e31daaa61c7 | note | Key - S
d3f70b1a-393b-585a-8cde-90233ae56cca | note | HPP CON Key - S
01a1dd6a-65f8-5326-86d3-c678c2af2007 | note | HPP QA Key - S
a54be877-90c5-5e32-96da-7f4da2f678d6 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
800d0624-4a66-5e1b-ae34-81cd67f456af | tickbox | Checklist
| checkpoint | 4.2 - Placement
c70081b9-a7b2-538b-927f-0a2fc92da6e3 | note | Ref docs - Drawings
3a651fe5-6a74-522a-8127-030b981302cb | note | Acceptance criteria - Position and secure bollard or sleeve in hole before pouring concrete
7fda9220-abf4-5bcd-90bb-d05e0b3948b6 | button | Acceptance | Yes,No,N/A
5ea65a69-457b-5d72-9229-2437cd1569fd | note | Key - S
bcbb14fc-9546-5290-9dce-760fcd35d2e4 | note | HPP CON Key - S
bf004806-1d3d-5c29-a6a3-1d2a8024741f | note | HPP QA Key - S
d8f88ee5-aa82-5de3-bbe1-4a53c5857067 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
66a72b0b-4576-5b14-b660-f74fb92460f9 | tickbox | Checklist
| checkpoint | 4.3 - Concrete - footing
9fd724ad-7c58-58e9-a545-41e5809545c3 | note | Ref docs - Drawings
d57c3bce-3923-5e0a-b42f-930616750e56 | note | Acceptance criteria - Fill N32 concrete around bollard foundation, slope the top of concrete down away from bollard all round
0b19df16-cd57-5b94-abb0-402d79293d17 | button | Acceptance | Yes,No,N/A
b78c6dbd-908b-52eb-9a70-e1ec84e495ff | note | Key - S
b3040641-4b83-5bdf-b57a-b31d5b047cba | note | HPP CON Key - S
595a840a-196c-51e1-b7a5-627af4a9c4df | note | HPP QA Key - S
77283a36-c1d8-5725-bcb8-b35e27104b56 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3cdb56df-b3b4-5e63-a11d-32f1031fb81d | tickbox | Checklist
| section | 5.0 Finishes
| checkpoint | 5.1 - Eyelets
38a0ce9d-dde5-53dc-8c65-54762ed2c04f | note | Ref docs - Drawings
00516d55-a33e-5990-90b4-88f607947382 | note | Acceptance criteria - Install eyelets in locations shown on drawings
1e04cd88-a39c-5e58-a3ed-81784c11a6c5 | button | Acceptance | Yes,No,N/A
a41fb0e0-f9a4-5e5a-9373-67e21a7662db | note | Key - S
d62d3284-3a6c-553a-98aa-84a7c61df967 | note | HPP CON Key - S
84a69bf6-11c7-5d33-a137-e3b6ba63cb29 | note | HPP QA Key - S
4dffe71c-b26b-5549-a13b-94a7e7ee04b6 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
110def9a-1d03-5fa8-886d-349cbb3ec8ab | tickbox | Checklist
| checkpoint | 5.2 - Concrete - bollard
c944850c-04d4-5f4b-bb84-243f28b0b342 | note | Ref docs - Drawings
d773e797-c78c-5257-ac17-aee5f5c7e1de | note | Acceptance criteria - Fill bollard with concrete – if detailed on the drawings
c4520f0c-5ef5-5663-b122-0310ccd2e1b0 | button | Acceptance | Yes,No,N/A
79e05411-637b-5e1e-a80e-ac96244ad9cc | note | Key - S
a184c241-295e-56aa-bc4c-c9215d22d71c | note | HPP CON Key - S
ad9eb101-e4ee-56fb-bdee-87fc968302f9 | note | HPP QA Key - S
0bf7b37a-cd36-5ac1-ad08-f653293d4ffc | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
3b129096-0490-54ee-a7fd-37bc6d4481fa | tickbox | Checklist
| checkpoint | 5.3 - Final Inspection
238e88d5-57ad-58d6-99bc-d8641a8e3454 | note | Ref docs - Drawings
5ce543fc-beea-5ca5-9291-e4f78f5637b7 | note | Acceptance criteria - Inspect bollard and apply touch up paint to any damaged areas
aa539510-604c-5b4b-afb5-61528a7f8610 | button | Acceptance | Yes,No,N/A
2a738bac-a665-5ffb-b4ef-da77ecba72d1 | note | Key - S
98c08bd8-515a-50cc-baa5-52432a614431 | note | HPP CON Key - S
a1aad8fa-f0d6-5df1-9f47-e7b9dc6802e3 | note | HPP QA Key - S
03eb0177-f8e4-5c9a-ad7f-96f6a7ff288a | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
fa251d4a-eb78-5470-8642-1c5be5e2338c | tickbox | Checklist
| section | 6.0 Acceptance of Works
| checkpoint | 6.1 - Acceptance and closure of non-conforming items
6dcab6c0-55c0-5727-917c-8df8fee96837 | note | Ref docs - Spec. 0161 Quality [Cl 3.8]
53807c0d-3223-5a0b-bbce-15bc73f1a259 | note | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
e47c4d0c-2f7a-5e76-b593-ed15bbf3e68e | note | ○ HOLD POINT
f7f7ac09-ce58-5086-8767-3d34ac2b543d | button | Acceptance | Yes,No,N/A
986c79be-5b94-546a-81be-ca8b7d5f2f55 | note | HPP CON Key - H
9390f524-f45d-5f72-8896-ad4cf5e831e8 | note | HPP QA Key - H
| signoff | AUTHORITY HOLDPOINT