## Sheet1
1.1 | General | Establishment | Risks Identified |  |  | Up to date, and specific to this contract | PM | Site Folder | 1.1 - General | DESCRIPTION - Establishment | TESTING &amp; INSPECTION METHODOLOGY - Risks Identified | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Up to date, and specific to this contract | RESPONSIBLE PERSON - PM | RECORD - Site Folder | 1.1 - General
1.2 | General | Health and Safety | Submitted to Client Health and Safety Representative |  |  | SSSP and SWMS produced and submitted | PM | SSSP SWMS | 1.2 - General | DESCRIPTION - Health and Safety | TESTING &amp; INSPECTION METHODOLOGY - Submitted to Client Health and Safety Representative | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - SSSP and SWMS produced and submitted | RESPONSIBLE PERSON - PM | RECORD - SSSP SWMS | DESCRIPTION - Establishment
1.3 | General | Construction Management Plan | CMP submitted prior to the commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer | PM | CMP | 1.3 - General | DESCRIPTION - Construction Management Plan | TESTING &amp; INSPECTION METHODOLOGY - CMP submitted prior to the commencement of on site works | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer | RESPONSIBLE PERSON - PM | RECORD - CMP | TESTING & INSPECTION METHODOLOGY - Risks Identified
1.4 | General | Quality | QA to be recorded and submitted for review |  |  | QA system needs to store test requirements in a manner that can be reasonably found on-demand | PM | ITP | 1.4 - General | DESCRIPTION - Quality | TESTING &amp; INSPECTION METHODOLOGY - QA to be recorded and submitted for review | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - QA system needs to store test requirements in a manner that can be reasonably found on-demand | RESPONSIBLE PERSON - PM | RECORD - ITP | SPECIFICATION REFERENCE -
1.5 | General | Environmental Management | CMP submitted prior to commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer | PM | Contract Management Plan | 1.5 - General | DESCRIPTION - Environmental Management | TESTING &amp; INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer | RESPONSIBLE PERSON - PM | RECORD - Contract Management Plan | HOLD POINTS -
1.6 | General | Programme | Construction Programme supplied to engineer for approval |  |  | Approved Construction Programme | PM | Construction Programme | 1.6 - General | DESCRIPTION - Programme | TESTING &amp; INSPECTION METHODOLOGY - Construction Programme supplied to engineer for approval | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Approved Construction Programme | RESPONSIBLE PERSON - PM | RECORD - Construction Programme | ACCEPTANCE CRITERIA - Up to date, and specific to this contract
1.7 | General | Traffic Management | Submitted, when received back, form local authority |  | Hold Point | TMP submitted and accepted prior to work commencing within roadway | PM | TMP | 1.7 - General | DESCRIPTION - Traffic Management | TESTING &amp; INSPECTION METHODOLOGY - Submitted, when received back, form local authority | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - TMP submitted and accepted prior to work commencing within roadway | RESPONSIBLE PERSON - PM | RECORD - TMP | RESPONSIBLE PERSON - PM
1.8 | General | Archaeological and Culture | CMP submitted prior to commencement of on site works |  |  | CMP submitted before commencing work, to be approved by Engineer. Local iwi has been notified of intent to start work. | PM | Contract Management Plan | 1.8 - General | DESCRIPTION - Archaeological and Culture | TESTING &amp; INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer. Local iwi has been notified of intent to start work. | RESPONSIBLE PERSON - PM | RECORD - Contract Management Plan | RECORD - Site Folder
1.9 | General | As-Builts | As-Built drawings submitted that comply with KDC requirements |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY | As built file | 1.9 - General | DESCRIPTION - As-Builts | TESTING &amp; INSPECTION METHODOLOGY - As-Built drawings submitted that comply with KDC requirements | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request | RESPONSIBLE PERSON - SVY | RECORD - As built file | 1.2 - General
2.1 | Earthworks | Topsoil Strip | Strip Topsoil |  | Hold Point | Photos and survey prior to further works | F | Survey and photos | 2.1 - Earthworks | DESCRIPTION - Topsoil Strip | TESTING &amp; INSPECTION METHODOLOGY - Strip Topsoil | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Photos and survey prior to further works | RESPONSIBLE PERSON - F | RECORD - Survey and photos | DESCRIPTION - Health and Safety
2.2 | Earthworks | Cut to Fill | Contractor to identify and select suitable material for fill. Quality records made available to the engineer. |  |  | Fill material approved by the Engineer | PM | Visual inspections and photos | 2.2 - Earthworks | DESCRIPTION - Cut to Fill | TESTING &amp; INSPECTION METHODOLOGY - Contractor to identify and select suitable material for fill. Quality records made available to the engineer. | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Fill material approved by the Engineer | RESPONSIBLE PERSON - PM | RECORD - Visual inspections and photos | TESTING & INSPECTION METHODOLOGY - Submitted to Client Health and Safety Representative
2.3 | Earthworks | Compaction | Compact fill material to 95% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC | SVY | MDD NDM Test Records | 2.3 - Earthworks | DESCRIPTION - Compaction | TESTING &amp; INSPECTION METHODOLOGY - Compact fill material to 95% of MDD | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC | RESPONSIBLE PERSON - SVY | RECORD - MDD NDM Test Records | SPECIFICATION REFERENCE -
2.4 | Earthworks | Topsoil Respread | Respread topsoil to Design FL |  |  | • Final inspection • Survey | PM SVY | Visual inspections and photos | 2.4 - Earthworks | DESCRIPTION - Topsoil Respread | TESTING &amp; INSPECTION METHODOLOGY - Respread topsoil to Design FL | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - • Final inspection • Survey | RESPONSIBLE PERSON - PM SVY | RECORD - Visual inspections and photos | HOLD POINTS -
3.1 | Drainage | Trench Base inspection | Inspect trench base prior to pipe installation | CCC CSS Part 3 Section 6.4 |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F | Photos | 3.1 - Drainage | DESCRIPTION - Trench Base inspection | TESTING &amp; INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation | SPECIFICATION REFERENCE - CCC CSS Part 3 Section 6.4 | HOLD POINTS - | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | RESPONSIBLE PERSON - F | RECORD - Photos | ACCEPTANCE CRITERIA - SSSP and SWMS produced and submitted
3.2 | Drainage | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 |  | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY | MDD NDM Test Record | 3.2 - Drainage | DESCRIPTION - Backfilling | TESTING &amp; INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals | SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32 | HOLD POINTS - | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | RESPONSIBLE PERSON - SVY | RECORD - MDD NDM Test Record | RESPONSIBLE PERSON - PM
3.3 | Drainage | Corbels | Corbel inspections (Pre construction and Post construction) |  | Hold Point | Ensure compliance with Local Council | F CENG | Engineer inspection Drainage Checklist | 3.3 - Drainage | DESCRIPTION - Corbels | TESTING &amp; INSPECTION METHODOLOGY - Corbel inspections (Pre construction and Post construction) | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Ensure compliance with Local Council | RESPONSIBLE PERSON - F CENG | RECORD - Engineer inspection Drainage Checklist | RECORD - SSSP SWMS
3.4 | Drainage | Pressure Testing | Air Pressuse testing (Pipes less the or equal to 450mm dia | CCC CSS Part 3 Section 14 |  | Pipe section is to be pumped to 10 kPa which is to be maintained for at least 3 minutes | F ENG | Engineer inspection Drainage Checklist | 3.4 - Drainage | DESCRIPTION - Pressure Testing | TESTING &amp; INSPECTION METHODOLOGY - Air Pressuse testing (Pipes less the or equal to 450mm dia | SPECIFICATION REFERENCE - CCC CSS Part 3 Section 14 | HOLD POINTS - | ACCEPTANCE CRITERIA - Pipe section is to be pumped to 10 kPa which is to be maintained for at least 3 minutes | RESPONSIBLE PERSON - F ENG | RECORD - Engineer inspection Drainage Checklist | 1.3 - General
3.5 | Drainage | CCTV | CCTV inspection | CCC CSS Part 3 Section 14 |  | General pipe cleanliness and ensure there is no sudden changes in alignment, leaking or potential areas prone to leaking (open joins), pipe cracking or obstructions/debris | SUB | Test report and footage | 3.5 - Drainage | DESCRIPTION - CCTV | TESTING &amp; INSPECTION METHODOLOGY - CCTV inspection | SPECIFICATION REFERENCE - CCC CSS Part 3 Section 14 | HOLD POINTS - | ACCEPTANCE CRITERIA - General pipe cleanliness and ensure there is no sudden changes in alignment, leaking or potential areas prone to leaking (open joins), pipe cracking or obstructions/debris | RESPONSIBLE PERSON - SUB | RECORD - Test report and footage | DESCRIPTION - Construction Management Plan
3.6 | Drainage | Drainage Checklist | Drainage Checklist to be completed of every pipe line |  |  | Completed by Foreman for every line installed, before starting a new line | F | Drainage Checklist | 3.6 - Drainage | DESCRIPTION - Drainage Checklist | TESTING &amp; INSPECTION METHODOLOGY - Drainage Checklist to be completed of every pipe line | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Completed by Foreman for every line installed, before starting a new line | RESPONSIBLE PERSON - F | RECORD - Drainage Checklist | TESTING & INSPECTION METHODOLOGY - CMP submitted prior to the commencement of on site works
3.7 | Drainage | As-Builts | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY | As-built file | 3.7 - Drainage | DESCRIPTION - As-Builts | TESTING &amp; INSPECTION METHODOLOGY - As-built survey | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request | RESPONSIBLE PERSON - SVY | RECORD - As-built file | SPECIFICATION REFERENCE -
4.1 | Footpath | Basecourse Material | Clean AP40 to be used |  |  | Complies with relevant material spec | F | Lab Report | 4.1 - Footpath | DESCRIPTION - Basecourse Material | TESTING &amp; INSPECTION METHODOLOGY - Clean AP40 to be used | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Complies with relevant material spec | RESPONSIBLE PERSON - F | RECORD - Lab Report | HOLD POINTS -
4.2 | Footpath | Basecourse Compaction | Clegg hammer testing at 15m intervals | CCC CSS Part 6 Section 6.6 | Hold Point | • CLEGG test shall exceed a CIV of 25 (Residential) • CLEGG test shall exceed a CIV of 35 (Commercial) • Engineer Inspection prior to seal/concrete | SVY | Engineer inspection CLEGG Test Records | 4.2 - Footpath | DESCRIPTION - Basecourse Compaction | TESTING &amp; INSPECTION METHODOLOGY - Clegg hammer testing at 15m intervals | SPECIFICATION REFERENCE - CCC CSS Part 6 Section 6.6 | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - • CLEGG test shall exceed a CIV of 25 (Residential) • CLEGG test shall exceed a CIV of 35 (Commercial) • Engineer Inspection prior to seal/concrete | RESPONSIBLE PERSON - SVY | RECORD - Engineer inspection CLEGG Test Records | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer
5.1 | Roading | Subgrade | Subgrade inspection prior to placing sub-base |  | Hold Point | • There is little to no moisture on the surface, no soft spots or organic matter on and/or in the subgrade and depths are in accrodance with design. | ENG | Engineer inspection and photos | 5.1 - Roading | DESCRIPTION - Subgrade | TESTING &amp; INSPECTION METHODOLOGY - Subgrade inspection prior to placing sub-base | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - • There is little to no moisture on the surface, no soft spots or organic matter on and/or in the subgrade and depths are in accrodance with design. | RESPONSIBLE PERSON - ENG | RECORD - Engineer inspection and photos | RESPONSIBLE PERSON - PM
5.2 | Roading | Sub-base Material | Clean AP65 to be used |  |  | Complies with relevant material spec | PM | MDD | 5.2 - Roading | DESCRIPTION - Sub-base Material | TESTING &amp; INSPECTION METHODOLOGY - Clean AP65 to be used | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Complies with relevant material spec | RESPONSIBLE PERSON - PM | RECORD - MDD | RECORD - CMP
5.3 | Roading | Sub-base Compaction | Compact all fill materials to 95% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | SVY | Engineer inspection NDM Test Records | 5.3 - Roading | DESCRIPTION - Sub-base Compaction | TESTING &amp; INSPECTION METHODOLOGY - Compact all fill materials to 95% of MDD | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | RESPONSIBLE PERSON - SVY | RECORD - Engineer inspection NDM Test Records | 1.4 - General
5.4 | Roading | Basecourse Material | Clean AP40 to be used |  |  | Complies with relevant material spec | PM | MDD | 5.4 - Roading | DESCRIPTION - Basecourse Material | TESTING &amp; INSPECTION METHODOLOGY - Clean AP40 to be used | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Complies with relevant material spec | RESPONSIBLE PERSON - PM | RECORD - MDD | DESCRIPTION - Quality
5.5 | Roading | Basecourse Compaction | Compact all fill materials to 98% of MDD |  | Hold Point | Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | SVY | Engineer inspection NDM Test Records | 5.5 - Roading | DESCRIPTION - Basecourse Compaction | TESTING &amp; INSPECTION METHODOLOGY - Compact all fill materials to 98% of MDD | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS | RESPONSIBLE PERSON - SVY | RECORD - Engineer inspection NDM Test Records | TESTING & INSPECTION METHODOLOGY - QA to be recorded and submitted for review
5.6 | Roading | Benkleman Beam Test | Benkleman Beam testing after basecourse compaction and prior to sealing |  | Hold Point | 95% of test must be less than specified requirements | SUB | Test report | 5.6 - Roading | DESCRIPTION - Benkleman Beam Test | TESTING &amp; INSPECTION METHODOLOGY - Benkleman Beam testing after basecourse compaction and prior to sealing | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - 95% of test must be less than specified requirements | RESPONSIBLE PERSON - SUB | RECORD - Test report | SPECIFICATION REFERENCE -
5.7 | Roading | Pre seal Inspection | Engineer inspections prior to sealing |  | Hold Point | ensure a moziac basecourse finish has been achieved and there is no pooling/high levels of moisture in the surface. | ENG CENG | Engineers sign off | 5.7 - Roading | DESCRIPTION - Pre seal Inspection | TESTING &amp; INSPECTION METHODOLOGY - Engineer inspections prior to sealing | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - ensure a moziac basecourse finish has been achieved and there is no pooling/high levels of moisture in the surface. | RESPONSIBLE PERSON - ENG CENG | RECORD - Engineers sign off | HOLD POINTS -
6.1 | Kerb and Channel | Basecourse Compaction | NDM testing every 10m |  | Hold Point | All ND readings shall not be less than 2150kg/m3 | SVY | NDM Test Records | 6.1 - Kerb and Channel | DESCRIPTION - Basecourse Compaction | TESTING &amp; INSPECTION METHODOLOGY - NDM testing every 10m | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - All ND readings shall not be less than 2150kg/m3 | RESPONSIBLE PERSON - SVY | RECORD - NDM Test Records | ACCEPTANCE CRITERIA - QA system needs to store test requirements in a manner that can be reasonably found on-demand
6.2 | Kerb and Channel | Kerb installation | Check alignment, grade, Cutdowns, SW outlets prior to pouring |  |  | All checks completed prior to commencement of kerb pour | F | Kerb QA Checklist | 6.2 - Kerb and Channel | DESCRIPTION - Kerb installation | TESTING &amp; INSPECTION METHODOLOGY - Check alignment, grade, Cutdowns, SW outlets prior to pouring | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - All checks completed prior to commencement of kerb pour | RESPONSIBLE PERSON - F | RECORD - Kerb QA Checklist | RESPONSIBLE PERSON - PM
6.3 | Kerb and Channel | Kerb Core Strength | 28 Days after kerb pour, 1 kerb core is to be taken for each pour |  |  | 90mm dia concrete core 28 day strength is to be greater than 20Mpa | F | Test report | 6.3 - Kerb and Channel | DESCRIPTION - Kerb Core Strength | TESTING &amp; INSPECTION METHODOLOGY - 28 Days after kerb pour, 1 kerb core is to be taken for each pour | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - 90mm dia concrete core 28 day strength is to be greater than 20Mpa | RESPONSIBLE PERSON - F | RECORD - Test report | RECORD - ITP
7.1 | Services | Trench Base inspection | Inspect trench base prior to pipe installation |  |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F | Photos | 7.1 - Services | DESCRIPTION - Trench Base inspection | TESTING &amp; INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | RESPONSIBLE PERSON - F | RECORD - Photos | 1.5 - General
7.2 | Services | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 | Hold Point | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY | MDD NDM Test Record | 7.2 - Services | DESCRIPTION - Backfilling | TESTING &amp; INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals | SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32 | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | RESPONSIBLE PERSON - SVY | RECORD - MDD NDM Test Record | DESCRIPTION - Environmental Management
7.3 | Services | As-Builts | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY | As-built file | 7.3 - Services | DESCRIPTION - As-Builts | TESTING &amp; INSPECTION METHODOLOGY - As-built survey | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request | RESPONSIBLE PERSON - SVY | RECORD - As-built file | TESTING & INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works
8.1 | Water | Trench Base inspection | Inspect trench base prior to pipe installation |  |  | Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | F | Photos | 8.1 - Water | DESCRIPTION - Trench Base inspection | TESTING &amp; INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design | RESPONSIBLE PERSON - F | RECORD - Photos | SPECIFICATION REFERENCE -
8.2 | Water | Thrust Block Inspection (pre construction) | Prior to backfilling and following installation of thrust block framework and reinforcing. |  | Hold Point | Ensure Complaince with Local Council | CENG | Inspection Sign off | 8.2 - Water | DESCRIPTION - Thrust Block Inspection (pre construction) | TESTING &amp; INSPECTION METHODOLOGY - Prior to backfilling and following installation of thrust block framework and reinforcing. | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Ensure Complaince with Local Council | RESPONSIBLE PERSON - CENG | RECORD - Inspection Sign off | HOLD POINTS -
8.3 | Water | Backfilling | NDM testing each 400mm layer at 15m intervals | CCC CSS Part 1 Section 32 |  | Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | SVY | MDD NDM Test Record | 8.3 - Water | DESCRIPTION - Backfilling | TESTING &amp; INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals | SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32 | HOLD POINTS - | ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³ | RESPONSIBLE PERSON - SVY | RECORD - MDD NDM Test Record | ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer
8.4 | Water | Constant pressure (water loss) method | After bedding and haunching but prior to backfilling |  | Hold Point | Test is to comply with NZS25466.2:2002 Section 6.3.4.1 | SUB | Test Report | 8.4 - Water | DESCRIPTION - Constant pressure (water loss) method | TESTING &amp; INSPECTION METHODOLOGY - After bedding and haunching but prior to backfilling | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Test is to comply with NZS25466.2:2002 Section 6.3.4.1 | RESPONSIBLE PERSON - SUB | RECORD - Test Report | RESPONSIBLE PERSON - PM
8.5 | Water | Pre-construction weld testing | Prior to submain welding on site |  |  | EF welding equipment to pass weld testing criteria on specified materials prior to use on site | F | Test Report | 8.5 - Water | DESCRIPTION - Pre-construction weld testing | TESTING &amp; INSPECTION METHODOLOGY - Prior to submain welding on site | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - EF welding equipment to pass weld testing criteria on specified materials prior to use on site | RESPONSIBLE PERSON - F | RECORD - Test Report | RECORD - Contract Management Plan
8.6 | Water | Standover for any live water connections | Any Live water connections |  | Hold Point | Application for live water connection has been submitted well in advance before live connection date | CENG | MDD NDM Test Record | 8.6 - Water | DESCRIPTION - Standover for any live water connections | TESTING &amp; INSPECTION METHODOLOGY - Any Live water connections | SPECIFICATION REFERENCE - | HOLD POINTS - Hold Point | ACCEPTANCE CRITERIA - Application for live water connection has been submitted well in advance before live connection date | RESPONSIBLE PERSON - CENG | RECORD - MDD NDM Test Record | 1.6 - General
8.7 | Water | As-built | As-built survey |  |  | As-Builts to be supplied to the engineer prior to practical completion or on request | SVY | As-built file | 8.7 - Water | DESCRIPTION - As-built | TESTING &amp; INSPECTION METHODOLOGY - As-built survey | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request | RESPONSIBLE PERSON - SVY | RECORD - As-built file | DESCRIPTION - Programme
8.8 | Water | Serial Number of water meter | Every lot with a water meter installed |  |  | Serial number and lot recorded in a schedule | PM | Spreadsheet | 8.8 - Water | DESCRIPTION - Serial Number of water meter | TESTING &amp; INSPECTION METHODOLOGY - Every lot with a water meter installed | SPECIFICATION REFERENCE - | HOLD POINTS - | ACCEPTANCE CRITERIA - Serial number and lot recorded in a schedule | RESPONSIBLE PERSON - PM | RECORD - Spreadsheet | TESTING & INSPECTION METHODOLOGY - Construction Programme supplied to engineer for approval
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Approved Construction Programme
RESPONSIBLE PERSON - PM
RECORD - Construction Programme
1.7 - General
DESCRIPTION - Traffic Management
TESTING & INSPECTION METHODOLOGY - Submitted, when received back, form local authority
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - TMP submitted and accepted prior to work commencing within roadway
RESPONSIBLE PERSON - PM
RECORD - TMP
1.8 - General
DESCRIPTION - Archaeological and Culture
TESTING & INSPECTION METHODOLOGY - CMP submitted prior to commencement of on site works
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - CMP submitted before commencing work, to be approved by Engineer. Local iwi has been notified of intent to start work.
RESPONSIBLE PERSON - PM
RECORD - Contract Management Plan
1.9 - General
DESCRIPTION - As-Builts
TESTING & INSPECTION METHODOLOGY - As-Built drawings submitted that comply with KDC requirements
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
RESPONSIBLE PERSON - SVY
RECORD - As built file
2.1 - Earthworks
DESCRIPTION - Topsoil Strip
TESTING & INSPECTION METHODOLOGY - Strip Topsoil
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Photos and survey prior to further works
RESPONSIBLE PERSON - F
RECORD - Survey and photos
2.2 - Earthworks
DESCRIPTION - Cut to Fill
TESTING & INSPECTION METHODOLOGY - Contractor to identify and select suitable material for fill. Quality records made available to the engineer.
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Fill material approved by the Engineer
RESPONSIBLE PERSON - PM
RECORD - Visual inspections and photos
2.3 - Earthworks
DESCRIPTION - Compaction
TESTING & INSPECTION METHODOLOGY - Compact fill material to 95% of MDD
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC
RESPONSIBLE PERSON - SVY
RECORD - MDD NDM Test Records
2.4 - Earthworks
DESCRIPTION - Topsoil Respread
TESTING & INSPECTION METHODOLOGY - Respread topsoil to Design FL
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - • Final inspection • Survey
RESPONSIBLE PERSON - PM SVY
RECORD - Visual inspections and photos
3.1 - Drainage
DESCRIPTION - Trench Base inspection
TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
SPECIFICATION REFERENCE - CCC CSS Part 3 Section 6.4
HOLD POINTS -
ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
RESPONSIBLE PERSON - F
RECORD - Photos
3.2 - Drainage
DESCRIPTION - Backfilling
TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32
HOLD POINTS -
ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
RESPONSIBLE PERSON - SVY
RECORD - MDD NDM Test Record
3.3 - Drainage
DESCRIPTION - Corbels
TESTING & INSPECTION METHODOLOGY - Corbel inspections (Pre construction and Post construction)
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Ensure compliance with Local Council
RESPONSIBLE PERSON - F CENG
RECORD - Engineer inspection Drainage Checklist
3.4 - Drainage
DESCRIPTION - Pressure Testing
TESTING & INSPECTION METHODOLOGY - Air Pressuse testing (Pipes less the or equal to 450mm dia
SPECIFICATION REFERENCE - CCC CSS Part 3 Section 14
HOLD POINTS -
ACCEPTANCE CRITERIA - Pipe section is to be pumped to 10 kPa which is to be maintained for at least 3 minutes
RESPONSIBLE PERSON - F ENG
RECORD - Engineer inspection Drainage Checklist
3.5 - Drainage
DESCRIPTION - CCTV
TESTING & INSPECTION METHODOLOGY - CCTV inspection
SPECIFICATION REFERENCE - CCC CSS Part 3 Section 14
HOLD POINTS -
ACCEPTANCE CRITERIA - General pipe cleanliness and ensure there is no sudden changes in alignment, leaking or potential areas prone to leaking (open joins), pipe cracking or obstructions/debris
RESPONSIBLE PERSON - SUB
RECORD - Test report and footage
3.6 - Drainage
DESCRIPTION - Drainage Checklist
TESTING & INSPECTION METHODOLOGY - Drainage Checklist to be completed of every pipe line
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Completed by Foreman for every line installed, before starting a new line
RESPONSIBLE PERSON - F
RECORD - Drainage Checklist
3.7 - Drainage
DESCRIPTION - As-Builts
TESTING & INSPECTION METHODOLOGY - As-built survey
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
RESPONSIBLE PERSON - SVY
RECORD - As-built file
4.1 - Footpath
DESCRIPTION - Basecourse Material
TESTING & INSPECTION METHODOLOGY - Clean AP40 to be used
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Complies with relevant material spec
RESPONSIBLE PERSON - F
RECORD - Lab Report
4.2 - Footpath
DESCRIPTION - Basecourse Compaction
TESTING & INSPECTION METHODOLOGY - Clegg hammer testing at 15m intervals
SPECIFICATION REFERENCE - CCC CSS Part 6 Section 6.6
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - • CLEGG test shall exceed a CIV of 25 (Residential) • CLEGG test shall exceed a CIV of 35 (Commercial) • Engineer Inspection prior to seal/concrete
RESPONSIBLE PERSON - SVY
RECORD - Engineer inspection CLEGG Test Records
5.1 - Roading
DESCRIPTION - Subgrade
TESTING & INSPECTION METHODOLOGY - Subgrade inspection prior to placing sub-base
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - • There is little to no moisture on the surface, no soft spots or organic matter on and/or in the subgrade and depths are in accrodance with design.
RESPONSIBLE PERSON - ENG
RECORD - Engineer inspection and photos
5.2 - Roading
DESCRIPTION - Sub-base Material
TESTING & INSPECTION METHODOLOGY - Clean AP65 to be used
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Complies with relevant material spec
RESPONSIBLE PERSON - PM
RECORD - MDD
5.3 - Roading
DESCRIPTION - Sub-base Compaction
TESTING & INSPECTION METHODOLOGY - Compact all fill materials to 95% of MDD
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS
RESPONSIBLE PERSON - SVY
RECORD - Engineer inspection NDM Test Records
5.4 - Roading
DESCRIPTION - Basecourse Material
TESTING & INSPECTION METHODOLOGY - Clean AP40 to be used
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Complies with relevant material spec
RESPONSIBLE PERSON - PM
RECORD - MDD
5.5 - Roading
DESCRIPTION - Basecourse Compaction
TESTING & INSPECTION METHODOLOGY - Compact all fill materials to 98% of MDD
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Fill material approved by the Engineer and compacted to 95% of MDD and 2% off OMC. Test every 10m alternating between LHS and RHS
RESPONSIBLE PERSON - SVY
RECORD - Engineer inspection NDM Test Records
5.6 - Roading
DESCRIPTION - Benkleman Beam Test
TESTING & INSPECTION METHODOLOGY - Benkleman Beam testing after basecourse compaction and prior to sealing
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - 95% of test must be less than specified requirements
RESPONSIBLE PERSON - SUB
RECORD - Test report
5.7 - Roading
DESCRIPTION - Pre seal Inspection
TESTING & INSPECTION METHODOLOGY - Engineer inspections prior to sealing
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - ensure a moziac basecourse finish has been achieved and there is no pooling/high levels of moisture in the surface.
RESPONSIBLE PERSON - ENG CENG
RECORD - Engineers sign off
6.1 - Kerb and Channel
DESCRIPTION - Basecourse Compaction
TESTING & INSPECTION METHODOLOGY - NDM testing every 10m
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - All ND readings shall not be less than 2150kg/m3
RESPONSIBLE PERSON - SVY
RECORD - NDM Test Records
6.2 - Kerb and Channel
DESCRIPTION - Kerb installation
TESTING & INSPECTION METHODOLOGY - Check alignment, grade, Cutdowns, SW outlets prior to pouring
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - All checks completed prior to commencement of kerb pour
RESPONSIBLE PERSON - F
RECORD - Kerb QA Checklist
6.3 - Kerb and Channel
DESCRIPTION - Kerb Core Strength
TESTING & INSPECTION METHODOLOGY - 28 Days after kerb pour, 1 kerb core is to be taken for each pour
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - 90mm dia concrete core 28 day strength is to be greater than 20Mpa
RESPONSIBLE PERSON - F
RECORD - Test report
7.1 - Services
DESCRIPTION - Trench Base inspection
TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
RESPONSIBLE PERSON - F
RECORD - Photos
7.2 - Services
DESCRIPTION - Backfilling
TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
RESPONSIBLE PERSON - SVY
RECORD - MDD NDM Test Record
7.3 - Services
DESCRIPTION - As-Builts
TESTING & INSPECTION METHODOLOGY - As-built survey
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
RESPONSIBLE PERSON - SVY
RECORD - As-built file
8.1 - Water
DESCRIPTION - Trench Base inspection
TESTING & INSPECTION METHODOLOGY - Inspect trench base prior to pipe installation
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Ensure there are no soft spots or organic matter on and/or in the subgrade and depths are in accordance with design
RESPONSIBLE PERSON - F
RECORD - Photos
8.2 - Water
DESCRIPTION - Thrust Block Inspection (pre construction)
TESTING & INSPECTION METHODOLOGY - Prior to backfilling and following installation of thrust block framework and reinforcing.
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Ensure Complaince with Local Council
RESPONSIBLE PERSON - CENG
RECORD - Inspection Sign off
8.3 - Water
DESCRIPTION - Backfilling
TESTING & INSPECTION METHODOLOGY - NDM testing each 400mm layer at 15m intervals
SPECIFICATION REFERENCE - CCC CSS Part 1 Section 32
HOLD POINTS -
ACCEPTANCE CRITERIA - Approved backfill material only compacted to 95% of MDD at 15m intervals with a minimum dry density of 2150kg/m³
RESPONSIBLE PERSON - SVY
RECORD - MDD NDM Test Record
8.4 - Water
DESCRIPTION - Constant pressure (water loss) method
TESTING & INSPECTION METHODOLOGY - After bedding and haunching but prior to backfilling
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Test is to comply with NZS25466.2:2002 Section 6.3.4.1
RESPONSIBLE PERSON - SUB
RECORD - Test Report
8.5 - Water
DESCRIPTION - Pre-construction weld testing
TESTING & INSPECTION METHODOLOGY - Prior to submain welding on site
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - EF welding equipment to pass weld testing criteria on specified materials prior to use on site
RESPONSIBLE PERSON - F
RECORD - Test Report
8.6 - Water
DESCRIPTION - Standover for any live water connections
TESTING & INSPECTION METHODOLOGY - Any Live water connections
SPECIFICATION REFERENCE -
HOLD POINTS - Hold Point
ACCEPTANCE CRITERIA - Application for live water connection has been submitted well in advance before live connection date
RESPONSIBLE PERSON - CENG
RECORD - MDD NDM Test Record
8.7 - Water
DESCRIPTION - As-built
TESTING & INSPECTION METHODOLOGY - As-built survey
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - As-Builts to be supplied to the engineer prior to practical completion or on request
RESPONSIBLE PERSON - SVY
RECORD - As-built file
8.8 - Water
DESCRIPTION - Serial Number of water meter
TESTING & INSPECTION METHODOLOGY - Every lot with a water meter installed
SPECIFICATION REFERENCE -
HOLD POINTS -
ACCEPTANCE CRITERIA - Serial number and lot recorded in a schedule
RESPONSIBLE PERSON - PM
RECORD - Spreadsheet