## Cl_Earthworks
CHECKLIST
SJB & COPPER CREEK DIVERSION BUNDS
Project: |  | South Jimblebar Flood Bund & Diversion Channel |  |  |  |  | Customer: | BHP Iron Ore Pty Ltd
Date: |  |  |  | Lot No: |  |  |  | Drawing No.:
BUND
Chainage: |  |  |  | to:
HP |  |  | Description of Work |  |  |  | Respon. | Checked | Hold Point Released
HP | Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary. | [5 empty] | FM/Surv
Sign / Date
| Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund | [5 empty] | PE / FM
| Strip nominated 100mm - 300mm topsoil and placed in approved stockpile locations | [5 empty] | PE / FM |  | Sign / Date
| Remove unsuitable material encountered at finished sub grade level and replace with approved fill material. | [5 empty] | PE / FM
HP | Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill | [5 empty] | PE / FM |  | Sign / Date
| Rip, Condition and Compact existing 300mm subgrade material , to achieve ± 2% modified OMC | [5 empty] | PE / FM
| Subgrade compaction testing | [5 empty] | PE / FM
| Place and compact General and Clayey Fill Material as per bund details and typical sections Conditioned fill to be placed & compacted in 300mm lifts Compaction Testing undertaken | [5 empty] | PE / FM
HP | Arrange for BHP Representative to inspect and undertake visual proof roll with roller or loaded 15kL watercart | [5 empty] | PE / FM |  | Sign / Date
| For guide bund excavate and blace Geotextile Material Install Facing Class Rip Rap (500mm depth) to drawing levels | [5 empty] | PE / FM
| Earthworks have been trimmed and finished to within specified tolerances - Evenly grade changes between design levels and existing ground level - Smoothly finished surface with no ruts or disturbances - Trim to final levels as shown on contract drawings | [5 empty] | PE / FM
HP | Arrange with SO for final inspection of finished product | [5 empty] | PE / FM |  | Sign / Date
KEY: | SO = Superintendent Officer; FM = Foreman; PM = Project Manager; MMDD = Modified Maximum Dry Density
HP = Hold Point, beyond which work cannot proceed without release by SO; RP = Review Point, requiring an Inspection by the SO
Signed for Austral Construction Pty Ltd: | [7 empty] | Date :
South Jimblebar Flood Bund & Diversion Channel |  |  |  |  | Job No.: | 20053 |  |  | BHPBIO Purchase Order No. 4510048339
CL_SJB & COPPER CREEK DIVERSION BUNDS_20053 |  |  |  |  | Page 1 of 1 |  | Approved: HSEQ Mgr |  | Nov-20