## Sheet1
HP | Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary. | FM/Surv | Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary. | HP | RESPON.: FM/Surv | Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary.
HP
| Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund | PE / FM | Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund | 0 | RESPON.: PE / FM | RESPON.: FM/Surv
| Strip nominated 100mm - 300mm topsoil and placed in approved stockpile locations | PE / FM | Strip nominated 100mm - 300mm topsoil and placed in approved stockpile locations | 0 | RESPON.: PE / FM | Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund
| Remove unsuitable material encountered at finished sub grade level and replace with approved fill material. | PE / FM | Remove unsuitable material encountered at finished sub grade level and replace with approved fill material. | 0 | RESPON.: PE / FM | 0
HP | Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill | PE / FM | Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill | HP | RESPON.: PE / FM | RESPON.: PE / FM
| Rip, Condition and Compact existing 300mm subgrade material , to achieve ± 2% modified OMC | PE / FM | Rip, Condition and Compact existing 300mm subgrade material , to achieve ± 2% modified OMC | 0 | RESPON.: PE / FM | Strip nominated 100mm - 300mm topsoil and placed in approved stockpile locations
| Subgrade compaction testing | PE / FM | Subgrade compaction testing | 0 | RESPON.: PE / FM | 0
| Place and compact General and Clayey Fill Material as per bund details and typical sections Conditioned fill to be placed CHAR(AMP) compacted in 300mm lifts Compaction Testing undertaken | PE / FM | Place and compact General and Clayey Fill Material as per bund details and typical sections Conditioned fill to be placed CHAR(AMP) compacted in 300mm lifts Compaction Testing undertaken | 0 | RESPON.: PE / FM | RESPON.: PE / FM
HP | Arrange for BHP Representative to inspect and undertake visual proof roll with roller or loaded 15kL watercart | PE / FM | Arrange for BHP Representative to inspect and undertake visual proof roll with roller or loaded 15kL watercart | HP | RESPON.: PE / FM | Remove unsuitable material encountered at finished sub grade level and replace with approved fill material.
| For guide bund excavate and blace Geotextile Material Install Facing Class Rip Rap (500mm depth) to drawing levels | PE / FM | For guide bund excavate and blace Geotextile Material Install Facing Class Rip Rap (500mm depth) to drawing levels | 0 | RESPON.: PE / FM | 0
| Earthworks have been trimmed and finished to within specified tolerances - Evenly grade changes between design levels and existing ground level - Smoothly finished surface with no ruts or disturbances - Trim to final levels as shown on contract drawings | PE / FM | Earthworks have been trimmed and finished to within specified tolerances - Evenly grade changes between design levels and existing ground level - Smoothly finished surface with no ruts or disturbances - Trim to final levels as shown on contract drawings | 0 | RESPON.: PE / FM | RESPON.: PE / FM
HP | Arrange with SO for final inspection of finished product | PE / FM | Arrange with SO for final inspection of finished product | HP | RESPON.: PE / FM | Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill
HP
RESPON.: PE / FM
Rip, Condition and Compact existing 300mm subgrade material , to achieve ± 2% modified OMC
0
RESPON.: PE / FM
Subgrade compaction testing
0
RESPON.: PE / FM
Place and compact General and Clayey Fill Material as per bund details and typical sections Conditioned fill to be placed CHAR(AMP) compacted in 300mm lifts Compaction Testing undertaken
0
RESPON.: PE / FM
Arrange for BHP Representative to inspect and undertake visual proof roll with roller or loaded 15kL watercart
HP
RESPON.: PE / FM
For guide bund excavate and blace Geotextile Material Install Facing Class Rip Rap (500mm depth) to drawing levels
0
RESPON.: PE / FM
Earthworks have been trimmed and finished to within specified tolerances - Evenly grade changes between design levels and existing ground level - Smoothly finished surface with no ruts or disturbances - Trim to final levels as shown on contract drawings
0
RESPON.: PE / FM
Arrange with SO for final inspection of finished product
HP
RESPON.: PE / FM