## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-002 - Departure Road Earthworks | itp |  |  |  |  | ITP-002 - Departure Road Earthworks Rev2
section | Departure Road Earthworks
checkpoint | 1 - Prior mobilisation laydown areas to be indentified and approved by BHP, complete Surface Mobile Equipment Compliance Inspection for approval by the BHP responsible person. Develope Traffic Management Plans (TMP) and associated site specific Traffic Control Plans (TCP) shall be submited to the Company for approval atleast (4) weeks prior to commencement. Implement temporary and permanent protection of existing infrastructure.
label | RP/HP: HP
label | ACCEPTANCE CRITERIA: Approval of laydown area, SMECI, TMP, and TCP
label | FREQUENCY: Prior to commencing
holdpoint | HOLD POINT
checkpoint | 2 - Ensure sufficient survey control is in place prior to commencing earthwork operation; Survey setout and pickup for construction to be performed to obtain PEAHR, Vegetation, Clearing Permit, and Excavation Permit from BHP to start the excavation/ clearing works. Survey shall use GDA94 MGA Zone 50
label | APPLICABLE STANDARD: STD-PLN-SUR-001 / SPEC-000-C-00105 Sect. 4.2, Section 5.2 & 7.1 SPEC-000-C-00105 Sect. 5.3.1
label | ACCEPTANCE CRITERIA: Survey set-out satisfactory; PEAHR
label | ○ Vegetation Clearing Permit
label | ○ Excavation permit
label | ○ Clear & grub to 300mm depth
label | ○ 3m outside limits of earthworks
label | FREQUENCY: Prior to commencing
checkpoint | 3 - Clear and grub ground surfaces of all stumps and roots;
label | RP/HP: HP
label | APPLICABLE STANDARD: STD-PLN-SUR-001 / SPEC-000-C-00105 Sect. 4.2, Section 5.2 & 7.1 SPEC-000-C-00105 Sect. 5.3.1
label | ACCEPTANCE CRITERIA: Survey set-out satisfactory; PEAHR
label | ○ Vegetation Clearing Permit
label | ○ Excavation permit
label | ○ Clear & grub to 300mm depth
label | ○ 3m outside limits of earthworks
label | FREQUENCY: Before clearing
holdpoint | HOLD POINT
checkpoint | 4 - Strip topsoil and placed in approved stockpile locations
label | RP/HP: HP
label | APPLICABLE STANDARD: Refer Dwgs SPEC-000-C-00105 Sect. 6.2.1
label | ACCEPTANCE CRITERIA: Minimum stripping depth 200mm to a stable base
label | FREQUENCY: Prior to excavation
holdpoint | HOLD POINT
checkpoint | 5 - Any pot holing, test pitting and cable locating required must be carried out in accordance with the approved Excavation Permit in order to verify the location of underground services against the CSMs provided.
label | ACCEPTANCE CRITERIA: Verifying all the points/ locations provided in CSM
label | FREQUENCY: Prior to excavation
checkpoint | 6 - Treatment of buried services to be as per WAIO excavation and penetration procedure. CEP ensures excavations comply with all applicable: Acts, Regulations, WAIO Standards, and SPEC-000-C-00105 WAIO Earthworks and IFC documentation relevant to the area to be excavated.
label | The permit shall be maintained at the work location by the Permit Holder.
label | The BHP Supervisor shall supervise the task.
label | APPLICABLE STANDARD: WAIO Excavation and Penetration Procedure SPR-HIS-SAF-001
label | ACCEPTANCE CRITERIA: Prior to work commencing a task based risk assessment (TBRA) to be completed, changes before or during the work reassess the risk and re-validate or update critical controls. If the location boundary or excavation method requires revision, the Controller Excavation Permit (CEPs) shall approve and document the change.
label | FREQUENCY: Prior to excavation and during excavation
checkpoint | 7 - Fill material to comply with BHP specifications and/or sourced from site locations (Borrow Pit BA2)
label | – Common Fill > Cut to Fill material on site
label | – Subgrade Material > Borrow Pit BA2
label | – Basecourse > Imported
label | RP/HP: HP
label | APPLICABLE STANDARD: 311010-00413-MEM-001 Rev1
label | ○ SPEC-000-C-00105 Sect. 10.2
label | ○ 311010-00413-MEM-001 Rev1
label | ○ SPEC-000-C-00116 Sect. 4.2.1
label | ○ SPEC-000-C-00116 Sect. 4.2.2
label | ACCEPTANCE CRITERIA: Inorganic material, LL < 35%, meets grading curve
label | ○ meets grading curve, LL < 25%, PL < 20%, PI < 9%, LS< 3%, CBR > 45%
label | FREQUENCY: Before placing materials
holdpoint | HOLD POINT
checkpoint | 8 - Excavate materials to the required lines and levels as per the construction drawings.
label | APPLICABLE STANDARD: SPEC-000-C-00105 Sect. 7.2 IFC Drawings
label | ACCEPTANCE CRITERIA: Lines and Levels as per drawings
label | FREQUENCY: During Excavation
checkpoint | 9 - Undertake a proof roll test using a Smooth Drum roller or similar with no visual heaving
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105 Sect. 10.3.1.2
label | ACCEPTANCE CRITERIA: Particle size distribution >75%
label | ○ CBR >5%
label | ○ 1 test per 2500m3
label | ○ DCP test to correlated >92% MMDD
label | FREQUENCY: Prior to placing fill
holdpoint | HOLD POINT
checkpoint | 10 - Testing of all earthworks material, Imported material and general fill must comply with the details in the design drawings and standards specified, and be approved for use by the company representative.
label | APPLICABLE STANDARD: SPEC-000-C-00105 and DESC-000-C-00002 311010-00413-MEM-001 Rev1
label | ACCEPTANCE CRITERIA: Complaince with the specifications or Approval by company's representative
label | FREQUENCY: Prior to placing fill
checkpoint | 11 - Place and compact general fill material to lines and level required as per construction drawings. Fill to be placed and compacted in layers of greater than 200mm and less than 300mm
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105 Sect. 12.3
label | ACCEPTANCE CRITERIA: Loose layer 200mm to 300mm
label | ○ 95% MMDD General Fill
label | ○ ± 2% Moisture Content
label | ○ 1 test per 1000m3
label | FREQUENCY: During fill placement
holdpoint | HOLD POINT
checkpoint | 12 - Import, place and compact basecoarse material in a single 200mm layer to the lines and levels as shown on the construction drawings
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00116 Sect. 8
label | ACCEPTANCE CRITERIA: 98% MMDD Subgrade
label | ○ ± 1% Moisture Content
label | ○ 1 test per 100 lineal metres
label | FREQUENCY: During basecourse
holdpoint | HOLD POINT
checkpoint | 13 - If where the ballast is removed and the SBC is more than 400mm below the designed RL of the underside of the sleeper. Then treatment to be applied as per DESC-000-C-00001 or as directed by company's representative,
label | RP/HP: HP
label | APPLICABLE STANDARD: DESC-000-C-00001
label | ACCEPTANCE CRITERIA: RL readings after remediation works or Approval by company's representative
label | FREQUENCY: During preparation of formation
holdpoint | HOLD POINT
checkpoint | 14 - Ballast Depth transitions to be applied to the ends of ballast replacement works.
label | APPLICABLE STANDARD: Track Maintenance Code of Practice - 0002664, section 2.5.1.2
label | ACCEPTANCE CRITERIA: Ballast depth transitions, or as directed by company representative
label | FREQUENCY: After ballast replacment works.
checkpoint | 15 - Trim and finish tops of basecourse to specified tolerances and undertake an As-built survey
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105 Sect 13.4
label | ACCEPTANCE CRITERIA: Thickness minimum
label | ○ Width -0mm to +100mm
label | ○ Surface Level -10mm, +20mm
label | FREQUENCY: After placing basecourse
holdpoint | HOLD POINT
checkpoint | 16 - Final inspection undertaken by client representative and approval of all work
label | RP/HP: HP
label | FREQUENCY: At completion
holdpoint | HOLD POINT
checkpoint | Final Inspection
holdpoint | Signed by Austral Construction / BHP Representative
checklist | SJB & Copper Creek Diversion Bunds Checklist | [5 empty] | SJB & Copper Creek Diversion Bunds Checklist
section | SJB & Copper Creek Diversion Bunds
checkpoint | Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary.
label | HP
label | RESPON.: FM/Surv
holdpoint | Hold Point Released
checkpoint | Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund
label | RESPON.: PE / FM
checkpoint | Strip nominated 100mm - 300mm topsoil and placed in approved stockpile locations
label | RESPON.: PE / FM
checkpoint | Remove unsuitable material encountered at finished sub grade level and replace with approved fill material.
label | RESPON.: PE / FM
checkpoint | Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill.
label | HP
label | RESPON.: PE / FM
holdpoint | Hold Point Released
checkpoint | Rip, Condition and Compact existing 300mm subgrade material , to achieve ± 2% modified OMC
label | RESPON.: PE / FM
checkpoint | Subgrade compaction testing
label | RESPON.: PE / FM
checkpoint | Place and compact General and Clayey Fill Material as per bund details and typical sections. Conditioned fill to be placed & compacted in 300mm lifts. Compaction Testing undertaken.
label | RESPON.: PE / FM
checkpoint | Arrange for BHP Representative to inspect and undertake visual proof roll with roller or loaded 15kL watercart
label | HP
label | RESPON.: PE / FM
holdpoint | Hold Point Released
checkpoint | For guide bund excavate and blace Geotextile Material. Install Facing Class Rip Rap (500mm depth) to drawing levels.
label | RESPON.: PE / FM
checkpoint | Earthworks have been trimmed and finished to within specified tolerances
label | – Evenly grade changes between design levels and existing ground level
label | – Smoothly finished surface with no ruts or disturbances
label | – Trim to final levels as shown on contract drawings
label | RESPON.: PE / FM
checkpoint | Arrange with SO for final inspection of finished product
label | HP
label | RESPON.: PE / FM
holdpoint | Hold Point Released
checkpoint | Signed for Austral Construction Pty Ltd:
holdpoint | Signoff
checklist | ITP - SJB Creek Diversion Bund | itp |  |  |  |  | ITP - SJB Creek Diversion Bund Rev0
section | SJB & Copper Creek Diversion Bunds
checkpoint | 1 - Ensure that sufficient survey information is available for set out. Establish the correct line and level for excavation and earthworks. Survey pegs to include PEAHR and Construction Boundary. Excavated Material (from Drain Diversion) as Common Fill material for Diversion Bund – approved by BHP
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105/16 Section 5.2 & 5.3
label | ○ SOW-960-C-12039/2 Section 3.3.6
label | ○ Drawings
label | – 960-C-13667
label | – 960-C-13668
label | – 960-C-13669
label | ACCEPTANCE CRITERIA: BHP excavation permit Survey Data provided by BHP
label | FREQUENCY: Prior to commencing
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: FM/Surv
holdpoint | HOLD POINT
checkpoint | 2 - Clearing, grubbing and stripping of all vegetation, stumps and roots along the footprint of the Creek Diversion Bund. Where topsoil material identified (between 100mm and 300mm depth), strip, load and haul to nominated stockpile areas, no higher than 2.0m.
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105/16 Section 5.2 & 5.3
label | ○ SOW-960-C-12039/2 Section 3.3.6
label | ○ Drawings
label | – 960-C-13667
label | – 960-C-13668
label | – 960-C-13669
label | ACCEPTANCE CRITERIA: Clear and grub to min 300mm depth below natural surface
label | ○ Where stumps/roots are larger than 200mm girth, Clear and grub 600mm
label | ○ Clear between 100mm - 300mm topsoil depth
label | FREQUENCY: Prior to Excavation
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
holdpoint | HOLD POINT
checkpoint | 3 - Remove unsuitable material encountered at finished sub grade level and replace with approved fill material. Company representative and Engineer to inspect the bottom of the excavation and approve the placement of fill material. Unsuitable foundation to be boxed out 0.3m minimum and replaced with A4 select fill
label | RP/HP: HP
label | APPLICABLE STANDARD: SOW-960-C-12039/2 Section 3.3.7
label | ACCEPTANCE CRITERIA: Visual Inspection Proof Roll
label | FREQUENCY: Prior to fill placement
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
holdpoint | HOLD POINT
checkpoint | 4 - The upper 300 mm below the subgrade shall be scarified by tyning, adding water asnecessary, to achieve ± 2% modified OMC and compacted over every point on the surface, operating in the dynamic mode unless instructed otherwise by the Company Representative. A minimum of 95% MMDD shall be achieved with no visual heaving after rolling.
label | RP/HP: HP
label | APPLICABLE STANDARD: SPEC-000-C-00105/16 Section 10.6
label | ○ SOW-960-C-12039/2 Section 3.3.7
label | ACCEPTANCE CRITERIA: Rip, Condition and Compact existing subgrade
label | ○ Proof Roll
label | ○ Compaction to be 95% MMDD and +/- 2% OMC
label | FREQUENCY: Prior to fill placement
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
holdpoint | HOLD POINT
checkpoint | 5 - Ensure that the material from BHP Billiton's material stockpiles comply with the Specification or BHP approved:
label | – Encapsulated Material (Middle of Bund):
label | ○ BHP Approved Fill Material generally as per Section 11.2.13.2 SPEC 000-C- 00105, be non-dispersive (Emerson class number 5 or higher), have permeability k<10m/d (may be deemed to comply if a minimum of 10% fines is present) and is not gap graded
label | – A4 Clayey Gravel (Outside of Bund):
label | ○ Blending of designated borrow material (A4, gap graded) with Sandy CLAY (CL) material sourced from separate borrow is required to improve the grading. Indicatively a ratio of 0.2 Sandy CLAY to 0.8 GRAVEL - subject to trial Maximum particle size shall remain within specified limits;
label | APPLICABLE STANDARD: SPEC-000-C-00105/16 SOW-960-C-12039/2 Section 3.3.7
label | Project Drawings
label | ○ 960-C-13666_0
label | ○ 960-C-13667_0
label | ○ 960-C-13668_0
label | ○ 960-C-13669_0
label | ○ 960-C-13672_0
label | ○ 960-C-13674_0
label | ○ 960-C-13680_0
label | ACCEPTANCE CRITERIA: Material testing to meet Scope and Specification, Approval by BHP for use
label | FREQUENCY: Prior to placement of fill
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
checkpoint | 6 - Place and compact approved fill material along length of Bund for Drain Detail Type 1, Type 2 and Type 3. Material to be type C1 General Fill or A4 Select Fill as directed by Company Representative.
label | Compaction process:
label | – Moisture condition, place and compact in 300mm lifts with 12-19T padfoot roller with vibrating mode up to design levels specified in Drawings
label | – Proof Roll & Compaction Testing
label | RP/HP: HP
label | APPLICABLE STANDARD: Project Drawings
label | ○ 960-C-13667_0
label | ○ 960-C-13668_0
label | ○ 960-C-13669_0
label | ○ 960-C-13672_0
label | ○ 960-C-13674_0
label | ○ 960-C-13680_0
label | ACCEPTANCE CRITERIA: Place and Compact moisture conditioned type C1 General Fill or A4 Select Fill
label | ○ Proof Roll
label | ○ Compaction to be 95% MMDD and +/- 2% OMC
label | FREQUENCY: Prior to final trim
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
holdpoint | HOLD POINT
checkpoint | 7 - For Guide Bund Install Bidim A34 geofabric in areas where overexcavated for placement of Rip Rap rock. Install Riprap rock protection on the Inlet and Outlet apron as shown on construction drawing.
label | APPLICABLE STANDARD: Project Drawings
label | ○ 960-C-13667_0
label | ○ 960-C-13668_0
label | ○ 960-C-13669_0
label | ○ 960-C-13672_0
label | ACCEPTANCE CRITERIA: Riprap placed as shown on Dwg Geotextile type Bidim A34 below riprap
label | FREQUENCY: On completion of excavation for Rip Rap
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
checkpoint | 8 - Trim and finish tops of earthworks to specified tolerances
label | – Evenly grade changes between design levels and existing ground level
label | – Smoothly finished surface with no ruts or disturbances
label | – Trim to final levels as shown on contract drawings
label | RP/HP: HP
label | APPLICABLE STANDARD: C-00105 Sect 16 SOW-960-C-12039/2 Project Drawings
label | ACCEPTANCE CRITERIA: RL top of earthworks = + 25mm Various cross sections
label | FREQUENCY: After excavation, placement of fill and Rip Rap
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM
holdpoint | HOLD POINT
checkpoint | 9 - Carry out an as-built survey and submit data to BHP
label | APPLICABLE STANDARD: SPEC-000-C-00105/16 Section 11.4
label | ACCEPTANCE CRITERIA: Within specified tolerances
label | FREQUENCY: On Completion
label | RECORDS: CL_SJB Diversion Bund
label | ACTION RESPON.: PE / FM