## Dig-out
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: Pavement Repair Dig-out |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.0 Pavement Repair (Digout)
1.01 | Scala | Determine the depth of excavation | M | For each site where digout is required | Measure / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.02 | Excavation | Excavate existing pavement from finish road level (FRL) and depth will vary from scala result | M | For each site where digout is required | Measure / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.03 | Geogrid | Geogrid maybe installed to reduce the digout depth | M | For each site where digout is required | Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.04 | Backfilling Thickness | Layer thickness is not to exceed 100mm (compacted), cloth will be installed prior to backfilling and AP40 to be used. | M | Varies from the depth of excavation | Measure / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.05 | Compaction Requirements | Clegg Impact Value using | H | Every 100mm depth compacted | Measure | Clegg Impact Value (CIV) ≥ 30 if NDM is not available on site | Carried out by competant operator, record results on digout Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.06 | Finished Level | Ensure the finished level of subgrade is flush with existing surfacing and there are no depressions that could hold water. | M | For each site where digout is required | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.