## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Dig-out | itp |  |  |  |  | ITP - Dig-out Rev 0
section | 1.0 Pavement Repair (Digout)
checkpoint | 1.01 - Scala
label | Detail of Activity / Test - Determine the depth of excavation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.02 - Excavation
label | Detail of Activity / Test - Excavate existing pavement from finish road level (FRL) and depth will vary from scala result
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.03 - Geogrid
label | Detail of Activity / Test - Geogrid maybe installed to reduce the digout depth
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
label | Inspection / Test method - Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.04 - Backfilling Thickness
label | Detail of Activity / Test - Layer thickness is not to exceed 100mm (compacted), cloth will be installed prior to backfilling and AP40 to be used.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Varies from the depth of excavation
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.05 - Compaction Requirements
label | Detail of Activity / Test - Clegg Impact Value using
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 100mm depth compacted
label | Inspection / Test method - Measure
label | Acceptance Criteria - Clegg Impact Value (CIV) ≥ 30 if NDM is not available on site
label | Record documents (QCP - Quality Control Portal) - Carried out by competant operator, record results on digout Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - Finished Level
label | Detail of Activity / Test - Ensure the finished level of subgrade is flush with existing surfacing and there are no depressions that could hold water.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where digout is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Project Specific Notes / Instructions -
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature