## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-209-STR-SSO-SUP Widening | itp |  |  |  |  | ITP-209-STR-SSO-SUP Widening Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-209-STR-SSO-SUP Widening
label | ITP Description: SSO-SUP Widening
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 23/10/2024
label | ITP created by: Dimitri Santoreneos
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads Section 602 June 2007
label | 1.2 Non Dependent
label | Reference: VicRoads Section 610 February 2020
label | 1.3 Non Dependent
label | Reference: VicRoads Section 611 November 2018
label | 1.4 Non Dependent
label | Reference: VicRoads Section 614 June 2017
label | 1.5 Non Dependent
label | Reference: AS3810.1 2018
section | Preliminaries - Materials
checkpoint | 2.1 Concrete Mix
label | REFERENCE: IFC Drawings VicRoads: Cl 610.07 Table 610.071
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | REFERENCE: VicRoads: Cl 611.05 (a)
label | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once for each supplier, 14 days of award of contract
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Bar Chairs/Aspros Certification
label | REFERENCE: VicRoads: Cl 610.26 (a)
label | ACCEPTANCE CRITERIA: Plastic Bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing (chloride ion and sulphate ion content) in accordance with AS 1012.20.1 on a 12 monthly basis or earlier if the mix design changes to demonstrate compliance with the requirements of clause 610.07(k) for soluble salts.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Evaporative Retardant
label | REFERENCE: VicRoads: Cl 610.17 (f)
label | ACCEPTANCE CRITERIA: Details of evaporative retardant and application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Curing Compound
label | REFERENCE: VicRoads: Cl 610.23 (d)
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 (non-volatile content and density in accordance with Cl 3.2, and for viscosity in accordance with Cl 3.1.5). Tests shall be vaild for not more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | REFERENCE: VicRoads: Cl 610.18 (a) (i)
label | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | REFERENCE: VicRoads: Cl 610.18 (a) (v)
label | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | REFERENCE: VicRoads: Cl 610.18 (a) (iv)
label | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | ○ Minutes of this meeting to be submitted to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | REFERENCE: VicRoads: Cl 610.17 (a)
label | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | REFERENCE: VicRoads: Cl 610.23 (a)
label | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 Concrete Drilling Procedure
label | REFERENCE: VicRoads: Cl 610.46
label | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 Temperature difference measuring-Calibration & Cover meter-calibration
label | REFERENCE: MRPA Quality Management Plan VicRoads: Cl 610.34
label | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
label | ○ Attach: Calibration certificate
label | METHOD: Document review
label | FREQUENCY: Where applicable
label | CATEGORY: HP*
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | METHOD: Document Review
label | FREQUENCY: Prior to starting Works and at regular intervals
label | CATEGORY: HP*
label | RESPONSIBILITY: All
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Survey Set-out
label | REFERENCE: IFC Drawings VicRoads: Cl 610.47 (a) Table 610.472
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
label | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Excavation support
label | REFERENCE: VicRoads: Cl 602.02
label | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
textbox | Enter: Teambinder Approval number
label | METHOD: Document Review
label | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | CATEGORY: WP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.4 Excavation Inspection
label | REFERENCE: VicRoads: Cl 602.03
label | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | METHOD: Visual
label | FREQUENCY: Where applicable, prior to placing blinding concrete
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 5.1 Formwork Design and Construction
label | REFERENCE: IFC Drawings VicRoads: Cl 614.04, Cl 614.05, Cl 614.06
label | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | METHOD: Document Review, Visual, Measure
label | FREQUENCY: Each type of element
label | CATEGORY: IP
label | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | REFERENCE: VicRoads: Cl 614.08 Table 614.041
label | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed and accepted by the Nominated Authority.
label | ○ The submission of formwork documentation and certification for the various concrete members shall be in accordance with the requirements of Table 614.041, For concrete members specified in (b), (c) & (d).
label | ○ Attach: Attachment A (as per Clause 614.04) and Attachment B (as per clause 614.08)
label | METHOD: Document Review, Visual, Measure
label | FREQUENCY: Each element (where greater than 2m)
label | CATEGORY: HP
label | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | REFERENCE: VicRoads: Cl 614.08 Table 614.041
label | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed and accepted by the Nominated Authority.
label | ○ The submission of formwork documentation and certification for the various concrete members shall be in accordance with the requirements of Table 614.041, for concrete members specified in (a).
label | ○ Attach: Attachment C (as per clause 614.08)
label | METHOD: Document Review, Visual, Measure
label | FREQUENCY: Each element (where 2m or less)
label | CATEGORY: HP
label | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 Pre-pour Survey
label | REFERENCE: VicRoads: Cl 610.47 (a) Table 610.472
label | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | ○ Erected formwork within the tolerances as per the table 610.472 as applicable to the element.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: HP*
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Reinforcement Placement
label | REFERENCE: IFC Drawings VicRoads: Cl 611.06, Cl 611.09, Cl 611.10, Cl 611.11, Cl 611.12
label | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location. Projecting steel reinforcement in newly poured concrete shall remain undisturbed for a minimum period of 24 hours
label | ○ Splice lengths achieve the minimum length and are in contact for this length, and the specified cover shall be maintained
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Cast-in Items
label | REFERENCE: IFC Drawings VicRoads: Cl 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
label | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | METHOD: Measure, Visual
label | FREQUENCY: Where applicable, each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Thermal Differential Monitoring
label | REFERENCE: VicRoads: Cl 610.22
label | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | ○ Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | METHOD: Measure
label | FREQUENCY: Where applicable, each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Pre-pour Inspection
label | REFERENCE: IFC Drawings VicRoads: Cl 610.18 (a) (ii) & (iii)
label | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the forms.
label | ○ ATTACH: Pre-Pour Checklist
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 Weather Conditions & Evaporation Limits
label | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Measure, Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.10 Concrete Testing - Sampling Frequency
label | REFERENCE: Site Sampling & Testing Procedure VicRoads: Cl 610.16 (b)
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | – For each additional 50m³ and additional sample shall be taken.
label | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | – Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | – Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.11 Concrete Testing - Slump
label | REFERENCE: VicRoads: Cl 610.16 (c) Table 610.162
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | – Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
label | REFERENCE: VicRoads: Cl 610.13 (b) Table 610.131
label | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | ○ T500 time (measure of viscosity) = 2 seconds to 5 seconds (to reach a spread of 500mm). Final spread shall not exceed 800mm in diameter
label | ○ Passability = ≤10mm (aggregate height differential)
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Test
label | FREQUENCY: Each sample of Self-compacting Concrete
label | CATEGORY: IP
label | RESPONSIBILITY: Concrete Tester
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.13 Supply & Discharge Rates
label | REFERENCE: VicRoads: Cl 610.13 (a) & (f), Cl 610.18 (a)
label | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | ○ No water is to be added once discharge commences.
label | ○ Maximum time between batching trucks is 25 minutes.
label | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | ○ Record: Required information on the Concrete Pour Record.
label | METHOD: Measure, Visual
label | FREQUENCY: Each load
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.14 Placement & Compaction
label | REFERENCE: Placement & Compaction Work Procedure VicRoads: Cl 610.18 (a), (b) & (d)(i)
label | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Concrete is not dropped freely from a height exceeding 2m.
label | ○ Concrete is not moved horizontally by use of vibrators.
label | ○ Adequate compaction is ensured
label | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | ○ Concrete layers are not more than 350mm
label | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | ○ Record: Required information on the Concrete Pour Record.
label | ○ Attach: Concrete Pour Record and Concrete delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each load
label | CATEGORY: SP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.15 Surface Finishes
label | REFERENCE: IFC Drawings VicRoads: Cl 610.20, Cl 610.31
label | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.16 Curing after formwork removal
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Thip ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Thermal Differential Monitoring
label | REFERENCE: VicRoads: Cl 610.22
label | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | ○ Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | ○ Attach: Thermal Monitoring Report
label | METHOD: Document Review
label | FREQUENCY: Where applicable, each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | METHOD: Document Review
label | FREQUENCY: Where applicable, each element
label | CATEGORY: IP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 Surface Inspection - Cracks
label | REFERENCE: VicRoads: Cl 610.24
label | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | METHOD: Visual, Measure
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Surface Inspection - Surface Finish
label | REFERENCE: IFC Drawings VicRoads: Cl 610.31 (a) - (n), Cl 610.32
label | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | METHOD: Visual
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.5 Measurement of Concrete Cover
label | REFERENCE: 610.34
label | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | ○ Minimum 10 no. measurements recorded in each area.
label | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | ○ Attach: Covermeter Check Record
label | METHOD: Measure
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | REFERENCE: Early Loading and Trafficking of Decks and Approach Slabs Procedure VicRoads: Cl 610.35
label | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | ○ Attach: Concrete Test Results or Maturity Test Results
label | METHOD: Document Review
label | FREQUENCY: Where applicable, each substructure element
label | CATEGORY: SP
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.7 Compressive Strength Test Results
label | REFERENCE: IFC Drawings VicRoads: Table 610.05.051 Cl 610.16 (g)
label | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | METHOD: Document Review
label | FREQUENCY: Each cylinder
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.8 As-built Survey
label | REFERENCE: IFC Drawings VicRoads: Cl 610.47 Table 610.472
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | ○ Attach: Survey As-builts / Survey Report
label | METHOD: Document Review
label | FREQUENCY: Each element
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-210-CIV-SSO-Kerb & Channel (Supply and Install) | itp |  |  |  |  | ITP-210-CIV-SSO-Kerb & Channel (Supply and Install) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-210-CIV-SSO-Kerb and Channel (Supply and Install)
label | ITP Description: SSO-Kerb and Channel (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 23/10/2024
label | ITP created by: Dimitri Santoreneos
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads Section: 703 (August 2021), VR SD2001, VR SD2102, AS 2876, AS1379
section | Preliminary - Materials
checkpoint | 2.2 Mix design
label | REFERENCE: SD2001, AS1379 VicRoads: Cl 703.05 (a)(b), Cl 703.06, Cl 703.07
label | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
label | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | ○ Attach: TeamBinder Material Approval No.
label | METHOD: Verify, Document Review
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Bedding Material
label | REFERENCE: IFC Drawings VicRoads: Cl 703.21
label | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | ○ Attach: TeamBinder Material Approval No.
label | METHOD: Verify, Document Review
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Curing Compound
label | REFERENCE: VicRoads: Cl 703.10
label | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
label | ○ Attach: TeamBinder Material Approval No.
label | METHOD: Verify
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminary - Documentation
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | – All drawings are the latest version (as per TeamBinder)
label | METHOD: Visual inspection
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Setting out
label | REFERENCE: IFC Drawings VicRoads: Cl 703.17
label | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | ○ Attach: Map-Marked up drawing to indicate the location of the Lot
label | METHOD: Verify
label | FREQUENCY: Prior to start
label | CATEGORY: HP
label | RESPONSIBILITY: Surveyor/Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 Temporary drainage provisions
label | REFERENCE: CEMP VicRoads: Cl 703.18
label | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | ○ Attach: relevant written approval from relevant stakeholder.
label | METHOD: Visual inspection, Document Review
label | FREQUENCY: Prior to start (where required)
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Bedding
label | REFERENCE: VicRoads: Cl 703.21
label | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.2 Formwork
label | REFERENCE: VicRoads: Cl 703.12 AS 3610
label | ACCEPTANCE CRITERIA: The materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610.
label | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.3 Pre Pour Check
label | REFERENCE: VicRoads: Cl 703.09, Cl 703.21, Cl 610.17 (a)(b)(c )(d)
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface .
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | ○ Attach: Pre-pour Inspection Record
label | METHOD: Verify
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.4 Concrete placement
label | REFERENCE: VicRoads: Cl 703.08, Cl 703.23
label | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | ○ Attach: Concrete Pour Records
label | METHOD: Site inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.5 Transitions
label | REFERENCE: VicRoads: Cl 703.24
label | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
label | METHOD: Site inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.6 Surface Finish
label | REFERENCE: VicRoads: Cl 703.25 AS 3610
label | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/ Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.7 Formwork Stripping
label | REFERENCE: VicRoads: Cl 703.12 AS 3610
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | – External faces 2 days
label | – Permanently hidden faces 1 day
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/ Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.8 Tolerance
label | REFERENCE: VicRoads: Cl 703.15
label | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings.
label | ○ Section dimensions shall not differ from those shown on the drawings by more than 5 mm except that overall width shall not exceed the specified width by more than 15 mm , for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm. Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | METHOD: Verify
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Surveyor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.9 Curing
label | REFERENCE: VicRoads: Cl 703.10
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete.
label | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.10 Joints
label | REFERENCE: VicRoads: Cl 703.26 (a)(i) (c)
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | METHOD: Verify
label | FREQUENCY: Each joint
label | CATEGORY: IP
label | RESPONSIBILITY: SE / Site Supervisor
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.11 Protection of Concrete
label | REFERENCE: VicRoads: Cl 703.27
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 5.12 Bus Stop Kerb Height
label | REFERENCE: DoT Handover Process
label | ACCEPTANCE CRITERIA: Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
label | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
label | METHOD: Visual Inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Backfilling
label | REFERENCE: VicRoads: Cl 703.29
label | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | METHOD: Verify
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 6.2 Cracking of Concrete
label | REFERENCE: VicRoads: Cl 703.30
label | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width, greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | ○ Attach: Pot-pour Inspection Record
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
date | Date Completed:
checkpoint | 6.3 Survey Conformance
label | REFERENCE: VicRoads: Cl 703.15
label | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | ○ Attach: as-built survey records
label | METHOD: Document Review
label | FREQUENCY: Completion of each lot
label | CATEGORY: WP
label | RESPONSIBILITY: Project Engineer/ Surveyor
label | VERIFYING DOCUMENTS: As-built survey records
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install) | itp |  |  |  |  | ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-211-CIV-SSO-Subsurface Drainage (Supply and Install)
label | ITP Description: SSO-Subsurface Drainage (Supply and Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 24/10/2024
label | ITP created by: Dimitri Santoreneos
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads Section 702 (May 2019)
label | 1.2 Non Dependent
label | Reference: VicRoads Section 204 (Dec 2015)
label | 1.3 Non Dependent
label | Reference: VicRoads SD1611
label | 1.4 Non Dependent
label | Reference: VicRoads SD1051
label | 1.5 Non Dependent
label | Reference: VicRoads SD1631
section | Preliminaries - Materials
checkpoint | 2.1 Drainage Pipes
label | REFERENCE: IFC Drawings VicRoads: Cl 702.04
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: Category 1: 100mm DIA Class 1000 corrugated perforated plastic pipe. Perforation size of maximum 1.5mm width and minimum length of 150 mm per m2.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Each Lot prior to work start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Granular Filter Material
label | REFERENCE: IFC Drawings VicRoads: Cl 702.05 Table 702.051
label | ACCEPTANCE CRITERIA: Granular filter material: Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accredited with VicRoads.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Each Lot prior to work start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 No Fines Concrete
label | REFERENCE: IFC Drawings VicRoads: Cl 702.05
label | ACCEPTANCE CRITERIA: No Fines Concrete: Shall be grade B4 in accordance with RC500.22, section 6.3 and shall comply with VicRoads Cl 702.05 (e)
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Each Lot prior to work start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Geotextile Filter
label | REFERENCE: IFC Drawings VicRoads: Cl 702.06 Table 702.061
label | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with VicRoas Cl 702.06 and Table 702.061 of the requirements for Geotextile Filter
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Each Lot prior to work start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 SSD Pits, Pit Lids, Flushout Risers
label | REFERENCE: IFC Drawings SD-1051, SD-1611, SD-1631
label | ACCEPTANCE CRITERIA: Subsurface drain pits: shall be Type S1 (as per SD 1611).
label | ○ Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
label | ○ Flushout risers: As per VicRoads, SD 1631
textbox | Enter: Teambinder Material Approval number
label | METHOD: Verify, Document Review
label | FREQUENCY: Each Lot prior to work start
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Preliminaries - Documentations
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision (as per TeamBinder)
label | METHOD: Visual inspection
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: WP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set Out
label | REFERENCE: IFC Drawings VicRoads: Cl 702.03
label | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor, Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Trench Excavation
label | REFERENCE: VicRoads: Cl 702.08
label | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | ○ The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
label | METHOD: Visual Inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, NA (Nominated Authority)
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 Placement of bedding
label | REFERENCE: VicRoads: Cl 702.09 c)
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
label | ○ Attach: bedding material delivery dockets
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.3 Pipe and Geotextile Installation (if required)
label | REFERENCE: VicRoads: Cl 702.03, Cl 702.09
label | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | ○ Attach: Suburface pipe and geotextile delievery dockets (if applicable)
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.4 Backfill Installation (Granular Filter Material)
label | REFERENCE: VicRoads: Cl 702.09 (g)
label | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
label | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | ○ Attach: Backfill Delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE, NA
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.5 Backfill Installation (No Fines)
label | REFERENCE: VicRoads: Cl 702.09 (g)
label | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
label | ○ Attach: Backfill Delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE, NA
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.6 Install Pits and Flushouts
label | REFERENCE: VicRoads: Cl 702.10
label | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run.
label | ○ Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
label | ○ Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | ○ Attach: Pit and Flushout Delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.7 Marker Posts
label | REFERENCE: VicRoads: Cl 702.11
label | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | ○ Attach: Marker Post Delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each outlet
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As Built Information
label | REFERENCE: VicRoads: Cl 702.03
label | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
label | ○ Attach: Survey Conformance Report
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 6.2 Flushing
label | REFERENCE: VicRoads: Cl 702.09 (h)
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | ○ Attach: Flushing Tests Records
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, NA
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 Inspection of Subsurface Drainage - CCTV
label | REFERENCE: VicRoads: Cl 702.09 (i)
label | ACCEPTANCE CRITERIA: All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
label | ○ Attach: CCTV Inspection Record
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, NA
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP