## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | INF-HSEQ CC0375-ITP-027 Guardrail and Fence - Rev.1 | itp | INF-HSEQ CC0375-ITP-027 Guardrail and Fence - Rev.1 |  | d845b96a-d7fb-4e97-8ce3-59dbc94bb117
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Documentation
e39cf4ac-600e-598e-867b-899eb1dde377 | note | Ref docs - Issued drawings / Site copy drawings
647090de-0eb3-5325-98f9-83bb6134cbb5 | note | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
dd756a1b-1345-5e4a-869b-a16bc49fbc6d | button | Acceptance | Yes,No,N/A
fe859caa-80c2-562a-a8a7-38c69c9a08af | note | Key - S
a4a3679a-9f91-5b30-8dd7-dbe42cebdda8 | note | HPP CON Key - S
6505bc55-d980-5fbc-8c8f-d41f13afa4fc | note | HPP QA Key - S
| checkpoint | 1.2 - Lot Traceability
b246b63a-829b-5b98-a260-cc29724964c1 | note | Ref docs - Spec. 0161 Quality [Cl 7.3]
bdb6c160-0efc-5e67-8f54-debcba4082e6 | note | Acceptance criteria - Prepare a lot map for traceability of the work area
f2d72e19-f40a-568e-a9d8-1a39551cf8d1 | button | Acceptance | Yes,No,N/A
3731d815-c1c8-5625-8c8b-74ca65a9cabe | note | Key - S
12d8b525-f150-5cec-a30a-bfa311bbe3e0 | note | HPP CON Key - S
c66bb236-a965-5eb8-8824-9343aa7d868a | note | HPP QA Key - S
77657394-f9c4-5889-a5ff-c0229b5170d0 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
46871d28-3a73-5900-ae0e-44d210d29e7c | tickbox | Lot map
| checkpoint | 1.3 - Material
898b7585-1402-5173-a9c3-7c651054d764 | note | Ref docs - Drawings
10df8617-e42e-597e-bc7e-286847de3aa0 | note | Acceptance criteria - Correct class & type of rail or fence been supplied and free of defects
51d78501-1bc1-54f4-8f56-e9d336f37503 | button | Acceptance | Yes,No,N/A
63f6dac3-192e-50ca-a632-036f04f17242 | note | Key - S
41471d82-5c9f-51a2-9d85-0c42e596df58 | note | HPP CON Key - S
fd9ecffb-c0e9-5d32-b077-9ab0bef83d01 | note | HPP QA Key - S
| checkpoint | 1.4 - Underlying Lot Conformance
6761d2df-ba7e-5923-832d-92eefd302d9f | note | Ref docs - Underlying Lot ITP
33b45e45-2b9a-5e6f-959d-feecd48b0675 | note | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
78774b56-4b4d-5fac-95a1-64dd825ccbe4 | note | ○ Refer underlying lot ITP(s)
e1d2a738-02a1-5128-ad15-962eccb0a62a | button | Acceptance | Yes,No,N/A
1360681f-4ecf-57e5-9da1-d7dc8992f2d2 | note | Key - S
1563d245-ba2b-5bf2-871e-3f951bea55e8 | note | HPP CON Key - S
e6dd3045-e953-50d4-ad4c-309dbc0226f9 | note | HPP QA Key - S
| checkpoint | 1.5 - Set out
3d58dda5-7433-5834-af02-909cb5bd790a | note | Ref docs - Drawings
091507a8-1646-5b8b-af71-7b38cf594763 | note | Acceptance criteria - Setout rail positions to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
009d1044-a483-5af2-a41d-5f110aa5597b | button | Acceptance | Yes,No,N/A
af018da9-e54a-5eb9-88ae-93c4d4780aff | note | Key - S
bde0a0dd-c86d-5d57-afc3-287ddddbadac | note | HPP CON Key - S
b3dc19c5-0834-5bc4-b9d4-0e5f433c90af | note | HPP QA Key - S
| checkpoint | 1.6 - Site checklist(s)
| note | Acceptance criteria - Have Site checklist(s) been signed and uploaded?
| button | Acceptance | Yes,No,N/A
| note | HPP CON Key - S
| note | HPP QA Key - S
| note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
| tickbox | Site Checklist(S)
| section | 2.0 Installation
| checkpoint | 2.1 - Location and length
a7872145-bce1-55ba-ab54-57517f1ded9b | note | Ref docs - Construction drawings
0c16aae9-1136-516a-9e6b-087cd3f6d8a4 | note | Acceptance criteria - Length and location confirmed by the Superintendent
15608712-d33d-535b-b279-5fc246538889 | button | Acceptance | Yes,No,N/A
23e8f158-0b82-552c-b756-dbc00e5fd3cf | note | Key - S
cb5a8941-0660-54f7-9414-9960d2846636 | note | HPP CON Key - S
a587a30c-328e-5d66-8471-fa5e62337ac0 | note | HPP QA Key - S
| checkpoint | 2.2 - Install
fd98dc6c-4863-5365-9cb2-7b83484de240 | note | Ref docs - Construction drawings
04f31ddc-a59b-5e17-ace7-b76d43c848d0 | note | Acceptance criteria - Guard rail or fence run been installed as per the relevant specifications and drawings
0034e818-a868-5589-a985-9c3682724de7 | button | Acceptance | Yes,No,N/A
8d91c1c5-c22b-5819-a70c-a19bc83735a5 | note | Key - S
f73ce631-68bd-50d6-be29-27ded1aec019 | note | HPP CON Key - S
44870a4e-c98d-5310-83b0-f6986b9214fe | note | HPP QA Key - S
| section | 3.0 Conformance check
| checkpoint | 3.1 - Survey Report
06bfc395-210e-5f71-bbc9-7319bdeb1a27 | note | Ref docs - Spec. 0161 Quality [Cl 3.13]
fd78cf43-4295-5a79-8db7-7d589c049377 | note | Acceptance criteria - +/- 25mm Specified Level
3411d47e-12d6-5e67-b3d0-f7dca1199401 | note | ○ +/- 50mm Specified Line
91f71439-552e-55c3-aac3-f8608bc955e2 | note | ○ Notwithstanding above specs, line and level of guard fence shall be adjusted where necessary to provide a smooth and even vertical and horizontal alignment
3fbc4920-a902-58b9-9099-e8d0837d4820 | button | Acceptance | Yes,No,N/A
954add99-dd72-5bf8-9580-44798824e93d | note | Key - R
7c32eba6-a85a-5126-8505-2cfdbb43683b | note | HPP CON Key - R
4d4dfa2c-2f04-5427-9718-f74bb6347f22 | note | HPP QA Key - R
00551019-9922-53c0-98eb-e8ece8281f98 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
0414f6fe-3186-57f3-a35f-1d143809f1f3 | tickbox | Survey report
| checkpoint | 3.2 - Acceptance and closure of non-conforming items
4ce20cbf-2afe-56d3-962a-f4c357a8f0d0 | note | Ref docs - Spec. 0161 Quality [Cl 3.8]
85793979-bd01-5f11-860a-48460cb9a06d | note | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
9071698b-5397-5c0b-bfab-65cc5077418c | note | HOLD POINT
74d27bb0-5b22-5793-ad20-7a8b471979c9 | button | Acceptance | Yes,No,N/A
132448f8-2cd1-584d-adcc-bea0e00c3929 | note | Key - H
b3ea1790-a3a8-5a24-987c-17b60eaf2934 | note | HPP CON Key - H
86d79593-66fa-57b7-b3c6-af4b0cb94185 | note | HPP QA Key - H
| signoff | AUTHORITY HOLDPOINT