## Sheet1
2.1 | Drainage Pipes | IFC Drawings VicRoads: Cl 702.04 | Subsurface drainage pipes: Category 1: 100mm DIA Class 1000 corrugated perforated plastic pipe. Perforation size of maximum 1.5mm width and minimum length of 150 mm per m2. Enter: Teambinder Material Approval number [free text box] | Verify, Document Review | Each Lot prior to work start | HP | Nominated Authority | Conqa HP Release | 2.1 Drainage Pipes | REFERENCE: IFC Drawings VicRoads: Cl 702.04 | ACCEPTANCE CRITERIA: Subsurface drainage pipes: Category 1: 100mm DIA Class 1000 corrugated perforated plastic pipe. Perforation size of maximum 1.5mm width and minimum length of 150 mm per m2. Enter: Teambinder Material Approval number [free text box] | METHOD: Verify, Document Review | FREQUENCY: Each Lot prior to work start | CATEGORY: HP | RESPONSIBILITY: Nominated Authority | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | 2.1 Drainage Pipes
2.2 | Granular Filter Material | IFC Drawings VicRoads: Cl 702.05 Table 702.051 | Granular filter material: Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accredited with VicRoads. Enter: Teambinder Material Approval number [free text box] | Verify, Document Review | Each Lot prior to work start | HP | Nominated Authority | Conqa HP Release | 2.2 Granular Filter Material | REFERENCE: IFC Drawings VicRoads: Cl 702.05 Table 702.051 | ACCEPTANCE CRITERIA: Granular filter material: Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accredited with VicRoads. Enter: Teambinder Material Approval number [free text box] | METHOD: Verify, Document Review | FREQUENCY: Each Lot prior to work start | CATEGORY: HP | RESPONSIBILITY: Nominated Authority | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | REFERENCE: IFC Drawings VicRoads: Cl 702.04
2.3 | No Fines Concrete | IFC Drawings VicRoads: Cl 702.05 | No Fines Concrete: Shall be grade B4 in accordance with RC500.22, section 6.3 and shall comply with VicRoads Cl 702.05 (e) Enter: Teambinder Material Approval number [free text box] | Verify, Document Review | Each Lot prior to work start | HP | Nominated Authority | Conqa HP Release | 2.3 No Fines Concrete | REFERENCE: IFC Drawings VicRoads: Cl 702.05 | ACCEPTANCE CRITERIA: No Fines Concrete: Shall be grade B4 in accordance with RC500.22, section 6.3 and shall comply with VicRoads Cl 702.05 (e) Enter: Teambinder Material Approval number [free text box] | METHOD: Verify, Document Review | FREQUENCY: Each Lot prior to work start | CATEGORY: HP | RESPONSIBILITY: Nominated Authority | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | ACCEPTANCE CRITERIA: Subsurface drainage pipes: Category 1: 100mm DIA Class 1000 corrugated perforated plastic pipe. Perforation size of maximum 1.5mm width and minimum length of 150 mm per m2. Enter: Teambinder Material Approval number [free text box]
2.4 | Geotextile Filter | IFC Drawings VicRoads: Cl 702.06 Table 702.061 | Geotextiles: Shall comply with VicRoas Cl 702.06 and Table 702.061 of the requirements for Geotextile Filter Enter: Teambinder Material Approval number [free text box] | Verify, Document Review | Each Lot prior to work start | HP | Nominated Authority | Conqa HP Release | 2.4 Geotextile Filter | REFERENCE: IFC Drawings VicRoads: Cl 702.06 Table 702.061 | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with VicRoas Cl 702.06 and Table 702.061 of the requirements for Geotextile Filter Enter: Teambinder Material Approval number [free text box] | METHOD: Verify, Document Review | FREQUENCY: Each Lot prior to work start | CATEGORY: HP | RESPONSIBILITY: Nominated Authority | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | METHOD: Verify, Document Review
2.5 | SSD Pits, Pit Lids, Flushout Risers | IFC Drawings SD-1051 SD-1611 SD-1631 | Subsurface drain pits: shall be Type S1 (as per SD 1611). Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit. Flushout risers: As per VicRoads, SD 1631 Enter: Teambinder Material Approval number [free text box] | Verify, Document Review | Each Lot prior to work start | HP | Nominated Authority | Conqa HP Release | 2.5 SSD Pits, Pit Lids, Flushout Risers | REFERENCE: IFC Drawings SD-1051 SD-1611 SD-1631 | ACCEPTANCE CRITERIA: Subsurface drain pits: shall be Type S1 (as per SD 1611). Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit. Flushout risers: As per VicRoads, SD 1631 Enter: Teambinder Material Approval number [free text box] | METHOD: Verify, Document Review | FREQUENCY: Each Lot prior to work start | CATEGORY: HP | RESPONSIBILITY: Nominated Authority | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | FREQUENCY: Each Lot prior to work start
3.1 | Check for correct documentation | IFC Drawings | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision (as per TeamBinder) | Visual inspection | Prior to commencing any activity | WP | SE/Site Supervisor | This ITP Signed-off | 3.1 Check for correct documentation | REFERENCE: IFC Drawings | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision (as per TeamBinder) | METHOD: Visual inspection | FREQUENCY: Prior to commencing any activity | CATEGORY: WP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | CATEGORY: HP
4.1 | Survey Set Out | IFC Drawings VicRoads: Cl 702.03 | Survey to set out Subsurface Drainage line. | Visual inspection | Each Lot | IP | SE/Site Supervisor Surveyor | This ITP Signed-off | 4.1 Survey Set Out | REFERENCE: IFC Drawings VicRoads: Cl 702.03 | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line. | METHOD: Visual inspection | FREQUENCY: Each Lot | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor Surveyor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | RESPONSIBILITY: Nominated Authority
5.1 | Trench Excavation | VicRoads: Cl 702.08 | The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe. There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed. The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations. | Visual Inspection | Each lot | HP | SE, NA (Nominated Authority) | Conqa HP Release | 5.1 Trench Excavation | REFERENCE: VicRoads: Cl 702.08 | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe. There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed. The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations. | METHOD: Visual Inspection | FREQUENCY: Each lot | CATEGORY: HP | RESPONSIBILITY: SE, NA (Nominated Authority) | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | VERIFYING DOCUMENTS: Conqa HP Release
5.2 | Placement of bedding | VicRoads: Cl 702.09 c) | Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level. Attach: bedding material delivery dockets | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP Signed-off | 5.2 Placement of bedding | REFERENCE: VicRoads: Cl 702.09 c) | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level. Attach: bedding material delivery dockets | METHOD: Visual inspection | FREQUENCY: Each lot | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | Date Completed:
5.3 | Pipe and Geotextile Installation (if required) | VicRoads: Cl 702.03 Cl 702.09 | Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements. Attach: Suburface pipe and geotextile delievery dockets (if applicable) | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP Signed-off | 5.3 Pipe and Geotextile Installation (if required) | REFERENCE: VicRoads: Cl 702.03 Cl 702.09 | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements. Attach: Suburface pipe and geotextile delievery dockets (if applicable) | METHOD: Visual inspection | FREQUENCY: Each lot | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | 2.2 Granular Filter Material
5.4 | Backfill Installation (Granular Filter Material) | VicRoads: Cl 702.09 (g) | Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA. Attach: Backfill Delivery Dockets | Visual | Each lot | HP* | SE, NA | This ITP Signed-off | 5.4 Backfill Installation (Granular Filter Material) | REFERENCE: VicRoads: Cl 702.09 (g) | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA. Attach: Backfill Delivery Dockets | METHOD: Visual | FREQUENCY: Each lot | CATEGORY: HP* | RESPONSIBILITY: SE, NA | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | REFERENCE: IFC Drawings VicRoads: Cl 702.05 Table 702.051
5.5 | Backfill Installation (No Fines) | VicRoads: Cl 702.09 (g) | All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing. Attach: Backfill Delivery Dockets | Visual | Each lot | HP* | SE, NA | This ITP Signed-off | 5.5 Backfill Installation (No Fines) | REFERENCE: VicRoads: Cl 702.09 (g) | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing. Attach: Backfill Delivery Dockets | METHOD: Visual | FREQUENCY: Each lot | CATEGORY: HP* | RESPONSIBILITY: SE, NA | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | ACCEPTANCE CRITERIA: Granular filter material: Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accredited with VicRoads. Enter: Teambinder Material Approval number [free text box]
5.6 | Install Pits and Flushouts | VicRoads: Cl 702.10 | Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings. Attach: Pit and Flushout Delivery Dockets | Visual | Each lot | WP | SE/Site Supervisor | This ITP Signed-off | 5.6 Install Pits and Flushouts | REFERENCE: VicRoads: Cl 702.10 | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings. Attach: Pit and Flushout Delivery Dockets | METHOD: Visual | FREQUENCY: Each lot | CATEGORY: WP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | METHOD: Verify, Document Review
5.7 | Marker Posts | VicRoads: Cl 702.11 | At all fill batter and drain outlets, supply and erect marker posts as shown on drawings Attach: Marker Post Delivery Dockets | Visual | Each outlet | IP | SE/Site Supervisor | This ITP Signed-off | 5.7 Marker Posts | REFERENCE: VicRoads: Cl 702.11 | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings Attach: Marker Post Delivery Dockets | METHOD: Visual | FREQUENCY: Each outlet | CATEGORY: IP | RESPONSIBILITY: SE/Site Supervisor | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | FREQUENCY: Each Lot prior to work start
6.1 | As Built Information | VicRoads: Cl 702.03 | The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length. Attach: Survey Conformance Report | Document Review | Each lot | IP | Surveyor SE/PE/SPE | This ITP Signed-off | 6.1 As Built Information | REFERENCE: VicRoads: Cl 702.03 | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length. Attach: Survey Conformance Report | METHOD: Document Review | FREQUENCY: Each lot | CATEGORY: IP | RESPONSIBILITY: Surveyor SE/PE/SPE | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | CATEGORY: HP
6.2 | Flushing | VicRoads: Cl 702.09 (h) | Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture. Attach: Flushing Tests Records | Document Review | Each lot | HP | SE, NA | Conqa HP Release | 6.2 Flushing | REFERENCE: VicRoads: Cl 702.09 (h) | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture. Attach: Flushing Tests Records | METHOD: Document Review | FREQUENCY: Each lot | CATEGORY: HP | RESPONSIBILITY: SE, NA | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | RESPONSIBILITY: Nominated Authority
6.3 | Inspection of Subsurface Drainage - CCTV | VicRoads: Cl 702.09 (i) | All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects. Attach: CCTV Inspection Record | Document Review | Each lot | HP | SE, NA | Conqa HP Release | 6.3 Inspection of Subsurface Drainage - CCTV | REFERENCE: VicRoads: Cl 702.09 (i) | ACCEPTANCE CRITERIA: All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects. Attach: CCTV Inspection Record | METHOD: Document Review | FREQUENCY: Each lot | CATEGORY: HP | RESPONSIBILITY: SE, NA | VERIFYING DOCUMENTS: Conqa HP Release | Date Completed: | VERIFYING DOCUMENTS: Conqa HP Release
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off | 6.4 Non-conformance Report (NCR) Closure | REFERENCE: MRPA Quality Management Plan | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs. | METHOD: Document Review | FREQUENCY: Once, prior to closure of this lot / element / Work area | CATEGORY: HP* | RESPONSIBILITY: SE/PE/SPE | VERIFYING DOCUMENTS: This ITP Signed-off | Date Completed: | Date Completed:
2.3 No Fines Concrete
REFERENCE: IFC Drawings VicRoads: Cl 702.05
ACCEPTANCE CRITERIA: No Fines Concrete: Shall be grade B4 in accordance with RC500.22, section 6.3 and shall comply with VicRoads Cl 702.05 (e) Enter: Teambinder Material Approval number [free text box]
METHOD: Verify, Document Review
FREQUENCY: Each Lot prior to work start
CATEGORY: HP
RESPONSIBILITY: Nominated Authority
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
2.4 Geotextile Filter
REFERENCE: IFC Drawings VicRoads: Cl 702.06 Table 702.061
ACCEPTANCE CRITERIA: Geotextiles: Shall comply with VicRoas Cl 702.06 and Table 702.061 of the requirements for Geotextile Filter Enter: Teambinder Material Approval number [free text box]
METHOD: Verify, Document Review
FREQUENCY: Each Lot prior to work start
CATEGORY: HP
RESPONSIBILITY: Nominated Authority
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
2.5 SSD Pits, Pit Lids, Flushout Risers
REFERENCE: IFC Drawings SD-1051 SD-1611 SD-1631
ACCEPTANCE CRITERIA: Subsurface drain pits: shall be Type S1 (as per SD 1611). Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit. Flushout risers: As per VicRoads, SD 1631 Enter: Teambinder Material Approval number [free text box]
METHOD: Verify, Document Review
FREQUENCY: Each Lot prior to work start
CATEGORY: HP
RESPONSIBILITY: Nominated Authority
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
3.1 Check for correct documentation
REFERENCE: IFC Drawings
ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision (as per TeamBinder)
METHOD: Visual inspection
FREQUENCY: Prior to commencing any activity
CATEGORY: WP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
4.1 Survey Set Out
REFERENCE: IFC Drawings VicRoads: Cl 702.03
ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
METHOD: Visual inspection
FREQUENCY: Each Lot
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor Surveyor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.1 Trench Excavation
REFERENCE: VicRoads: Cl 702.08
ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe. There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed. The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
METHOD: Visual Inspection
FREQUENCY: Each lot
CATEGORY: HP
RESPONSIBILITY: SE, NA (Nominated Authority)
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
5.2 Placement of bedding
REFERENCE: VicRoads: Cl 702.09 c)
ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level. Attach: bedding material delivery dockets
METHOD: Visual inspection
FREQUENCY: Each lot
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.3 Pipe and Geotextile Installation (if required)
REFERENCE: VicRoads: Cl 702.03 Cl 702.09
ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements. Attach: Suburface pipe and geotextile delievery dockets (if applicable)
METHOD: Visual inspection
FREQUENCY: Each lot
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.4 Backfill Installation (Granular Filter Material)
REFERENCE: VicRoads: Cl 702.09 (g)
ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA. Attach: Backfill Delivery Dockets
METHOD: Visual
FREQUENCY: Each lot
CATEGORY: HP*
RESPONSIBILITY: SE, NA
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.5 Backfill Installation (No Fines)
REFERENCE: VicRoads: Cl 702.09 (g)
ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing. Attach: Backfill Delivery Dockets
METHOD: Visual
FREQUENCY: Each lot
CATEGORY: HP*
RESPONSIBILITY: SE, NA
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.6 Install Pits and Flushouts
REFERENCE: VicRoads: Cl 702.10
ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings. Attach: Pit and Flushout Delivery Dockets
METHOD: Visual
FREQUENCY: Each lot
CATEGORY: WP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
5.7 Marker Posts
REFERENCE: VicRoads: Cl 702.11
ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings Attach: Marker Post Delivery Dockets
METHOD: Visual
FREQUENCY: Each outlet
CATEGORY: IP
RESPONSIBILITY: SE/Site Supervisor
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
6.1 As Built Information
REFERENCE: VicRoads: Cl 702.03
ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length. Attach: Survey Conformance Report
METHOD: Document Review
FREQUENCY: Each lot
CATEGORY: IP
RESPONSIBILITY: Surveyor SE/PE/SPE
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed:
6.2 Flushing
REFERENCE: VicRoads: Cl 702.09 (h)
ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture. Attach: Flushing Tests Records
METHOD: Document Review
FREQUENCY: Each lot
CATEGORY: HP
RESPONSIBILITY: SE, NA
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
6.3 Inspection of Subsurface Drainage - CCTV
REFERENCE: VicRoads: Cl 702.09 (i)
ACCEPTANCE CRITERIA: All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects. Attach: CCTV Inspection Record
METHOD: Document Review
FREQUENCY: Each lot
CATEGORY: HP
RESPONSIBILITY: SE, NA
VERIFYING DOCUMENTS: Conqa HP Release
Date Completed:
6.4 Non-conformance Report (NCR) Closure
REFERENCE: MRPA Quality Management Plan
ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
METHOD: Document Review
FREQUENCY: Once, prior to closure of this lot / element / Work area
CATEGORY: HP*
RESPONSIBILITY: SE/PE/SPE
VERIFYING DOCUMENTS: This ITP Signed-off
Date Completed: